## XCTFIN209A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-09-10 |  | Version 4.6 | 2014-04-08
India |  | Project/Program Title: | Rajasthan Renewable Energy Transmission Investmet Program
Implementing MDB 1: |  |  | ADB | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFIN209A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 200 | [6 empty] | Project lifetime: | 25 | years
Date of First MDB Approval: |  |  | 2013-09-01 | [6 empty] | Expected Reporting Closure Date: | 2018-10-01
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 135000000 | 135000000 | 5400000 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Target tons of GHG emissions reduced or avoided: 5,400,000 ton CO2e per year. Assuming a conservative grid emissions factor of 0.7 tons CO2e / MW-h from 4,300 MW. Over a time-period of 25 years (useful lifetime of transmission projects are significantly higher than 25 years), avoided emissions will be about 135 million tons CO2e
Total Project size in US million $ |  | 800 | 800 | 800 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
B2. Volume of direct finance leveraged through CTF funding | million USD | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB |  |  | 300 | 300 | 0 | 0
Other MDB (please specify)
Government |  |  | 300 | 300 |  | 0
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other).
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 4300 | 4300 | 4300 |  | 0
Wind
Solar
Hydro
Geothermal
Other/ Mixed |  |  | 4300 | 4300 |  | 0 | [5 empty] | 0
Describe method of calculation | Transmission lines. The project will support the development of the in-state transmission network to evacuate and transmit atleast 4300 MW of new renewable energy capacity.
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Employment opportunities | No. of people |  | nts | nts |  | 0 | [5 empty] | 0
Describe the development co-benefits | Substantial employment opportunities will be created during construction and implementation period. The project will also support livelihood opportunities for communities is western rajasthan.
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain. 2014: NO
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: Not yet effective

## XCTFPH059A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-09-10 |  | Version 4.6 | 2014-04-08
Philippines |  | Project/Program Title: | Energy Efficient Electric Vehicles project
Implementing MDB 1: |  |  | ADB | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFPH059A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 105 | [6 empty] | Project lifetime: | 10 | years
Date of First MDB Approval: |  |  | 2012-12-01 | [6 empty] | Expected Reporting Closure Date: | 2017-12-01
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 2700000 | 2700000 | 270000 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Target tons of GHG emissions reduced or avoided: 270,000 ton CO2e per year. The reduction per vehicle is 2.69 tCO2e/year or 0.27 million tCO2e/year for the 100,000 vehicle fleet. Assumptions: Vehicle operation per day is 80 km; vehicle mileage is 15 km/liter; vehicle operation is 300 days/year; e-trike electricity consumption is 6 KWh/day; and emission factor of grid is 0.52 tCO2e/MWh. With 10 -year vehicle lifetime, the total GHG emission reduced will be 2.7 Million tCO2e.
Total Project size in US million $ |  | 504 | 504 | 504 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
B2. Volume of direct finance leveraged through CTF funding | million USD | 399 | 399 | 399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB |  | 300 | 300 | 300 | 0 | 0
Other MDB (please specify)
Government |  | 99 | 99 | 99 | 0 | 0
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other).
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people/day | 700000 | 700000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [5 empty] | 0 | [5 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated | The EEEVs will showcase e-Trike; a 3-wheeled electric vehicle that is used to ferry a few passengers in short distances along side streets. The EEEVs will use lithium-ion battery technology with solar and grid-connected charging stations. E-Trike can accommodate 7 passengers; this is based on the maximum allowed passenger capacity of tricycles set by the government. Ordinary tricycles can accommodate 4 passengers. The 100,000 e-trike vehicles, each on a single travel with seven passengers can serve a total of up to 700,000 paassengers using low carbon transport.
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Employment Opportunities | No. of persons employed | 10000 | 10000 | 10000 | 0 | 0 | [5 empty] | 0
Describe the development co-benefits | The fabrication and assembly of e-trike will be done locally, the project could create a net employment gain of around 10,000 jobs by 2015.
Note: n.a. = not applicable n.t.s. = no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain. 2014: The project will likely receive payments for carbon credits after it is implemented.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: Project effective December 2013 The targets for passengers was increased 08/01/14

## XCTFVN091A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-09-10
Vietnam |  | Project/Program Title | Vietnam transport (HCMC)
|  | Implementing MDB 1: | ADB | [6 empty] | Project/Program ID (from CTF pipeline): | XCTFVN091A
|  | Implementing MDB 2: | [7 empty] | Project/Program ID (from CTF pipeline):
|  | Amount of CTF sub-project funding (million USD): | 50 | [6 empty] | Project lifetime: | 20 years
|  | Date of first MDB approval: | 2014-02-01 | [6 empty] | Expected Sub-Project Reporting Closure Date: | 2019-02-01
|  | Reporting period covered in this sheet: | July 1, 2013 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Report Year 2020
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 586500 | 586500 | 7127 |  | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Target tons of GHG emissions reduced or avoided: 29,300 ton CO2e per year. The GHG target ranges from 7,127 tCO2e in 2018 to 49,999 tCO2e by 2038, to get the annual target the annual average was used instead thus the target 29,300. The estimated cumulative emission reduction from 2018 to 2038 is 586,500 tCO2e. The TEEMP GHG analyses concluded that the MRT2 line would reduce emissions by about 0.12 ton CO2e per daily rider per year, which increases to about 0.16 ton CO2e per daily rider per year.
Total project size in US million $ | million USD | 66 | 66.05 | 66.05 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
B2. Volume of direct finance leveraged through CTF funding |  | 16 | 16.05 | 16.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB |  |  | 10 | 10
Other MDB (please specify)
Government |  |  | 6.05 | 6.05 | 0 | 0
Private sector
Bilateral
Other
Exchange rate used for non-US investments: | US$1=
Specify the source of direct finance (e.g., name of the private sector, bilateral agency and other)
B3. Installed capacity (MW) as a result of CTF interventions | MW | n.a. | n.a. | n.a. |  | n.a.
Wind
Solar
hydro
geothermal
Other/Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people per day | 30% public transport share | 412745 | 83824 |  | 0
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated | The analysis used in transport demand forecasts for the MRT Line 2 prepared in a 2010 feasibility study: 135,000 passengers per day in 2018, and 328,500 passengers per day in 2028. Using the feasibility study estimate of a post-2028 traffic growth rate of 3.5% per annum, the daily demand in 2038 was estimated to be 463,365 passengers per day. The demand estimates in terms of the project station entries and exits excluded transfers between other MRT lines. The daily demand in terms of passenger entries and exits at the project stations was estimated to be 128,960 passengers per day in 2018 and 412,745 passengers per day in 2038. The 2018 target of 83, 824 considers ramp-up discount of 65% in first year as used in TEEMP. These demand forecasts took into account incremental demand on MTR Line 2 expected to result from the project.
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Employment opportunities | No. of people | n.t.s. | n.t.s. | n.t.s. |  | 0
Describe the development co-benefits | employment opportunities will be created for bus drivers, ticket takers, security at stations
Does the project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain. 2014: NO
Please provide remarks for any indirect GHG emissions reduction and indirect finance leveraged. 2014: NO
General comments/project status (optional) 2014: Project not yet effective

## PCTFTH074A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-09-10 |  | Version 4.6 | 2014-04-08
Thailand |  | Project/Program Title: | Private Sector Renewable Energy program
Implementing MDB 1: |  |  | ADB | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFTH074A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 100 | Approved to todate: | 51.6 |  |  |  |  | Project lifetime: | 20 | years
Date of First MDB Approval: |  |  | 2012-06-25 | [6 empty] | Expected Reporting Closure Date: | 2022-06-01
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 20000000 | 2231520 | 2231520 | 0 | 105900 | [5 empty] | 105900
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Target tons of GHG emissions reduced or avoided: 111,000 ton CO2e per year (based on MDB approved subprojects' targets to date - 3 of 5 subprojects) Program emission reduction target is explained in this doc: https://www.climateinvestmentfunds.org/cif/sites/climateinvestmentfunds.org/files/CTF_Thailand_Private_Sector_RE_Program_Final_for_Submission_2012_04_09_Disclosure_version_FINAL.pdf
Total Project size in US million $ |  | 1000 | 234.6 | 234.6 | 101.16 | 234.16 | 234.16 | 234.16 | 234.16 | 234.16 | 234.16 | 234.16
B2. Volume of direct finance leveraged through CTF funding | million USD | 900 | 183 | 183 | 49.56 | 133 | 0 | 0 | 0 | 0 | 0 | 182.56
MDB |  |  | 81 | 81 | 24.36 | 57 | [5 empty] | 81.36
Other MDB (please specify)
Government
Private sector |  |  | 102 | 102 | 25.2 | 76 | [5 empty] | 101.2
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). | CTF co-financing for individual sub-projects will be priced in accordance with minimum concessionality principles
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 520 | 97 | 97 | 32 | 65 | [5 empty] | 97
Wind |  | 350 | 8 | 8 |  | 8 | [5 empty] | 8
Solar |  | 120 | 89 | 89 | 32 | 57 | [5 empty] | 89
Hydro
Geothermal
Other/ Mixed Waste |  | 50
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
No. of person employed during construction | person |  |  |  | 450 | 975 | [5 empty] | 1425
No. of person employed during commercial operation | person |  |  |  | 80 | 39
Describe the development co-benefits
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain. 2014: No
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional)
Note on C17: David Barton: "The total cost of projects to be supported by the Program is estimated to be $1 billion" https://www.climateinvestmentfunds.org/cif/sites/climateinvestmentfunds.org/files/CTF_Thailand_Private_Sector_RE_Program_Final_for_Submission_2012_04_09_Disclosure_version_FINAL.pdf

## PCTFID016A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-09-10 |  | Version 4.6 | 2014-04-08
Indonesia |  | Project/Program Title: | Private Sector Geothermal Energy Program
Implementing MDB 1: |  |  | ADB | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFID016A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 150 | Approved to date: | 80 |  |  |  |  | Project lifetime: | 20 | years
Date of First MDB Approval: |  |  | 2013-12-01 | [6 empty] | Expected Reporting Closure Date: | 2023-12-01
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 88000000 | 48000000 | 48000000 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Target tons of GHG emissions reduced or avoided: 2,270,000 ton CO2e per year (based on MDB approved subprojects' targets to date - 2 of 3 subprojects) Program emission reduction target explained in this doc: https://www.climateinvestmentfunds.org/cif/sites/climateinvestmentfunds.org/files/2013.09.16%20CTF%20Indo%20Geo%20program%20PUBLIC.pdf
Total Project size in US million $ |  | 2600 | 1707 | 1707 |  | 1706.5 | 1706.5 | 1706.5 | 1706.5 | 1706.5 | 1706.5 | 1706.5
B2. Volume of direct finance leveraged through CTF funding | million USD | 2450 | 1627 | 1627 |  | 1626.5 | 0 | 0 | 0 | 0 | 0 | 1626.5
MDB |  |  | 250 | 250 |  | 250 | [5 empty] | 250
Other MDB (please specify)
Government
Private sector |  |  | 823 | 823 |  | 822.5 | [5 empty] | 822.5
Bilateral |  |  | 534 | 534 |  | 534 | [5 empty] | 534
Other |  |  | 20 | 20 |  | 20 | [5 empty] | 20
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). | Bilateral - $534 million from the Japan Bank for International Cooperation Other - $20 million from the ADB Canadian Climate Fund for the Private Sector in Asia Under the Clean Energy Financing Partnership Facility
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 750 | 560 | 560 |  | 560 | [5 empty] | 560
Wind
Solar
Hydro
Geothermal |  | 750 | 560 | 560 |  | 560 | [5 empty] | 560
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
No. of person employed during construction | person |  | 200 | 200 |  | 239
No. of person employed during commercial operation | person
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain. FY2014: NO
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional)