## A Philippines EE Electric Vehic
Table A: Monitoring and Reporting for CTF Projects and Programs
Philippines |  | Project/Program Title: | Energy Efficient Electric Vehicles project
Implementing MDB 1: |  |  | ADB
Implementing MDB 2:
Amount of CTF funding (million USD): |  |  | 105
Date of First MDB Approval: |  |  | 2012-12-01 | [5 empty] | Expected Reporting Closure Date: | 2018-12-30
|  | Reporting period covered in this sheet: | From: July 01 | 2012 | To: June 30 | 2013
Please complete all cells colored
Core indicators | Unit | Target indicated at the time of TFC approval (cumulative over project lifetime) | Target indicated at the time of MDB approval (cumulative over project lifetime) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Report Year 2020
|  |  |  | Annual | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 2700000 | 2700000 | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Assumptions: Vehicle operation per day is 80 km; vehicle mileage is 15 km/liter; vehicle operation is 300 days/year; e-trike electricity consumption is 6 KWh/day; and emission factor of grid is 0.52 tCO2e/MWh. The reduction per vehicle is 2.69 tCO2e/year or 0.27 million tCO2e/year for the 100,000 vehicle fleet. With 10 -year vehicle lifetime, the total GHG emission reduced will be 2.7 Million tCO2e.
B2. Volume of direct finance leveraged through CTF funding | million USD | 399 | 399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB |  | 300 | 300 | 0
Government |  | 99 | 99 | 0
Private sector
Bilateral
Other
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other) and the exchange rate used for non-USD finance
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 0 | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a
|  |  | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a
|  |  | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a
|  |  | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a
Comment on methods of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people/day | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female |  | 300000 | 300000 | 0
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated | The EEEVs will showcase e-Trike; a 3-wheeled electric vehicle that is used to ferry a few passengers in short distances along side streets. The EEEVs will use lithium-ion battery technology with solar and grid-connected charging stations. E-Trike can accommodate 7 passengers; this is based on the maximum allowed passenger capacity of tricycles set by the government. Ordinary tricycles can accommodate 4 passengers. The 300,000 additional passengers per day is computed based on the added 3 passengers multiplied to the target 100,000 vehicles.
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh |  | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a | n.a
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Employment Opportunities | No. of persons employed | 10000 | 10000 | 0
Describe the development co-benefits | The fabrication and assembly of e-trike will be done locally, the project could create a net employment gain of around 10,000 jobs by 2015.
Please provide remarks, as appropriate, for any indirect GHG emissions reduction and indirect finance leveraged.

## BThailand PSRE Provincial Solar
Table B: Monitoring and Reporting for CTF Private Sector Sub-Projects | [10 empty] | PCTFTH074A
To be completed for each sub-project
Thailand | Program Title: | Private Sector Renewable Energy program
Private Sector Sub-Project Title: |  | Provincial Solar Power Project
Implementing MDB: |  | ADB
Amount of CTF sub-project funding (million USD): |  | 15
Date of Approval of Sub-Project by the MDB: |  | 2012-06-25 |  |  |  | Expected Sub-Project Reporting Closure Date: |  |  |  | 2014-12-30
| Reporting period covered in this sheet: | From: July 1 | 2012 | To: June 30 | 2013
Please complete all cells colored
Core indicators | Unit | Sub-project target indicated at the time of MDB approval (cumulative over project lifetime) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Report Year 2020
|  |  | Annual | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 380000 | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Assumptions: Average grid emissions factor is 0.55 tCO2e/MWh; Plants operations at 8,760 hours/year; and Plant load factor of 15%. The 380,000 tCO2e is based on the computed 38,000 tCO2e average avoidance per year multiplied by 10 years of initial operation (2013-2023).
B2. Volume of direct finance leveraged through CTF funding | million USD | 25.2 | 49.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB |  | 25.2 | 24.36
Government
Private sector |  |  | 25.2
Bilateral
Other
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other) and the exchange rate used for non-USD finance | The ADB approved total loan amount of up to US$ 25.20 M (B780 M). In the signed loan agreement (ADB-A Loan), the loan was reduced to US$ 24.36 M (B754 M). While, a local Thailand commercial bank co-financed an equivalent amount of up to US$ 25.20 M (B780 M). Exchange rate used: US$1=B30.95.
B3. Installed capacity (MW) as a result of CTF interventions | MW | 32 | 32
Identify technology and methods of calculation | The project involves the installation of 2 multicrystalline photovoltaic (PV) solar power plants operating under 4 standard RE power purchase agreements. Each plant has installed capacity of 8 MW. The target 32 MW solar power capacity was already achieved by first quarter of 2013.
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female |  |  | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Male |  |  | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
No. of person employed during construction | person | > 100 | 450
No. of person employed during commercial operation | person | > 80 | 80
Describe the development co-benefits | The project created direct employment opportunities. Skilled and unskilled laborers were hired during construction, while full time equivalent staff were employed during its commercial operation. The commercial operation commenced last March/April 2013.Results to be verified.
Please provide remarks, as appropriate, for any indirect GHG emissions reduction and indirect finance leveraged.