## Mexico TR - XCTFMX048A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-08-13 |  | Version 4.6 | 2014-04-08
Mexico |  | Project/Program Title: | Urban Transport Transformation Project
Implementing MDB 1: |  |  | IBRD | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFMX048A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 200 | [6 empty] | Project lifetime: | 20 | years
Date of First MDB Approval: |  |  | 2010-03-01 | [6 empty] | Expected Reporting Closure Date: | 2017-06-30
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 30000000 | 30000000 | 1960000 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 1,960,000 ton CO2e per year. Measurements of actual reductions will be made once projects become fully operational.
Total Project size in US million $ |  | 2694 | 2694 | 2694 | 1850 | 1850 | 1850 | 1850 | 1850 | 1850 | 1850 | 1850
B2. Volume of direct finance leveraged through CTF funding | million USD | 2494 | 2494 | 2494 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650
MDB (IBRD) |  | 150 | 150 | 150 | 11.6 | 0 | [5 empty] | 11.6
Other MDB (please specify)
Government |  | 737.5 | 737.5 | 737.5 | 460 | 0 | [5 empty] | 460
Private sector |  | 839 | 839 | 839 | 910 | 0 | [5 empty] | 910
Bilateral
Other; FONADIN |  | 767.5 | 767.5 | 767.5 | 268.4 | 0 | [5 empty] | 268.4
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). | Other: FONADIN (National Infrastructure Fund) |  |  |  | *Note: Figures based on actual disbursements from different sources *$15M disbursed under CTF; *IBRD $11.6 M; *PROTRAM $460M; *counterpart financing $910M; *the missing difference will be updated once the project is completed
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people/day | 3960000 | 3960000 | 3960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female |  | 1980000 | 1980000 | 1980000 |  | 0 | [5 empty] | 0
Male |  | 1980000 | 1980000 | 1980000 |  | 0 | [5 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Reduction in exposure to airborne pollutants |  |  |  |  | 0 | 0 | [5 empty] | 0
Increased Institutional capacity to implement lare-scale low-carbon projects |  |  |  |  | 0 | 0 | [5 empty] | 0
Reduction of energy intensity in transport sector |  |  |  |  | 0 | 0
Sustainable urban development |  |  |  |  | 0 | 0
Reduction of traffic accidents |  |  |  |  | 0 | 0
Describe the development co-benefits |  |  |  |  | Development indicators will be assessed upon completion of project
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: Implementation of sub-projects is progressing well in some cities. For instance, the CTF co-financed corridor improvement and bus rapid transit system is already complete and operational, respectively, in the city of Monterrey. Results indicators will be updated soon as part of the mid-term review of the project.

## Mexico EE - XCTFMX049A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-08-13 |  | Version 4.6 | 2014-04-08
Mexico |  | Project/Program Title: | Efficient Lighting and Appliance Project
Implementing MDB 1: |  |  | IBRD | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFMX049A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 50 | [6 empty] | Project lifetime: | 20 | years
Date of First MDB Approval: |  |  | 2010-11-01 | [6 empty] | Expected Reporting Closure Date: | 2014-06-30
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 7134000 | 7134000 | 1491000 | 992561 | 544834 | [5 empty] | 1537395
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 616,800. ton CO2e per year. *Additional 544,834 tons CO2 were avoided in 2013. Cumulative avoided from the project start till December 2013: 1,537,395 tons CO2; *1,048,710 (from avoided electricity consumption) + 488,685.10 (from capture of refrigerant gases).
Total Project size in US million $ |  | 713.44 | 713.325 | 713.325 | 305.63 | 305.63 | 305.63 | 305.63 | 305.63 | 305.63 | 305.63 | 305.63
B2. Volume of direct finance leveraged through CTF funding | million USD | 663.44 | 663.325 | 663.325 | 255.63 | 0 | 0 | 0 | 0 | 0 | 0 | 255.63
MDB (IBRD) |  |  | 250.625 | 250.625 | 250.63 | 0 | [5 empty] | 250.63
Other MDB (please specify)
Government |  |  | 102.7 | 102.7 | 0 | 0 | [5 empty] | 0
Private sector (Consumers) |  |  | 176 | 176 | 0 | 0 | [5 empty] | 0
Bilateral
Other |  |  | 134 | 134 | 5 | 0 | [5 empty] | 5
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). |  | "Other": NAFIN: ($127 million) GEF ($7 million) |  |  | *Note: Figures based on actual disbursements from different sources * IBRD dibursment $251M; $5M GEF; CTF disbursement $50M - fully disbursed; at this point no information on other co-financiers
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | 9600 | 9600 | 1200 | 802.1 | 1317.39 | [5 empty] | 2119.49
Comment on methods of calculation |  | Target: 1,200 GWh savings per year
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Climate and Ozone Co-benefits | CO2, NOx, SOx |  |  |  | 0 | 0 | [5 empty] | 0
Demonstration effect from scale (creating a high level of awareness in consumers and financiers) |  |  |  |  | 0 | [6 empty] | 0
Increased private sector participation (retailers, carbon funds) |  |  |  |  | 0 | 0 | [5 empty] | 0
increased affordability of efficient appliances(improved standard of living) |  |  |  |  | 0 | 0 | [5 empty] | 0
Economic benefits of reduced stratospheric ozone depletion including, improved human immune responses, improved disrupted growth processes in plants, and improved development in fish |  |  |  |  | 0 | 0 | [5 empty] | 0
Number or Staff trained |  | 20 | 20 | 20 | 0 | 0 | [5 empty] | 0
Describe the development co-benefits |  |  |  |  | Development indicators will be assessed upon completion of the project
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: An impact evaluation study is underway and an implementation completion report will be produced in FY16.

## Turkey - XCTFTR077A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-24 |  | Version 4.6 | 2014-04-08
Turkey |  | Project/Program Title: | Private Sector RE and EE Project
Implementing MDB 1: |  |  | IBRD | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFTR077A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 100 | [6 empty] | Project lifetime: | 20 | years
Date of First MDB Approval: |  |  | 2009-05-01 | [6 empty] | Expected Reporting Closure Date: | 2016-12-31
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 70140000 | 70140000 | 4707000 | 5595300 | 2925616 | [5 empty] | 8520916
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 3,507,000 ton CO2e per year. *Note that the values for the report year 2013 are cummulative, GHG emissions avoided from December 2009 until May 2013 *target value at project closing is a sum of Renewable Energy(2,071tCO2) + Energy Efficiency (1,436tCO2)
Total Project size in US million $ |  | 1550 | 1550 | 1550 | 935.9837 | 971.9837 | 971.9837 | 971.9837 | 971.9837 | 971.9837 | 971.9837 | 971.9837
B2. Volume of direct finance leveraged through CTF funding | million USD | 1450 | 1450 | 1450 | 835.9837 | 36 | 0 | 0 | 0 | 0 | 0 | 871.9837
MDB (IBRD) |  | 1000 | 1000 | 1000 | 835.9837 | 36 | [5 empty] | 871.9837
Other MDB (please specify)
Government
Private sector |  | 450 | 450 | 450 | 0 | 0 | [5 empty] | 0
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). |  |  | Project revised September 2011. Original at the Board approval was $800 million =IBRD $500 million+private sector $300 million.Additional financing was added $650= IBRD $500 M + privare sector $150 M |  | *private sector co-financing figures not yet available. | *private sector co-financing figures not yet available. IBRD funds are expected to be fully disbursed by the end of 2014
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 950 | 950 | 952 | 747 | 74 | 0 | 0 | 0 | 0 | 0 | 821
Wind |  |  |  | 225 | 157 | 54 | [5 empty] | 211
Solar | [11 empty] | 0
Hydro (Micro) |  |  |  | 700 | 556 | 20 | [5 empty] | 576
Geothermal |  |  |  | 26 | 34 | 0 | [5 empty] | 34
Other/ Mixed
Describe methods of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF |  | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female | [11 empty] | 0
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated | Project revised September 2011. Original target was revised to reflect the final target after additional financing. Breakdown by technology based on Implementation Status Reports. |  |  |  | *MW installed in 2013 | *numbers will be reviswed by the end of 2014
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | 25207 | 25207 | 1382 | 3253 | 1152 | [5 empty] | 4405
Comment on methods of calculation: | Target: 1,382 GWh savings per year Project revised in September 2011; Revised to 3495 Tcal by the end of project implementation ( 4064 GWh); 7231 GWh saved during project implementation (7 yr) and 1382 GWh per year thereafter (13 yr) over 20 years |  |  |  | * cumulative up to 2013 | *annual savings in 2014: 1152GWh; cumulative savings have already exceded the target
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Demonstration potential - Scope for avoided GHG emissions through replication
Enhanced energy security
Support to transition to clean energy
Increasing private sector involvement - in the development and financing of clean energy and energy efficiency investments
Reduced energy intensity of the economy
Reduced pollution and better air quality
Improved health (due to avoided adverse effects of pollution)
Labor-intensive renewable and energy efficiency projects provide employment (social benefits)
Describe the development co-benefits
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014:The project is on track to be closed on or before the originally envisaged closing date of December 31, 2014. The project has financed 44 Renewable Energy (RE) projects and 29 Energy Efficiency (EE) projects as of end May 2013. 2014: Revision based on Projet Paper dated Oct27,2011 in reaction to additional finance. Revision to B5 on Oct 24, 2014.

## Egypt - XCTFEG010A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-08-13 |  | Version 4.6 | 2014-04-08
Egypt |  | Project/Program Title: | Wind Power Development Project(Transmission)
Implementing MDB 1: |  |  | IBRD | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFEG010A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 140 | [6 empty] | Project lifetime: | 20 | years
Date of First MDB Approval: |  |  | 2010-06-01 | [6 empty] | Expected Reporting Closure Date: | 2015-12-31
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 28500000 | 28500000 | 1400000 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 1,400,000 ton CO2e per year. *target changed from 7,000,000 tons CO2 to 1,400,000 tons CO2, based on restructured project document
Total Project size in US million $ |  | 786 | 785.5 | 793.5 | 140 | 143.71 | 143.71 | 143.71 | 143.71 | 143.71 | 143.71 | 143.71
B2. Volume of direct finance leveraged through CTF funding | million USD | 646 | 645.5 | 653.5 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 3.71
MDB |  |  | 70 | 70 | 0 | 3.21 | [5 empty] | 3.21
Other MDB (please specify)
Government |  |  | 54.8 | 62.3 | 0 | 0 | [5 empty] | 0
Private sector |  |  | 450 | 450 | 0 | 0 | [5 empty] | 0
Bilateral |  |  | 70.7 | 70.7 | 0 | 0 | [5 empty] | 0
Other: PPIAF |  |  |  | 0.5 | 0 | 0.5 | [5 empty] | 0.5
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). |  | "Other" includes PPIAF, |  | * co-finaning numbers revised based on restructured project document | *The leveraged amount will be assessed upon comissioning of the transmission line (source: ISR;May 2014)
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 790 | 790 | 790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind |  | 790 | 790 | 790 | 0 | 0 | [5 empty] | 0
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation | Transmission line implemented through the project will facilitate the evacuation of 790MW intead of 2,500MW of wind power capacity (based on restructured project document)
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Critical transmission infrastructure necessary for private sector investments in generation |  |  |  |  | 0 | 0 | [5 empty] | 0
Total job creation in wind industry | number |  | n/a | 15200 | 0 | 0 | [5 empty] | 0
Local production facilities of the electrical components (cables, transformers) and wind turbine towers |  |  |  |  | 0 | 0 | [5 empty] | 0
Improved insitutional arrangements to facilitate further development of wind and solar projects (land use, customs duties, bank guarantees, foreign exchange denominated PPAs, and permitting ) |  |  |  |  | 0 | 0 | [5 empty] | 0
Supply Chain development | US$ |  | n/a | 198000000 | 0 | 0 | [5 empty] | 0
Improved quality and reliability of power supply to local consumers |  |  |  |  | 0 | 0 | [5 empty] | 0
Support for building up industrial infrastructure for future development |  |  |  |  | 0 | 0 | [5 empty] | 0
Female beneficiaries |  |  |  |  | 0 | 0 | [5 empty] | 0
Global environmental benefits |  |  |  |  | 0 | 0 | [5 empty] | 0
Describe the development co-benefits | *some indicators have target value in the ISR; other development indicators will be assessed upon completion of project |  |  |  | Development indicators will be assessed upon completion of project
Note: n.a. = not applicable n.t.s.=no target set n/a = not available
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional): 2014: Implementation is progressing well with the contract for the construction of the CTF-funded transmission line being signed in December 2013. Given the nature of this project, results will be achieved and reported toward the end of implementation. Project was restructured in June 2014. Target indicators are revised acordingly.
Note on C28: Gunta Niparte: in these two cells we had left 2500 but it should be 790;

## Indonesia - XCTFID017A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-08-13 |  | Version 4.6 | 2014-04-08
Indonesia |  | Project/Program Title: | Indonesia Geothermal Clean Energy Investment Project
Implementing MDB 1: |  |  | IBRD | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFID017A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 125 | [6 empty] | Project lifetime: | 30 | years
Date of First MDB Approval: |  |  | 2011-07-01 | [6 empty] | Expected Reporting Closure Date: | 2015-03-31
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 33000000 | 33000000 | 1100000 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 1,100,000 ton CO2e per year. *Avoided emissions can only be calculated after the power plant is commissioned
Total Project size in US million $ |  | 574.7 | 574.7 | 574.7 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
B2. Volume of direct finance leveraged through CTF funding | million USD | 449.7 | 449.7 | 449.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB |  | 175 | 175 | 175 | 0 | 0 | [5 empty] | 0
Other MDB (please specify) | [11 empty] | 0
Government |  | 274.7 | 274.7 | 274.7 | 0 | 0 | [5 empty] | 0
Private sector | [11 empty] | 0
Bilateral | [11 empty] | 0
Other | [11 empty] | 0
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other).
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar
Hydro
Geothermal |  | 150 | 150 | 150 | 0 | 0 | [5 empty] | 0
Other/ Mixed
Describe method of calculation |  |  |  |  | *ISR (April 2013) | *ISR (February 2014)
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Public health benefits from avoided local pollution over project life-cycle | US$ |  | 45000000 |  | 0 | 0 | [5 empty] | 0
Environmental co-benefits in terms of avoided local pollution (tonnes per year) | NOx, SO2, TSP; |  | NOx - 3,000; SO2 - 5,400; TSP - 2,500 |  | 0 | 0 | [5 empty] | 0
Number of potential new residential connections | Number |  | Up to 955,000 |  | 0 | 0
Improved energy security (Increased RE Share (incl. hydro): Sothern Sumatra) |  |  | from 38% to 42%; |  | 0 | 0
Improved energy security (Increased RE Share (incl. hydro): INorthern Sulawesi |  |  | from 61% to 70% |  | 0 | 0
Development of local industry |  |  |  |  | 0 | 0
Increased employment |  |  |  |  | 0 | 0
Cost reduction |  |  |  |  | 0 | 0
Describe the development co-benefits |  |  |  |  | Developmental indicators wil be calculated after the plant is comissioned
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional): 2014: The project is supporting steam field above-ground systems and power plant construction, so results should be expected toward the end of project implementation. The project is lagging two years behind the original schedule and while no results can be reported yet, the project has made significant progress in the production drilling program as well as in procurement of steam gathering systems and power plants. Construction of Ulubelu 3&4 110 MW and and Lahendong 5&6 40MW is started.

## Morocco - XCTFMB026A-27A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-08-13 |  | Version 4.6 | 2014-04-08
CSP-MENA |  | Project/Program Title: | Morocco Ouarzazate CSP
Implementing MDB 1: |  |  | IBRD | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFMB026A
Implementing MDB 2: |  |  | AfDB | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFMB027A
Amount of CTF funding (million USD): |  |  | 197 | [6 empty] | Project lifetime: | 25 | years
Date of First MDB Approval: |  |  | 2011-11-01 | [6 empty] | Expected Reporting Closure Date: | 2021-06-30
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 6000000 | 6000000 | 240000 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 240,000 ton CO2e per year. * 0 tCO2 reduction as of reporting date
Total Project size in US million $ |  | 1427 | 1390 | 1427 | 197 | 197 | 197 | 197 | 197 | 197 | 197 | 197
B2. Volume of direct finance leveraged through CTF funding | million USD | 1230 | 1193 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB |  |  | 200 | 200 | 0 | 0 | [5 empty] | 0
Other MDB (please specify) AfDB |  |  | 245 | 245 | [7 empty] | 0
Government |  |  | 379 | 379 | 0 | 0 | [5 empty] | 0
Private sector | [11 empty] | 0
Bilateral |  |  | 369 | 369 | 0 | 0 | [5 empty] | 0
Other |  |  |  | 37 | [7 empty] | 0
Exchange Rate used for non-US investments: | US$1 = |  |  |  | 0
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). |  |  | *Bilateral: AFD, KfW, EIB *Others: EC/NIF grant *amount differts from AfDB due to difference in exchange rate | *Note: difference with AfDB co-financing figure $1,292 million is due to the difference in exchange rates | *$40M CTF funds disbursed through IBRD on June 2013; $0 disbursement of IBRD funds | *ISR, April 2014 *total of $80M CTF funds disbursed
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar |  | 160 | 160 | 160 | 0 | 0 | [5 empty] | 0
Hydro
Geothermal
Other/ Mixed
Describe method of calculation |  | Power Generation 9250 GWh (during project lifetime, 25 years) | Power Generation 370 GWh per year
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Development of local industry (modernization) |  |  | 0 |  | 0 | 0 | [5 empty] | 0
Increased employment |  |  | 850 |  | 0 | 0 | [5 empty] | 0
CSP Cost reduction |  |  | 0 |  | 0 | 0
Creation of a Mediterranean electricity market connected to Europe |  |  | 0 |  | 0 | 0
Economic integration in the region, fostering increased trade and knowledge exchange |  |  | 0 |  | 0 | 0
Energy supply diversification through renewable energy increases energy security |  |  | 0 |  | 0 | 0
Global environmental benefits |  |  | 0 |  | 0 | 0
Describe the development co-benefits | *800 jobs during the construction phase and 50 during the operation phase |  |  |  | Developmental indicators wil be calculated after the plant is comissioned
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional): 2014: Implementation is progressing well, with overall construction progress approximately 33 percent complete. The project has experienced small delays largely due to fabrication/manufacturing of equipment. Note that given the nature of the project, results will be achieved and reported toward the end of implementation.

## Vietnam -XCTFVN094A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-08-13 |  | Version 4.6 | 2014-04-08
Vietnam |  | Project/Program Title: | Vietnam Distribution Efficiency Project
Implementing MDB 1: |  |  | IBRD | [6 empty] | Project/Program ID (from the CTF pipeline): | XCTFVN094A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 30 | [6 empty] | Project lifetime: | 10 | years
Date of First MDB Approval: |  |  | 2012-09-01 | [6 empty] | Expected Reporting Closure Date: | 2018-12-31
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 2690000 | 2690000 | 269148 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 269,148 ton CO2e per year. *Target at TFC/Board: see PAD (p70); project life time for this project 10 years *Target at project closing: see PAD (p21); |  |  |  | *0 tCO2 avoided as of reporting date | *0 tCO2 avoided as of reporting date
Total Project size in US million $ |  | 435 | 435 | 435 | 72.5 | 168.5 | 168.5 | 168.5 | 168.5 | 168.5 | 168.5 | 168.5
B2. Volume of direct finance leveraged through CTF funding | million USD | 405 | 405 | 405 | 42.5 | 96 | 0 | 0 | 0 | 0 | 0 | 138.5
MDB |  |  | 300 | 300 | 42.5 | 96 | [5 empty] | 138.5
Other MDB (please specify)
Government |  |  | 105 | 105 | 0 | 0 | [5 empty] | 0
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). |  |  |  |  | *Note: Figures based on actual disbursements from different sources *$139M IBRD funds disbursed; information from the WB project portal
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Female
Male
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | 3659 | 3659 | 366 | 0 | 0 | [5 empty] | 0
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Environmental co-Benefits (lower local pollutant due to avoided thermal power generation) |  |  |  |  | 0 | [6 empty] | 0
Improved reliability of services provided by PCs |  |  |  |  | 0 | [6 empty] | 0
Enhanced demand forecasting and optimization of available generation resources |  |  |  |  | 0
Empowering customers and reducing load shedding |  |  |  |  | 0
Increase in RE penetration (facilitates connection and integration of small scale generation from renewable resources, which connect to PCs’ network) |  |  |  |  | 0
Reduction of technical losses (due to elimination of overloads in networks) and of unmetered consumed energy (commercial losses) |  |  |  |  | 0
Enhanced transparency in operations due to the timely availability of reliable information across each company |  |  |  |  | 0
Improved electricity tariff structure |  |  |  |  | 0
Local socio-economic development |  |  |  |  | 0
Describe the development co-benefits |  |  |  |  | Developmental indicators wil be calculated after the plant is comissioned
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: After a slow start up, implementation is progressing well with 20 percent of sub-projects under procurement and construction. The project will soon start reporting on outcome indicators.