## PCTFCO008A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-17 |  | Version 4.6 | 2014-04-08
Colombia |  | Project/Program Title: | Sustainable Energy Finance Program
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFCO008A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 6.74 | Approved to date: | 6.74 |  |  |  |  | Project lifetime: | 7 | years
Date of First MDB Approval: |  |  | 2011-05-01 | [6 empty] | Expected Reporting Closure Date: | 2018-09-30
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 3100000 | 3100000 | 777000 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Target tons of GHG emissions reduced or avoided: 440,000 ton CO2e per year Program at the time of MDB approval was 111,000 MtCO2 per year over the period of 7 years, with the total of 777,000 MtCO2 At the time of the reporting, the sub-projects under this program arein the ramp up period and has not reported GHG emission reduction amounts
Total Project size in US million $ * |  | 109.74 | 109.74 | 109.74 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6
B2. Volume of direct finance leveraged through CTF funding | million USD | 103 | 103 | 103 | Data confidential | Data confidential | 0 | 0 | 0 | 0 | 0 | 0
MDB
Other MDB (please specify)
Government
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). | * The "Total Project size in US million $"2013 and 2014 fields indicate cumulative Portfolio Outstanding Balance
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.t.s. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation | There are no specified targets for the portfolio composition. The program supports eligible projects in Energy Efficiency, Renewable Energy, Cleaner Production, and Green Construction
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.t.s. | [9 empty] | 0
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
0
Describe the development co-benefits | Increased competitiveness of the corporate/SME sector; Increased capacity of the local banking sector to finance commercial investments in sustainable energy Demonstration of commercial viability of sustainable energy finance in Colombia
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain. 2014: No
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments and/or sub-project status (Optional): 2014: Sub-projects under the program are in the ramp-up stage

## PCTFMX054A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-17 |  | Version 4.6 | 2014-04-08
Mexico |  | Project/Program Title: | Private Sector Wind Development
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFMX054A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 15.6 | [6 empty] | Project lifetime: | 20 | years
Date of First MDB Approval: |  |  | 2010-07-01 | [6 empty] | Expected Reporting Closure Date: | 2015-12-01
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 900000 | 900000 | 900000 | 370000 | 0 | [5 empty] | 370000
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Target tons of GHG emmissions reduced or avoided: Data confidential Program's target covers emission reductions achieved over the 5-year period (2010 to 2014)
Total Project size in US million $ |  | 195.6 | 195.6 | 195.6 | 195.6 | 195.6 | 195.6 | 195.6 | 195.6 | 195.6 | 195.6 | 195.6
B2. Volume of direct finance leveraged through CTF funding | million USD | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 180
MDB
Other MDB (please specify)
Government
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other).
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW |  | 68 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 68
Wind |  | 68 | 68 | 68 | 68 | 0 | [5 empty] | 68
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.t.s. | [9 empty] | 0
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
0
Describe the development co-benefits | Enable further development of EDF’s additional 112.5MW of wind power in Mexico, and possibly lead to an estimated 150 to 350 MW of incremental private wind power projects over the five year period (abating additional 2.0 to 4.7 MtCO2e) Reduce project and market risks
Note: n.a. = not applicable n.t.s.=no target set
Does the sub-project intend to seek carbon finance or has it received explain. 2014: Yes, it is registered with the CDM
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: Sub-Project is in operation

## PCTFZA068A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-17 |  | Version 4.6 | 2014-04-08
South Africa |  | Program Title: | Sustainable Energy Acceleration Program
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFZA068A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 42.5 | [6 empty] | Project lifetime: | 18 | years
Date of First MDB Approval: |  |  | 2011-10-01 | [6 empty] | Expected Reporting Closure Date: | 2030-12-15
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 13000000 | 13000000 |  | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Target tons of GHG emissions reduced or avoided: Data confidential The GHG reduction project target over the tenor of the financial instrument is indicated above. Sub-projects under the program (power plants) are under construction
Total Project size in US million $ |  | 1357.5 | 1424.5 | 42.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2. Volume of direct finance leveraged through CTF funding | million USD | 1315 | 1382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB
Other MDB (please specify)
Government
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other).
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.t.s. | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar |  |  | 150 | 150 | [7 empty] | 0
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. |  |  | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
0
Describe the development co-benefits
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain. 2014: No
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: The sub-projects under the program are in construction phase

## PCTFZA071A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-17 |  | Version 4.6 | 2014-04-08
South Africa |  | Project/Program Title: | EE Program
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFZA071A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 7.5 | Approved to date: | 2.5 |  |  |  |  | Project lifetime: | 15 | years
Date of First MDB Approval: |  |  | 2011-05-01 | [6 empty] | Expected Reporting Closure Date: | 2018-09-15
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 2360000 | 2360000 | 340000 | 0 | [6 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 80,000 ton CO2e per year. The cumulative target stated in the program proposal (2.36) is for joint AfDB/IFC $15 mil program. AfDB has since left the program. The target is therefore prorated The sub-projects under the program are developing a pipeline that will be comprised of eligible EE/RE sub-projects Sub-projects are in the ramp-up period and the GHG data are not available yet
Total Project size in US million $ |  | 16.5 | 11.5 | 2.5 | 11.5 | 11.5 | 11.5 | 11.5 | 11.5 | 11.5 | 11.5 | 11.5
B2. Volume of direct finance leveraged through CTF funding | million USD | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9
MDB |  | 9 | 9 |  | 9 | 0
Other MDB (please specify)
Government
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). | Actual MDB investment: IFC - $9.3M The sub-projects under the program are developing a pipeline that will be comprised of eligible EE/RE sub-projects
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.t.s. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation | Specific targets are not set. Investment will support banking sector efforts in providing long-term financing to: (i) the SMEs/ Midsized Corporate clients and previously underserved segments of markets across South Africa; and (ii) the SME clients with EE/RE related projects.
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.t.s. | [9 empty] | 0
Comment on methods of calculation | Specific targets are not set. Investment will support banking sector efforts in providing long-term financing to: (i) the SMEs/ Midsized Corporate clients and previously underserved segments of markets across South Africa; and (ii) the SME clients with EE/RE related projects.
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
0
Describe the development co-benefits | Development of SMEs / Mid Market clients in South Africa, through increased access/reach of financial services; Promotion of the development of sustainability business through providing long term financing to projects that result in environmental benefits.
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: The sub-projects under the program are in the ramp-up period and developing a pipeline

## PCTFTH075A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-17 |  | Version 4.6 | 2014-04-08
Thailand |  | Project/Program Title: | Renewable Energy Accelerator Program(TSEFF)
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFTH075A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 40 | Approved to date: | 4.6 |  |  |  |  | Project lifetime: | 25 | years
Date of First MDB Approval: |  |  | 2011-05-01 | [6 empty] | Expected Reporting Closure Date: | 2025-08-31
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 2590000 | 2590000 | 200000 | 32336 | 33378 | [5 empty] | 65714
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Part of the program that has been MDB-approved, is expected to generate an estimated 4,500-5,000 tCO2e of GHG reduction per year. This amounts to a total estimated reduction benefit of 100,000-130,000 tCO2e over each of the project’s 25 year life, or a total of 200,000-260,000 tCO2e for the project.
Total Project size in US million $ |  | 77 | 41.3 | 41.6 | 25.2 | 31.2 | 31.2 | 31.2 | 31.2 | 31.2 | 31.2 | 31.2
B2. Volume of direct finance leveraged through CTF funding | million USD | 37 | 36.7 | 37 | 20.6 | 6 | 0 | 0 | 0 | 0 | 0 | 26.6
MDB |  | 12 | 12 | 12 | 8 | 1.3 | [5 empty] | 9.3
Other MDB (please specify)
Government
Private sector |  | 24.7 | 24.7 | 25 | 12.6 | 4.7 | [5 empty] | 17.3
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other).
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 100 | 100 | 12 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 27
Wind
Solar |  |  |  | 12 | 12 | 15 | [5 empty] | 27
Hydro
Geothermal
Other/ Mixed
Describe method of calculation | Two grid-connected solar PV farms, each of 6MW of installed capacity and 3MW additions
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. |  |  | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
0
Describe the development co-benefits | The program has helped to grow an additional 208MW capacity resulting in 4,080,000 mtCO2e addtional abatement. Strong demonstration impact might lead to kick starting an estimated 50-100MW of additional private solar power projects in the next years.
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional): Portion of the funds under the program has been allocated to sub-projects. IFC continues building a pipeline

## PCTFTH076A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-17 |  | Version 4.6 | 2014-04-08
Thailand |  | Project/Program Title: | Sustainable Energy Finance Program(T-SEF)
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFTH076A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 30 | Approved to date: | 4.8 |  |  |  |  | Project lifetime: | 15 | years
Date of First MDB Approval: |  |  | 2011-06-01 | [6 empty] | Expected Reporting Closure Date: | 2023-11-30
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 5000000 | 5000000 | 1100000 | 266 | 822 | [5 empty] | 1088
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 330,000 ton CO2e per year. Expected savings of 140,000-145,000 tons of CO2e per year per year after ramp-up period over 12 years of ficality lifetime
Total Project size in US million $ |  | 95 | 70 | 70 | 1.5 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93
B2. Volume of direct finance leveraged through CTF funding | million USD | 65 | 65.2 | 65.2 |  |  | 0 | 0 | 0 | 0 | 0 | 0
MDB |  | 31.5 | 31.5 | 31.5 | [7 empty] | 0
Other MDB (please specify)
Government
Private sector |  | 33.75 | 33.7 | 33.7 | [7 empty] | 0
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). | Sub-projects under the program provide lease financing to EE related projects and some small scale RE projects through Financial intermediaries. Specific RE targets are not identified in the composition of the target portfolio
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.t.s. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.t.s. | [9 empty] | 0
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
0
Describe the development co-benefits
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional): 2014: Sub-projects under the program are in a ramp-up period

## PCTFTR080A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-17 |  | Version 4.6 | 2014-04-08
Turkey |  | Project/Program Title: | Commercializing Sustainable Energy Finance Program (CSEF)
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFTR080A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 21.7 | Approved to date: | 20.5 |  |  |  |  | Project lifetime: | 10 | years
Date of First MDB Approval: |  |  | 2010-05-01 | [6 empty] | Expected Reporting Closure Date: | 2020-09-15
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 2800000 | 4200000 | 350000 | 50303 | 10403 | [5 empty] | 60706
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 280,000 ton CO2e per year. The sub-projects under the program are expected to support at least 30 new leases to EE /RE projects. At the end of the five-year ramp up period (2010 to 2015), savings should reach 70,000 MtCO2eq/year
Total Project size in US million $ |  | 116.7 | 115.5 | 20.5 | 80.5 | 115.5 | 115.5 | 115.5 | 115.5 | 115.5 | 115.5 | 115.5
B2. Volume of direct finance leveraged through CTF funding | million USD | 95 | 95 | 0 | 60 | 35 | 0 | 0 | 0 | 0 | 0 | 95
MDB
Other MDB (please specify)
Government
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other).
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.t.s. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation | The sub-projects under the program are expected to support at least 30 new leases to EE /RE projects. At the end of the five-year ramp up period (2010 to 2015), average energy savings should reach 160 GWh/year
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | 2200 | 2200 | [8 empty] | 0
Comment on methods of calculation | The sub-projects under the program are expected to support at least 30 new leases to EE /RE projects. At the end of the five-year ramp up period (2010 to 2015), average energy savings should reach 220 GWh/year
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
Increased capacity among the staff members including loan, credit and marketing staff (at least 40 people), on topics of EE improvements theory and EE measures, RE technologies, marketing of EE, and IFC | 40 | [10 empty] | 0
Describe the development co-benefits
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: Three sub-projects are fully operational.

## PCTFUA090A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-08-06 |  | Version 4.6 | 2014-04-08
Ukraine |  | Project/Program Title: | Renewable Energy Program
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFUA090A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 24.96 | Approved to date: | 0.025 |  |  |  |  | Project lifetime: | 20 | years
Date of First MDB Approval: |  |  | 2013-11-01 | [6 empty] | Expected Reporting Closure Date: | mm/dd/yy
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored | PLEASE NOTE THAT THIS PROGRAM HAS NO SUB-PROJECTS YET
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 1650000 | 0 | 0 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | Tons of GHG emissions reduced or avoided: 40,000 ton CO2e per year.
Total Project size in US million $ |  | 293.96 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025
B2. Volume of direct finance leveraged through CTF funding | million USD | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB
Other MDB (please specify)
Government
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other).
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.a. | n.a, |  | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a.
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
0
Describe the development co-benefits
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014:This program has no sub-projects yet

## PCTFVN095A
Table A: Monitoring and Reporting for CTF Projects and Programs
[8 empty] | Date this report was submitted: | 2014-10-17 |  | Version 4.6 | 2014-04-08
Vietnam |  | Project/Program Title: | Sustainable Energy Finance Program
Implementing MDB 1: |  |  | IFC | [6 empty] | Project/Program ID (from the CTF pipeline): | PCTFVN095A
Implementing MDB 2: | [9 empty] | Project/Program ID (from the CTF pipeline):
Amount of CTF funding (million USD): |  |  | 8.6 | [6 empty] | Project lifetime: | 15 | years
Date of First MDB Approval: |  |  | 2011-11-01 | [6 empty] | Expected Reporting Closure Date: | mm/dd/yy
|  | Report Year 2014 covered in this sheet: | From: | 2013-07-01 | To: | 2014-06-30
Please complete all cells colored
Core indicators | Unit | Target at the time of TFC approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (cumulative over lifetime of the investment) | Target at the time of MDB approval (as of expected reporting closure date) | Report Year 2013 | Report Year 2014 | Report Year 2015 | Report Year 2016 | Report Year 2017 | Report Year 2018 | Report Year 2019 | Total actual to date
[5 empty] | Cumulative from start | Annual | Annual | Annual | Annual | Annual | Annual | Annual
B1. Tons of GHG emissions reduced or avoided | Tons of CO2 equivalent | 4500000 | 803571.4286 | 0 | 0 | 0 | [5 empty] | 0
Provide assumptions and remarks related to estimation of GHG emissions reduced and/or avoided | The investment component of the program was scaled down from $28mil to $5mil, with the size of the program reduced to $8.6mil. The revised cumulative lifetime target is 4.5 x 5/28 = 0.8 million tons Annual target accordingly is 0.8 / 15 years = 0.05 million tons / year
Total Project size in US million $ |  | 108.6 | 17.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2. Volume of direct finance leveraged through CTF funding | million USD | 100 | 17.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDB
Other MDB (please specify)
Government
Private sector
Bilateral
Other
Exchange Rate used for non-US investments: | US$1 =
Specify the source of direct finance (e.g., name of the private sector,bilateral agency and other). | The investment component of the program was scaled down from $28mil to $5mil. The revised cumulative target is $100 x 5/28 = $17.86 million
B3. Installed capacity (MW) as a result of CTF interventions (Identify technology below) | MW | n.t.s. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind
Solar
Hydro
Geothermal
Other/ Mixed
Describe method of calculation
B4. Number of additional passengers using low-carbon transport as a result of CTF | No. of people |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Female | [11 empty] | 0
Male | [11 empty] | 0
Describe the type (car, bus, train, other) of low carbon transport and how passenger numbers have been calculated
B5. Annual energy savings as a result of CTF interventions (GWh) | GWh | n.t.s. | [9 empty] | 0
Comment on methods of calculation
Development indicator(s): Please identify at least one indicator for development co-benefits. Reporting on development co-benefits must be done when information is available, not necessarily annually. At a minimum, at project completion.
0
Describe the development co-benefits
Note: n.a. = not applicable n.t.s.=no target set
Does that project/program intend to seek carbon finance or has it received carbon credits? If yes, please explain.
Please provide remarks for any indirect GHG emissions reduction and indirect funding leveraged.
General comments/Project status (Optional) 2014: The investment component of the program was scaled down from $28mil to $5mil.