## Cover
PPCR Monitoring and Reporting
Jamaica |  | PPCR Investment Plan
Annual Reporting Period
From: | 2017-01-01
To: | 2017-12-31
Projects:
ID No. | XPCRJM048A | Title | Adaptation Program and Financing Mechanism for the Pilot Program For Climate Resilience Jamaica
| XPCRJM049A | Title | Improving Climate Data and Information Management Project
| PPCRJM505A | Title | Financing water adaptation in Jamaica’s new urban housing sector

## 1 Integrated
PPCR Scorecard 1 | [6 empty] | Date of Report: |  |  | 2017-06-30
PPCR Core Indicator 1: | Degree of integration of climate change into national planning
Data Collection Method: | Data scored at the country level
Jamaica | PPCR Investment Plan
Reporting Period: |  |  |  | From: | 2017-01-01 |  | To: |  |  | 2017-12-31
Complete below the sectors identified as a priority in the PPCR investment plan. Insert other priority sectors or ministries below(optional) | Is there an approved climate change plan for the nation/ sector? |  | Have climate resilience strategies been embedded in the central government's/ sector's principal planning documents? |  | Has responsibility been assigned to institutions or persons to integrate climate resilience planning? |  | Have specific measures to address climate resilience been identified and prioritized? e.g. investments and programs |  | Do all planning processes routinely screen for climate risks?
a | b |  | c |  | d |  | e |  | f
| Score- 2016 reporting period (last year) | Score-2017 reporting period (new) | Score- 2016 reporting period (last year) | Score-2017 reporting period (new) | Score- 2016 reporting period (last year) | Score-2017 reporting period (new) | Score- 2016 reporting period (last year) | Score-2017 reporting period (new) | Score- 2016 reporting period (last year) | Score-2017 reporting period (new)
National Planning | 6 | 7 | 7 | 7 | 5 | 6 | 5 | 6 | 5 | 6
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! | Promulgation of the Forest Policy for Jamaica; Approval of the Forest Reserve Orders; Passage of the Building Bill in the House of Representatives towards the establishment of a legislative framework to support the resilience of the built environment; Water Sector Policy was submitted for revision in 2017. Road Traffic Act making reference to emission control was tabled in 2017; Work commenced on adapting the PAHO Model Smart Health Care Facility Policy for Jamaica, (a policy for Building Resilience against Climate Change in the Health Sector); National Settlement strategy reviewed and updated to include climate change considerations |  | Climate change considerations incorporated in Medium Term Socio-Economic Framework (MTF 2015-2018); remain in country agreements with International Development Partners (IDPs); climate resilience strategies integrated in the local development planning framework and considered in development orders and Local Sustainable Development Plans. |  | Climate Change Focal Point Network functioning and focal points for 5 key sector ministries identified and actively involved in integrating climate change into development planning. Efforts made by the Climate Change Division (CCD) to increase activity within the focal point network. |  | A number of climate change projects continue to be implemented. GCF Readiness Grant of US$300,000 approved by the GCF to enhance policy and institutional support to the Climate Change Division; Another US$580,000 grant approved to engage the private sector to strengthen their capacity in accessing GCF resources for climate change action; Project preparation for PPCR project to promote community based resilience in the Fisheries Sector completed; Completion of the Rural Economic Development Initiative (R.E.D.I) which contributed to building resilience in the agriculture sector through the introduction of drip irrigation technology and water storage facilities in drought prone areas. Project Preparation for R.E.D.I 2 commenced (scoping, concept note prepared $US40,000,000) and expected to be approved in 2018. GOJ/Adaptation Fund Programme identified Annotto Bay for intervention to build the town's resilience to climate change related disasters. ACP bridging project - development of additional agro parks using climate SMART agriculture. 9 agroparks using climate change technology. |  | The review process of the Public Investment Management System (PIMS) through which projects are considered for budgetary support screens for climate risks.PIMS staff trained in project management (PM). The PIOJ advance the development of an Environment and Social Framework which includes climate change screening, finalized and trained staff and GOJ partners; draft of the 2015 SOJC provides data/information for sectors and selected communities to facilitate screening at sectoral and community level
Agriculture and Food Security | 6 | 6 | 6 | 7 | 4 | 4 | 8 | 8 | 3 | 4
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! | Final Draft of National Youth in Agriculture Policy prepared and includes Environmental Sustainability (including climate change adaptation) as a guiding principle , |  | Ministry of Industry, Commerce, Agriculture & Fisheries Strategic Business Plan 2017 – 2021 includes Increased responsiveness to impacts of climate change as a strategic outcome and risk management and climate change identified as a key strategy for the implementation of programmes and projects |  | 3 focal points remain members of the CCFPN: Ministry of Agriculture and Fisheries (MOAF) , Rural Agricultural Development Authority (RADA), Fisheries Division. CCFP trained. |  | Increasing Access to Climate Smart Agriculture (IACA) programme launched by IDB, UNEP DTU and INMED Partnership for Children with an aim to enhance technical and business capacity for aquaponics production for climate resilience, economic stability, food and water security; The , ‘Building Resilience and Adaptation to Climate Change while Reducing Disaster Risk in Peckham, Clarendon, and Surrounding Communities’ launched by CDB/Environmental Health Foundation (EHF) to increase productivity and adaptive capacity, strengthened capacity for farmer groups; Completion of the Rural Economic Development Initiative (R.E.D.I) which contributed to building resilience in the agriculture sector through the introduction of drip irrigation technology and water storage facilities for over 1000 farmers operating on over 254 hectares of farmlands; three demonstration projects launched under the regional Japan Caribbean Climate Change Partnership to introduce solar powered irrigation to select farming communities impacted by drought; refurbishment of tanks and water harvesting technology ; and sustainable climate smart school gardens ; Government committed $30 million for the implementation of five water harvesting projects in St. Ann to combat drought and other problems resulting from climate change under GOJ/Adaptation Fund Programme; Seven Water Users Groups formalised and registered as legal entities; Score remains unchanged as the Strategy and action plan is still not finalized. Soil moisture probes procured for installation at agro parks and other selected locations under the PPCR (ICDIMP). |  | Informal screening continues to routinely assess planning processes for climate change/variability risks using lessons learnt etc. Fisheries Division incorporating climate change variability/risk.
Water Resources | 6 | 8 | 3 | 4 | 4 | 4 | 7 | 8 | 2 | 3
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! | Work continued on revision and amendment of Water Sector Policy and preparation of the Rural Water Supply Development Strategy. Water Sector Plan prepared and submitted to cabinet |  | The country’s Water Resources Development Master Plan (WRDMP) being updated to include climate change considerations; The Flood Control Act being developed; |  | No change; focal point at Water Resources Authority remains active member of the CCFPN |  | The hdyro-met network strengthened through the development of a real time network, and upgrading of rain gauges and streamflow monitors monitoring systems. Rainwater Harvesting and Catchment Tank Rehabilitation Programme continued; Pilot project commenced in Pennants Clarendon by the Ministry of Local Government and Community Development to establish Water shop facilities in drought stricken areas to improve access to potable water by residents |  | Informal systems being used to screen planning processes for climate change/ variability risks on an ad-hoc basis. This will improve the screening process . Data made available through 2015 SOJC to facilitate screening as it includes sector and geographic breakdown
Tourism | 4 | 4 | 5 | 6 | 3 | 4 | 4 | 4 | 1 | 2
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! | Ministry of Tourism developed a policy framework which includes the sustainable development and management of tourism within an healthy natural environment as one of the strategic policy objectives |  | Climate change and disaster risk management being mainstreamed into the tourism sector through the Climate Change and Multi-Hazard Contingency Programme. (The Programme is ongoing with capacity building strategies being implemented in Climate Change and Disaster Risk Management.) |  | CCFPN Focal Point remains fully functional within the Ministry of Tourism. The Ministry provided secretariat functions to the Tourism Emergency management Committee (TEMC) and is responsible for the planning and implementation of strategies related to Climate Resilience and Disaster Risk Management Planning. |  | The Climate Change and Multi-Hazard Contingency Programme is aimed primarily at strengthening the resilience of the tourism sector against the various natural disasters and emergencies that may disrupt industry operations; The Ministry is currently in the process of developing comprehensive Disaster Risk management Plans for the 6 Resort Areas. Plans are also underway to undertake Hazard, Risk and Vulnerability Assessments for each Resort Area. |  | Some policies and programmes in the Ministry are screened for Climate Risks - particularly the Draft Policy on Motorized and Non motorized Water based Recreational Activities in Marine and Riverine Environments, the Community Tourism Policy, The Tourism Networks Policy. Policies currently being drafted such as the Destination Assurance Policy will undergo a climate screening process.
Human Health | 2 | 4 | 5 | 6 | 4 | 7 | 2 | 4 | 3 | 5
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! | Work commenced on adopting the PAHO Model Smart Health Care Facility Policy for Jamaica, (a policy for Building Resilience against Climate Change in the Health Sector); Improvement in the reporting requirements based on the strengthening of islandwide national surveillance system for communicable disease (Acute respiratory illnesses and arboviral illnesses ) and its reporting requirements. |  | Preparation of Ten Year Strategic Plan continued and situational analysis of Health Sector prepared. Revision of the service level agreements between the MOH and regional health authorities to include climate resilience indicators (this will inform the strategic plans in this area) |  | CCFPN includes 3 person. The Emergency Management and Disaster and Special Services Branch has direct responsibility for climate change in the Ministry of Health. Training seminar on impact of climate change on health held for approximately 80 personnel (approx. 60 female) including senior managers and each region and facility has an assigned CC focal point. The ministry has commenced the development of regional climate change resilience plans. |  | The Smart Hospitals Initiative continued implementation incorporating climate change considerations for mitigation and adaptation - Hospitals were selected for extensive retrofitting for climate resilience (40 Hospitals completely assessed by the end of 2017 and 30 in the process of being assessed);Mosquito Control and Research Unit established to inter alia conduct research on the impact of climate change on vector abundance and disease transmission. Execution of the mass raring of sterile mosquitos in an effort to reduce the population of aedes aegypti mosquito ( IAEA project). Online CDC vector surveillance system takes climate change considerations into account and, among other things, looks at the distribution of vectors against seasons. |  | Institutionalised the programme of contracting 1000 persons between June and September to inspect and treat breeding sites. This was informed by climate risk analysis
Human Settlement and Coastal Resources | 5 | 6 | 3 | 4 | 4 | 4 | 4.5 | 5.5 | 4 | 6
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! | Coastal Management and Beach restoration Guidelines prepared (ACP-EU); Jamaica's National Strategy on Resettlement related to Disaster Risk Management and Climate Change Adaptation prepared; Passage of the Building Bill in the House of Representatives to facilitate the adoption and efficient application of National Building Code of Jamaica for ensuring safety in the built environment and minimize damage caused by natural or man-made hazards; Draft National Forest management and Conservation Plan developed which includes the management of mangrove forests; National Settlement Strategy reviewed and updated to include climate change considerations |  | Four Development Orders with climate change considerations prepared for Kingston and St Andrew and Pedro Cays, St. Mary, St Catherine and Clarendon; Additional development orders drafted for Hanover, Westmoreland, St Thomas and St Elizabeth. 1 Local Sustainable Development Plan prepared for Clarendon with climate change considerations. |  | Three focal points remain as part of the CCFPN. |  | Sea level tide gauge installed on the north coast to assist in monitoring sea level rise due to climate change. Creation of two Fish Sanctuaries in 2017 under the PPCR (ICDIMP). GOJ/Adaptation Fund Programme advanced preparations for proposal for coastal intervention along north-eastern coast of Jamaica (particularly in Annotto Bay). IWECO project in Negril targeting Negril morass- targeting climate resilience approved in 2017 |  | The Climate Resilient Screening Tool (CReST) for all municipalities to standardize processes for assessing the vulnerability of their planned programs, projects and activities to climate and disaster risks and make informed, participatory decisions on how they can be adjusted to reduce risks was far advanced (under the USAID-funded Jamaica Rural Economy and Ecosystems Adapting to Climate Change II (JAREEACH II) ). Climate change risk taken into account during the Development Order process, this is a routine exercise- screening process for EIAs etc. The Building Bill will give effect to the National Building Codes which will be used to guide/facilitate screening for compliance with the codes in the building application process.
Instructions: 1. Please establish scoring criteria for each of the aspects of this scorecard and submit them with your report. This should be done once, preferably at baseline stage and used during subsequent reporting years. 2. If you have previously established your scoring criteria, use them and submit them with your report . 3. Score each cell with a score between 0 and 10 (refer to your scoring criteria defined for this scorecard) 4. Provide explanation of change in scores between 2016 and 2017 in appropriate cells and avoid abbreviations.
Gender Mainstreaming: To what extent and in what ways have gender and socioeconomic vulnerability concerns been mainstreamed with the climate resilience planning processes at national and sector levels ?
(e.g., through gender budgeting approaches; gender needs assessments and consultations, or similar, including coordination with the Ministry of Women’s Affairs, women’s organizations).
As a part of the implementation of the Vulnerability Resilience Country Profile 25 participants were trained in a workshop on Gender in the Biodiversity Policy Landscape in Jamaica. A report on the latter was also prepared. The Government also commenced work focusing on the extent to which climate change impacts genders and how these issues can be comprehensively addressed and has since held stakeholder consultations under the theme ‘Supporting Gender Equitable Development – A Gender Analysis of the Climate Change Policy Framework'. Gender considerations are mainstreamed in project implementation processes for example - financing mechanisms under the Adaptation Programme and Financing Mechanism (PPCJ) project includes gender considerations in their design and implementation process - within the Special Climate Change Adaptation Fund , there is an additional weighting given for projects with considerations for vulnerable groups and women. Climate Change Adaptation Line of Credit also make some gender consideration.
Lessons learned: What have been the key successes when integrating climate change in national, including sector planning ?
During the reporting period, significant effort was made by the Ministry of Health to mainstream climate change adaptation/considerations into their strategic planning process and routine activities. The approach taken to mainstreaming CC in the sector through regional CC focal points should be replicated. Resilience building also continued apace in the agriculture sector with significant efforts towards drought resilience from the formalisation of water users group to promote water use efficiency to the extensive use of water storage and water saving climate-smart agricultural techniques. The enhancement of the climate data collection systems of the Water Resources Authority (WRA) and the Meteorological Services Division (MSD) have significantly improved the quality of climate data available to both climate experts and researchers. It has also improved the efficiency of the routine processes of beneficiary agencies.
What have been the key challenges and what opportunities for improvement do you see?
Challenges
1. Gender disaggregated data being collected routinely in some sectors but gender analysis utilising this data could be improved in terms of evaluating climate change impacts on each gender; looking at building resilience among women especially for post disaster recovery
2. Communicating the benefits of climate change on livelihoods to small farmers etc. needs to be improved. Beneficiaries of climate-smart interventions are not making the link between these measures and building resilience to climate change
3. Continuity of focal points in the Ministries and Agencies is important. Sufficient documentation of processes, methodologies is required to ensure sustainability that will withstand staff attrition and change in administration.
4. Fostering buy-in and understanding of mainstreaming climate change in decision making at the policy makers level is still a major challenge. While technocrats within the various sectors are adequately aware of the benefits of building climate resilience and are convinced that adaptation is key, it is felt that decision-makers still need assistance to help them to see how climate change can adversely impact or augment their various plans, projects.
Opportunities
1. Increased attention is being placed on building resilience through disaster risk financing, in addition to that provided by the CCRIF, the MOFP is now looking at risk transfer mechanisms for smaller more frequent events which still have devastating impacts; solutions for this being provided by international development partners.
2. The availability of existing technical documents such as the 2012 and 2015 SOJC provides both technocrats and policy makers with an opportunity to make evidence-based decisions; greater effort is therefore required to make both technocrats and policy-makers aware of the existence of these documents.
3. At least three Government entities are in the process of pursuing GCF accreditation. Approval of these entities will facilitate increased opportunities to scale up climate resilience building efforts across all priority sectors
Sharing experiences: please let us have some insights into the particular experience of your country with integrating climate change in national, including sector planning
Climate change continues to be a priority for the Jamaican government both at the national and sectoral level. At the national level the integration of climate change in policies and plans is guided by the actions outlined in the Medium Term Socio-Economic Framework (Vision 2030 Jamaica National Development Plan). The Climate Change Division supported CC integration and mainstreaming efforts through its work with the Climate Change Focal Point Network (See Scorecard 2 for details). The focus on climate change has also been strengthened by Jamaica's commitment to achieving the Sustainable Development Goals. The Public Investment Management Secretariat also continues to screen projects and programmes for alignment with the relevant goals and outcomes in both the Vision 2030 Jamaica and the SDGS. At the local level, there has been a deliberate effort to mainstream climate change into the preparation of the Local Sustainable Development Plans and Development Orders through extensive review of these documents. The mainstreaming of climate change in the area of agriculture has been consistent and extensive as various projects (including the PPCR, the GOJ/Adaptation Fund Programme, Japan Caribbean Climate Change Partnership) continue to provide support for climate-smart agricultural practices and the training of farmers in these practices. Despite the various initiatives however, a Climate Change Strategy and Action Plan for the sector is yet to be prepared. This resulted in the score being unchanged on the scorecard. The Health sector has made significant strides in the area of integration through inclusion of climate change considerations in it's strategic planning process and building awareness among health professionals at the level of the Ministry and the regional offices.

## 2 Capacity
PPCR Scorecard 2 | [6 empty] | Date of Report: |  |  | mm/dd/yy
PPCR Core Indicator 2: |  |  | Evidence of strengthened government capacity and coordination mechanism to mainstream climate resilience
Data Collection Method: |  |  | Data scored at the country level
Jamaica |  |  | PPCR Investment Plan
Reporting Period: |  |  | From: |  | 2017-01-01 |  | To: |  |  | 2017-12-31
Government Capacity Complete below the sectors identified as a priority in the PPCR investment plan. Insert other priority sectors or ministries below (optional) |  |  | Are information, studies and assessments addressing climate change, variability and resilience available? |  | Is the necessary climate change expertise available? |  | Do national/sector incentives and legislative policies expressly address climate change and resilience? |  | Does the government/sector participate in the coordination mechanism?
a |  |  | b |  | c |  | d |  | e
|  |  | Score- 2016 reporting period (last year) | Score-2017 reporting period (new) | Score- 2016 reporting period (last year) | Score-2017 reporting period (new) | Score- 2016 reporting period (last year) | Score-2017 reporting period (new) | Score- 2016 reporting period (last year) | Score-2017 reporting period (new)
National Planning |  |  | 8 | 9 | 7 | 7 | 6 | 6 | 6 | 7
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! |  |  | 2015 State of the Jamaican Climate Report and Summary for Policy makers completed. Report provides information on current climate and downscaled climate scenarios; Five Sector Reports prepared as inputs into Jamaica's Third National Communication to the UNFCCCC (Human Health, Agriculture, Water Resources, Coastal Resources including Human Settlement and Tourism); National Database for Greenhouse Gas Inventories developed; Climate Change Capacity Building for Media Practitioners Training Manual produced under the Japan Caribbean Climate Change Project (JCCCP). Scientific Platform for Applied Research and Knowledge Sharing (SPARKS) fully functional and contributing to the availability and accessibility of national climate projections and high resolution maps; Specific sites identified under the PPCR regional Track for LIDAR data capture to support research in vulnerable areas; Procurement for Climate Information Portal begun. |  | Over 30 Budget, policy and planning officers from 12 ministries, departments and agencies of Government receive training through a two-day workshop on planning for climate change impacts within the budgeting process; 151 grantees representing Community Based Organisations, Farmer Groups, Academia, and Faith Based Organizations trained in Proposal Writing to access grants under the Special Climate Change Adaptation Fund (SCCAF) of the Adaptation Programme and Financing Mechanism of the PPCR in Jamaica; Meteorological Service Division personnel received training in dry spell forecasting under the Regional PPCR; Score unchanged as expertise available at the national level still needs to be transferred more comprehensively to priority sectors |  | Youth in Agriculture Policy; The Climate Change and Multi-hazard contingency planning programme for Tourism; Local Sustainable Development Plans and Development Orders |  | Thematic Working Groups (TWG) of Vision 2030 continue to coordinate and monitor the implementation of activities related to climate change adaptation related policies, projects and programmes. National Social Protection committee has a sub-committee on Social Services and Infrastructure that incorporates climate change considerations and also bears in mind vulnerable groups, with women specifically considered. Information sharing is provided for via various websites;
Agriculture and Food Security |  |  | 8 | 8.5 | 7 | 7 | 6 | 7 | 4 | 5
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! |  |  | Agriculture Sector Report prepared as inputs into Jamaica's Third National Communication to the UNFCCCC. A number of UWI CSGM Studies prepared: Caribbean Food Security, Future of Livestock in a warmer Climate; Characterising Heat Stress on Livestock using Temperature-Humidity Index (Abstract/Full text available online) Publication of data on several national food programmes within Ministry of Industry Commerce Agriculture and Fisheries indicating improved self-sufficiency rates in Irish potato and onion production; Pest Forecasting Early Warning System developed to address outbreaks of Beet Army Worm. Crop Resilience and Crop Suitability modelling Study for Five Crops in the Upper Rio Minho Watershed started. Varietal screening studies completed towards identification of high-yielding disease-tolerance crops, e.g.. Cocoa-Frosty Pod Rot Disease; Mumbassa Grass; Tomato-Yellow Leaf Curl. |  | Over 130 farmers trained in climate-smart land husbandry techniques under the GOJ/Adaptation Fund Programme; Building Climate Change Resilience identified as component of Human Resource Capacity Plan of Ministry of Industry, Commerce, Agriculture & Fisheries Strategic Business Plan 2017 – 2021. Internal knowledge sharing and training (through farmer field school methodology) continues. |  | Youths in Agriculture Policy submitted to Cabinet. Policy position taken to upgrade Bodles to a Seed Bank. RADA drought mitigation activities and climate change activities continue. Elements of Production and Productivity Programme related to climate Change |  | Increased number of groups involved in the different projects/climate change activities. Agricultural interest are represented on an increased number of climate change project steering committees.
Water Resources |  |  | 6 | 7 | 3 | 4 | 4 | 5 | 5 | 6
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! |  |  | Aquifer Recharge Study completed (and operational). Water Quality Atlas completed. Study on water hydrology on Dry Harbour Mountain by UWI CSGM began. |  | Increase in number of personnel at the WRA who have attained additional education in climate change (higher degrees). NWC now demonstrating expertise in incorporating climate change scenarios in planning. |  | WRA has hired consultants to update Water Resources Master Plan. Water Sector Policy moved to 2nd Draft and submitted to Cabinet. Water Resources (Water Abstraction Charges) Regulations, finalized and gazetted in May 2017. The regulations introduces the application of water abstraction charges/volume-based fees (WAC/VBF)to facilitate more efficient management of the country's water resources |  | NWC-IAEA Project (water management strategy component) Project and NIC's Essex Valley Project. Information sharing is being done via Web Map portal open. Additional coordination with Municipal corporation and Clarendon PDC to implement minor water supplies for domestic and agricultural uses (rainwater harvesting, solar pumps, etc.). JCCP-sponsored Improving adaptive capacity of climate change through rehabilitation and construction of water Harvesting Infrastructure in Upper Clarendon. Continued collaboration on special climate change projects. Increased in participation of small water supply.
Tourism |  |  | 5 | 6 | 5 | 5 | 2 | 3 | 5 | 5
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! |  |  | Tourism Sector Report ) prepared as inputs into Jamaica's Third National Communication to the UNFCCCC (far advanced for incorporation). |  | The Ministry has built the capacity of internal staff through local and international workshops and for a to treat with the development of Climate Change Plans and Strategies. |  | The Climate Change and Multi-hazard contingency planning programme takes in account both Climate Change Resilience and Disaster Risk management. |  | The sector through the Ministry of Tourism continues to participate in the CCFPN; supports coordination mechanism of the Vision 2030 Jamaica and sits on a number of project steering committees of CC and DRM related projects
Human Health |  |  | 5 | 6 | 3 | 5 | 2 | 3 | 2 | 3
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! |  |  | An additional 30 Smart Hospitals have been assessed. Integrated Vector Management Strategy was implemented. |  | The Ministry of Health and the University of the West Indies (UWI) established a Mosquito Control and Research Unit at the UWI (need to confirm status with MOH). Continues to pull on resources of PAHO and approximately 80 senior managers at MoH trained at capacity building workshop in Climate Change and Health. Specialized Training in Contingency and Conservation Planning; and Energy Efficiency Monitoring developed in 2017 for members of staff at health care facilities that will be retrofitted for Climate Resilience under the Smart Health Care Facilities in the Caribbean Project. |  | Climate change is now mentioned in the yearly Operational Plan at the MoH. However, input not substantial enough to warrant improved scoring. National Epidemiology Unit has formalised research arm and has developed research agenda to include research on climate change impacts. |  | Regular participation in all the CCFPN activities and PAHO regional activities related to climate change continues. Additional cross-sectoral trainings provided in Emergency Operation Centre and Incident Command Systems. There is coordination between government and non-government groups in training for psycho-social and mental health support for victims of disasters related to climate change. There is implicit consideration for vulnerable groups and gender (moreso for the former) but explicit consideration is not currently being made. E.g.. Vector control programme identifies high-risk/vulnerable communities.
Human Settlement and Coastal Resources |  |  | 6 | 6 | 3 | 4 | 3 | 4 | 5 | 5
How do you justify the increase (or decrease) in scores between scores reported in 2016 reporting period and scores reported in 2017 reporting period ? Please explain! |  |  | Under the Caribbean Regional Track of the Pilot Programme for Climate Resilience (PPCR) in the Caribbean, three vulnerable areas identified as priority sites for LIDAR data capture to support bathymetric and nearshore topographic research for specific vulnerable locations . Portmore Municipal Council (PMC) obtained technical assistance grant from the CDB to enhance it's capacity to make evidenced-based decisions in respect of DRM and climate change adaptation (CCA);involves the preparation of a Multi-Hazards Risk Profile and Comprehensive Disaster Risk Management Plan (DRM) for the Municipality; |  | UNCTAD conducted national workshop on “Climate Change Impacts and Adaptation for Coastal Transport Infrastructure in Caribbean SIDS” (more info needed here). Increased expertise available in coral reef rehabilitation, e.g.. from NGOs such as White River Marine Association. Knowledge-sharing activities with the MDAs exist and technical know-how is apparent among people on-the-ground. Academia now including taught programmes in architecture and climate change (UTECH) that provide grounds for expertise in climate change to be available. Expansion of number of students doing climate change studies and acquisition of higher degrees (UWI and UTECH). |  | Local Sustainable Development Plans and Development Orders expressly address CC adaptation and resilience building. This includes the Clarendon Local Sustainable Development Plan; Four Provisional Development Orders (KSA and Pedro Keys, St. Mary, St. Catherine and Clarendon) and two Draft Development Orders (St. James and Portmore) all prepared during the review period; Passage of the Building Bill which gives effect to the National Building Codes in House of Representatives. the codes seek to reduce vulnerability and increase resilience in the country's built environment. Coastal Management and Beach Restoration Guideline was launched. |  | Sector Ministries, Departments and Agencies (MDAs) continue to participate in Vision 2030 Jamaica Thematic Working Groups (TWGs), Climate Change Focal Point Network (CCFPN) and a number of project/programme steering committees
Coordination Mechanism Name the coordination mechanism below | Is the coordination mechanism functional e.g., established, effective and efficient? |  | Does it coordinate climate resilience interventions other than those funded by PPCR? |  | Is there a broad set of non-governmental stakeholders involved? |  | Is the relevant climate resilience information in the public domain? |  | Are females and males participating equally?
| Score reported in 2016 (last year) | Score in 2017 (new) | Score reported in 2016 (last year) | Score in 2017 (new) | Score reported in 2016 (last year) | Score in 2017 (new) | Score reported in 2016 (last year) | Score in 2017 (new) | Score reported in 2016 (last year) | Score in 2017 (new)
| 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 6
How do you justify the increase (or decrease) in scores between scores reported in the 2015 reporting period and scores reported in the 2016 reporting period? Please explain! | The Climate Change Focal Point Network (CCFPN) and Hazard Risk Reduction and Adaptation to Climate Change Thematic Working Group both remained functional. The Climate Change Advisory Board is functional and meets quarterly |  | The CCFPN members are tasked with climte change mainstreaming within their respecive entities.Five-day training workshop for the Climate Change Focal Point Network conducted by the Climate Change Division and the German Federal Enterprise for International Cooperation aimed at mainstreaming climate change considerations into development planning. The TWG provides general strategic level guidance to climate change and this was facilitated through meetings held during the year. |  | The score remains unchanged as i) the CCFPN is comprised of ministries, departments and agencies of the government and ii) non-governmental stakeholders remain involved in the TWG. The Advisory Board has membersip from NGOs, CBOs and Academia |  | Information on climate change was produced and preliminary drafts shared with stakeholders for review and comments. These included sector reports for the Third National Communication to the UNFCC which covered 5 key sectors: Water Resources; Human Health; Agriculture; Tourism; and Coastal Resources and Human Settlements. The advanced draft of the 2015 State of the Jamaican Climate was produced and shared for review. |  | There was a relative change in the ratio of men to women on the CCFPN (3:2) including members and alternates. There was also a relative even participation of men and women on the TWG. The Climate Change Advisory Board has primarily male members.
Instructions: 1. Please establish scoring criteria for each of the aspects of this scorecard and submit them with your report. This should be done once, preferably at baseline stage and used during subsequent reporting years. 2. If you have previously established your scoring criteria, use them and submit them with your report . 3. Score each cell with a score between 0 and 10 (refer to your scoring criteria defined for this scorecard) 4. Provide explanation of change in scores between 2016 and 2017 in appropriate cells and avoid abbreviations.
Gender considerations and Coordination mechanism: Please elaborate on whether and how gender good practice at the institutional level has been mainstreamed into the coordination mechanism unit This should include commentary on the number of technical staff (women, men) in the unit and whether any gender training/ capacity-building has been offered with PPCR support to: i) staff in the Coordination Unit(women, men)other Government staff working on climate change
Lessons Learned: What have been the key successes when strengthening the Government capacity and the coordination mechanism?
1. Draft Gender Review Policy has been done for Climate Change Focal Point Network. Consultations completed in Kingston and Montego Bay. It has informed decisions and policy at COP.
2. The Climate Change Division continued to pursue various initiatives related to strengthening government capacity to mainstream CC considerations in development planning. This included a five-day training of climate change focal points across all ministries, departments and agencies. The training which was done in collaboration with the German Federal Enterprise for International Cooperation covered topics such as the essentials of adaptation to climate change, assessing climate risk and vulnerability, identifying adaptation options, and selecting adaptation measures.
What have been the key challenges and what opportunities for improvement do you see?
1. Not enough deliberate consideration in incorporating gender into climate planning. Having greater collaboration between CCFP and the Gender Focal Point is an opportunity to improve.
2. Explore opportunities to have increased cadre of climate change experts across sectors.
3. Greater visibility of actions being done in Tourism sector towards improving government capacity in CC. Monitoring framework should be routinely provided to the different sectors to encourage fulfilment of Project requirements.
Sharing experiences : Please let us have some insights into the particular experience of your country with strengthening the Government capacity and the coordination mechanism to mainstream climate resilience
The government continued to support mechanisms for mainstreaming climate resilience through, inter alia, the Climate Change Focal Point Network (CCFPN). In 2017, the CCFPN met on different occasions which facilitated further agreement on their role collectively and within their respective entities as well as to build their knowledge and understanding of the climate change landscape.
Formulas:
mm/dd/yy = [3]Cover!B9

## 3 Tested
PPCR Scorecard 3 |  | (OPTIONAL) |  |  |  | Date of Report: | mm/dd/yy
PPCR Core Indicator 3: |  |  |  | Quality of and extent to which climate responsive instruments/investment models are developed and tested
Data Collection Method: |  |  |  | Scored at the project-level and compiled at the PPCR Investment plan level
PPCR Investment Plan
Project/Program Report
Reporting Period: |  |  |  | From: | 2017-01-01 | To: | 2017-12-31
Project Title | Climate responsive instrument/ investment models identified: |  |  | Has the instrument/ investment model been developed and tested? | Has the instrument/ investment model been implemented to the scale proposed? | Has the instrument/ investment model appropriately incorporated the needs of both females and males into its design and implementation? | Has the instrument/ investment model incorporated the needs of vulnerable populations into its design and implementation?
a | # | b |  | c | d | e | f
Adaptation Program and Financing Mechanism for the Pilot Program For Climate Resilience Jamaica | 1 | Climate Change Adaptation Line of Credit (CCALoC) |  | 7 | 5 | 6 | 6
|  |  |  | The CCALoC was established and became fully functional. Effectiveness of financial instrument reviewed by fund administrator and adjustments made | The CCALoC has been implemented to 52% of the scale proposed and 18 loans approved. | CCALoC appropriately incorporate the needs of both females and males into its design and monitoring. Need to more adequately integrate gender considerations and use of gender guidelines/checklists in marketing and promotion of the product | CCALoC has incorporated the needs of all vulnerable populations into its design. Need to deliberately target vulnerable groups in marketing and promotion plan
| 2 | Special Climate Change Adaptation Fund (SCCAF) |  | 8 | 8 | 10 | 10
|  |  |  | The SCCAF fully operational. Two calls for proposals made; assessment of financial instrument conducted; adjustments made and recommendations made for incorporation of lessons learnt | 80 grants approved and 44 awarded, which exceeds the scale proposed. Some grants approved in 2017 were awarded in the subsequent year. (Based on budgetary allocation the scale proposed for 2017 was a minimum of 41 grants awarded at a maximum of 5 million per grantee) | The SCCAF appropriately incorporates the needs of both females and males into both its design and implementation -Call for proposal and selection criteria | SCCAF incorporates the needs of vulnerable populations (children in pre-primary and primary level; wards of the state; at risk youth; inner city communities; women) into both its design and implementation.
| 3 | Number of water management and conservation units established - 1800 units of check dams |  | 2 | 0 | 6 | 3
|  | Briefly comment on each score |  | RFQs prepared and 1245 sites pre-selected for inspection of potential bidders when the tender is launched. |  | Design of infrastructure appropriately incorporates the needs of males and females. Consultations held with communities re the location of the check dams. | Design of infrastructure appropriately incorporates the needs of vulnerable groups.. Consultations held with communities re the location of the check dams, with specific emphasis on women and youth. Effort was made to reach persons living in remote (hard to reach) communities
| 4 | Number of water management and conservation units established - 250 communal rainwater harvesting systems |  | 0 | 0 | 0 | 0
Briefly comment on each score
| 5 | 3 Rainwater Ponds rehabilitated |  | 0 | 0 | 0 | 0
Briefly comment on each score
| 6 | 5 Aquaponics systems established and operating |  | 2 | 0 | 6 | 6
|  | Briefly comment on each score |  | TOR and specifications for design developed tender documents prepared and approved. |  | Activity specifically targets direct livelihoods for women. | Needs of vulnerable groups incorporated in the RFQ
| 7 | 3 greenhouse/ shade houses established and operating |  | 0 | 0 | 0 | 0
Briefly comment on each score
| 8 | 1 post-harvest storage and processing facilities established/ rehabilitated |  | 0 | 0 | 0 | 0
| 9 | Amount disbursed to MSMEs, NGOs and CBOs (through the climate change adaptation line of credit) to finance climate change resilience activities. |  | 8 | 8 | 6 | 6
|  |  |  | USD 1.06 of 2.5 MN allocated. Components in place for implementation and review | Scale proposed in amount invested is USD 1.25 MN and up 84% was achieved | CCALoC appropriately incorporate the needs of both females and males into its design and monitoring. Need to more adequately integrate gender considerations and use of gender guidelines/ checklists in marketing and promotion of the product | CCALoC has incorporated the needs of all vulnerable populations into its design. Need to deliberately target vulnerable groups in marketing and promotion plan
| 10 | Amount disbursed to MSMEs, NGOs and CBOs (through the Special Climate Change Adaptation Fund) to finance climate change resilience activities. |  | USD 1.61 MN | 0 | 0 | 0
| 11 | PPCR webpage developed and functioning |  | 8 | 9 | 6 | 9
|  |  |  | PPCR website developed and launched | Website fully implemented to the scale proposed | Website could better feature the benefits derived from the project by different groups | Website incorporates special features for the visually and hearing impaired. Social media platforms interconnected.
| 12 | Report on project’s methodologies, techniques, lessons learned and good practices |  | 0 | 0 | 0 | 0
Improving Climate Data and Information Management Project | 1 | All weather stations |  | 7 | 4 | 5 | 5
|  | Briefly comment on each score |  | Determination of specifications for system upgrade, procurement completed and staff trained | App 50% of stations to upgrade network installed | The network has been upgraded taking the needs of females and males into the design specifically in relation to the location and coverage of the stations. AWS consoles installed in easily accessible places. A real time data system will be installed which will improve accessibility of data. | The network has been upgraded taking the needs of vulnerable groups into the design specifically in relation to the location and coverage of the stations. AWS consoles accessible to vulnerable groups. A real time data system will be installed which will improve accessibility of data.
| 2 | Agro-met stations |  | 7 | 2 | 5 | 5
|  | Briefly comment on each score |  | Determination of specifications for system upgrade, procurement completed and staff trained | App 20% of stations were installed | The network has been upgraded taking the needs of females and males into the design specifically in relation to the location and coverage of the stations. AWS consoles installed in easily accessible places. A real time data system will be installed which will improve accessibility of data. | The network has been upgraded taking the needs of vulnerable groups into the design specifically in relation to the location and coverage of the stations. AWS consoles accessible to vulnerable groups. A real time data system will be installed which will improve accessibility of data.
| 3 | Upgrade to data transmission of existing stations (AWS) |  | 2 | 0 | 5 | 5
|  | Briefly comment on each score |  | Specifications developed, and supplier was identified to develop the real time data system and the procurement process is ongoing. | This has not yet been implemented. | The real time data system will capture information for both AWS and Agro-met stations and will increase the accessibility to both women and men. | The real time data system will capture information for both AWS and Agro-met stations and will increase the accessibility for vulnerable groups including real time messaging.
| 4 | Automatic intensity rain gauges |  | 10 | 9 | 5 | 5
|  | Briefly comment on each score |  | Equipment installed, commissioned and operational. | 17 of 18 stations installed. | Information from the intensity rain gauges take the needs of both women and men in the design; however even though the WRA has access to the network in real time the information is not yet made directly available to the public via a website etc. | Information from the intensity rain gauges take the needs of both women and men in the design; however even though the WRA has access to the network in real time the information is not yet made directly available to the public via a website and direct messaging.
| 5 | Stream/flow river gauging loggers |  | 10 | 10 | 5 | 5
|  | Briefly comment on each score |  | Equipment installed, commissioned and operational. | System implemented to a greater scale than proposed. | Information from the stream flow monitors take the needs of both women and men in the design; however even though the WRA has access to the network in real time the information is not yet made directly available to the public via a website etc. | Information from the stream flow monitors take the needs of both women and men in the design; however even though the WRA has access to the network in real time the information is not yet made directly available to the public via a website and direct messaging.
| 6 | Upgrade to rainfall intensity gauging network |  | 10 | 9 | 5 | 5
|  | Briefly comment on each score |  | The real time network developed, tested and commissioned | 90 % of systems reporting in real time. | The real time data system takes the needs of both women and men in the design, however the information is not yet available directly to the public directly via a website etc. | The real time data system takes the needs of vulnerable groups in the design, however the information is not yet available to the vulnerable groups via website or direct messaging.
| 7 | Ground water monitoring loggers |  | 10 | 10 | 5 | 5
|  | Briefly comment on each score |  | Loggers procured, tested and staff trained | 100% of mobile loggers being used. Fixed loggers will be installed in 2018 as per work plan | Information from the loggers will be beneficial to both females and males, especially in real time. | Information from the stream flow monitors will be beneficial to vulnerable groups.
| 8 | Soil moisture probes |  | 4 | 0 | 5 | 5
|  | Briefly comment on each score |  | 33 soil moisture probes procured (12 WRA and 21 MSJ) | WRA to partner with National Irrigation Commission in the installation of soil moisture probes while the MSJ will partner with Rural Agricultural Development Authority | Information from the soil moisture probes will benefit both females and males | Information from soil moisture probes will benefit vulnerable groups
|  | Back up power supplies |  | 10 | 10 | 10 | 10
| 9 | Briefly comment on each score |  | Standby generators were procured for the MSJ and the WRA | Both installed and operational. | Yes | Yes
| 10 | Weather Doppler Radar |  | 2 | 2 | 5 | 5
|  | Briefly comment on each score |  | Specifications were finalized and approved in 2017. | Specifications developed taking into consideration all the needs of the MSJ. Gap assessment in the forecasting process also completed and relevant element incorporated in the specifications | Yes: specifications incorporate gender consideration to be reflected in design | Yes: specifications incorporate vulnerable groups and to be reflected in design
| 11 | Climate Scenarios/2015 State of Jamaican Climate report |  | 10 | 5 | 10 | 10
|  | Briefly comment on each score |  | Models downscaled, report completed and stakeholders trained | Data was not available across a wide network | Yes: provides analysis of impact by gender with focus on impact by sector. For example impact on women's health and with respect to water | Yes: provides analysis of impact on different vulnerable groups especially in 7 vulnerable communities
| 12 | Vulnerability Assessment and Costed Plan for Health Sector |  | 3 | 0 | 5 | 5
|  | Briefly comment on each score |  | Terms of reference (TOR) for consultant was completed. | not yet implemented | Yes | Yes
| 13 | Vulnerability Assessment of Priority sectors |  | 2 | 0 | 5 | 5
|  | Briefly comment on each score |  | Approval granted to contract a Project Officer to oversee implementation at the Office of Disaster Preparedness and Emergency management | Not yet implemented | Yes | Yes
| 14 | Community Risk profiling |  | 2 | 0 | 5 | 5
|  | Briefly comment on each score |  | Approval granted to contract a Project Officer to oversee implementation at the Office of Disaster Preparedness and Emergency management | Not yet implemented | Yes: messaging will specifically target gender | Yes: activity specifically addresses vulnerable groups in vulnerable communities
| 15 | Upgraded GOJ Web Portal for Climate Change Disaster Risk and end users access |  | 4 | 2 | 5 | 5
|  | Briefly comment on each score |  | Search software, enterprise service router and layer three switch procured. | The design has taken all the needs of the NSDMD and different categories of end users | Yes | Yes
| 16 | Information Education and behaviour change campaigns |  | 5 | 1 | 5 | 5
|  | Briefly comment on each score |  | A Behaviour Change Specialist contracted and Programme developed and pre-tested. Panos Caribbean contracted to implement voices for Climate Change initiative. | Behaviour Change program designed not yet implemented | The public education/behaviour change campaigns will target both male and females. | Several vulnerable groups will be targeted including farmers, children and the elderly.
Financing water adaptation in Jamaica’s new urban housing sector | 1 | 2 Launch events hosted |  | 2 | 0 | 5 | 2
|  | Briefly comment on each score |  | Event concept developed – activity put on hold pending completion of IDB market demand study and the initial design of loan |  | Appropriately incorporates the needs of both females and males into its design but implementation has not yet commenced | Incorporates the needs of 1-2 vulnerable populations into its design
| 2 | Home owner's guide to water management developed |  | 2 | 0 | 5 | 2
|  | Briefly comment on each score |  | Specifiations for Guide developed |  | Appropriately incorporates the needs of both females and males into its design but implementation has not yet commenced | Incorporates the needs of 1-2 vulnerable populations into its design
| 3 | Online platform is accessed (number of times) |  | 4 | 2 | 5 | 2
|  | Briefly comment on each score |  | ToR for procurement developed and far advanced/near completion | Technology or infrastructure investment implemented up to 30% of the scale proposed | Appropriately incorporates the needs of both females and males into its design but implementation has not yet commenced | Incorporates the needs of 1-2 vulnerable populations into its design
| 4 |  |  | 0 | 0 | 0 | 0
Briefly comment on each score
| 5 |  |  | 0 | 0 | 0 | 0
Briefly comment on each score
There are no outputs for the Financing Water Adaptation in Jamaica's New Urban Housing Sector Project as that project was approved in 2017 .
Lessons Learned: AP&FM
What have been the key successes when developing and testing these instruments/investment models?
1. Important to make procurement a participatory exercise to include key implementing entities
2.Genuine need for systems being provide by the loan. Mentoring/coaching of applicants to support readiness for access to loans provided, primarily applicants for agricultural solutions. Opportunity to document assistance given.
3.Particular work needs to be done to stimulate demand in the targeted markets for the consultants required - e.g.. Hosting of pre-bidders conference
What have been the key challenges and what opportunities for improvement do you see?
1.Adequately Incorporating gender considerations in project implementation - More training in how to apply gender checklists (Gender Policy)will have to be applied/adapted to assess integration of gender considerations/equity in the climate responsive instruments and investment models
2.It is difficult to assess gender equality and the incorporation of the needs of vulnerable population in the design and implementation of the agro-met equipment.
3.Fund administrator of CCaLOC will be asked to adjust marketing and promotion plan to specifically target by gender and vulnerable groups
4. Website could incorporate more stories/lessons learnt for gender
Lessons Learned:ICDIMP
What have been the key successes when developing and testing these instruments/investment models?
1.It is important to conduct research into the suitability of equipment in relation to local conditions in order to procure equipment that is fit for purpose. The equipment procured for water monitoring utilised by the WRA generally worked very efficiently in most conditions even in remote locations because research was conducted to ensure that equipment was suitable for local conditions.
2. It is beneficial to train staff of the implementing entities in the installation and maintenance of the equipment to ensure sustainability of the monitoring networks. Technical staff of both the Water Resources Authority (WRA) and the Meteorological Services Division both received training in the use of the equipment being installed. As a result, the WRA was able to install entire water monitoring network without the need for external contractors.
3. The development of Terms of References that takes into consideration all the needs of the consultancy, is clear and easy to understand by consultants. This will help to facilitate responses to the request for Expressions of Interest which are most suited to the consultancy. This was evident in the preparation of Terms of Reference for the Doppler Weather Radar consultancy.
What have been the key challenges and what opportunities for improvement do you see?
1. The MSJ lost their capacity to set-up, install and maintain the Automatic Weather Stations, due to the retirement of one senior officer and the untimely death of another . This issue therefore presented an opportunity to build the capacity of MSJ staff by conducting cross-divisional training during the installation process of the AWS. This was supported by the preparation of a Manual to aid in installation and maintenance. An opportunity also exists to train the MSJ voluntary observers and AWS partners to ensure that a high standard of data collection is maintained across the manual rain gauges
2. The project required the engagement of a number of specialist who are not readily available. This resulted in delays in procurement, the need to search regionally and internationally and to adjust work plans
3. Staff turnover in partner agencies results in delays as there is a learning curve for new focal points who sometimes have differing ideas from their predecessors.
Formulas:
mm/dd/yy = [1]Cover!B9

## 4 Used
PPCR Table 4 | [7 empty] | Date of Report: | mm/dd/yy
PPCR Core Indicator 4: |  |  | Extent to which vulnerable households, communities, businesses and public sector services use improved PPCR supported tools, instruments, strategies, activities to respond to Climate Variability and Climate Change
Data Collection Method: |  |  | Data collected for each project and compiled at the PPCR investment plan level
Country Aggregate Report
Reporting Period: |  |  | From: |  | 2017-01-01 | To: | 2017-12-31
A- Tools/instruments developed for the Households
# | Name of the tool/invest model | Project | Number of Households |  | Please describe how the tools, instruments, strategies, and activities developed by the project have help households increase their adaptive or resilience capacity.
|  | Title | Actual results (Cumulative since project started) | Expected Results | Please provide 1 example from the project for each of the tools/instruments identified
1 | Automatic Weather Stations | ICDIMP | 15256 | 25903 | Households have direct access to the data from Automatic Weather Stations installed in their communities. Data from at least 4 AWS are also available online in real time.
2 | Agro-met Stations | ICDIMP | 3790 | 24261 | Farming communities have direct access to the data for the Agro-met stations. Data from 2 Agro-met stations are available online in real time.
3 | Early warning system (Bog Walk) | ICDIMP | 3459 | 3459 | Apart from the Bog Walk community, the Gorge is a main linkage ( Class A road) between the Corporate Area and the North Coast and is heavily used
4 | Sea Level Tide Gauge | ICDIMP | 32953 | 32953 | The sea level tide gauge is located at the Montego Bay Pier and provides information on changes in sea levels particularly for the city which is an important tourist destination in the country.
B: Tools/instruments developed for the Communities
# | Name of the tool/invest model | Project | Number of Communities |  | Please describe how the tools, instruments, strategies, and activities developed by the project have help communities increase their adaptive or resilience capacity.
|  | Title | Actual results (Cumulative since project started) | Expected Results | Please provide 1 example from the project for each of the tools/instruments identified
1 | Automatic Weather Stations | ICDIMP | 9 | 21 | Community stakeholders have access to the data provided by the AWS .The number reflects the number of communities within which AWS have been installed.
2 | Agro-met Stations | ICDIMP | 3 | 14 | Community stakeholders have access to the data provided by the Agro-met Stations via project partners such as schools where consoles are erected. Agro-met stations have been primarily installed in farming communities.
3 | Early warning system (Bog Walk) | ICDIMP | 1 | 1 | The early warning system developed for the Bog Walk Gorge has contributed to the safe guarding of life and property on this important thoroughfare in the parish of St. Catherine. Since the installation of the system WRA has been able to inform the Office of Disaster Preparedness and Emergency Management and the Jamaica Constabulary Force about the rising stage of the Rio Cobre river resulting in the timely closure of the access points to the public.
4 | Sea Level Tide Gauge | ICDIMP | 1 | 1 | The sea level tide gauge installed on the Montego Bay Pier is the only such equipment on the North Coast and therefore bridges a critical data gap in the country's hazard information. The data from the gauge also feeds directly into the Caribbean tsunami warning system.
C: Tools/instruments developed for the Public services
# | Name of the tool/invest model | Project | Number of Public Services |  | Please describe how the tools, instruments, strategies, and activities developed by the project have help Public services increase their adaptive or resilience capacity.
|  | Title | Actual results (Cumulative since project started) | Expected Results | Please provide 1 example from the project for each of the tools/instruments identified
| Automatic Weather Stations | ICDIMP | 4 | 20 | Most public sector partners are educational institutions which provides a good opportunity for mainstreaming the use of the information
1 | Back Up Power Supplies | ICDIMP | 2 | 2 | Back up power supplies have improved business continuity for the Met Service Jamaica and the Water Resources Authority. This has proved particularly beneficial during incidents of outage of the public power supply which normal disrupt the operations of the agencies. The MSJ is an essential service and there needs ongoing access to uninterrupted power supply to minimize data loss and facilitate timely and accurate forecasting. Prior to the project, the agency had no back up power.
4 | Intensity rain gauges | ICDIMP | 2 | 2 | The WRA utilizes the data from the intensity rain gauges in daily operations. The MSJ has direct access to this data as well from the real time data platform.
5 | Streamflow/river gauging loggers | ICDIMP | 2 | 2 | The WRA utilizes the data from the Streamflow gauges in their daily operations. The National Irrigation Commission also benefits from this data directly.
6 | Downscaled climate models providing information (projections and impact) by sector and geographic area - 2015 State of Jamaica Climate Report | ICDIMP | 22 | >50 | The report was completed in 2017 and a stakeholders workshop hosted to disseminate the findings and demonstrate how the data can be applied; report officially published and launched in 2018. Data from the report was utilized in planning, preparation of reports and documents and other activities by several entities.
7 | Real Time Data collection System | ICDIMP | 1 | 1 | Real time data system has contributed to the improvement in the efficiency of operations of the Water Resources Authority (WRA), for e.g. the WRA has indicated that previous to the setting up of the system, it required a minimum of 8 weeks to generate a report on a particular rainfall event this can now be done within a week. This period includes all quality assurance checks being done. This was demonstrated in the November 2017 flood rains in Montego Bay.
D: Tools/instruments developed for the Businesses
# | Name of the tool/invest model | Project | Number of Businesses |  | Please describe how the tools, instruments, strategies, and activities developed by the project have help Businesses increase their adaptive or resilience capacity.
|  | Title | Actual results (Cumulative since project started) | Expected Results | Please provide 1 example from the project for each of the tools/instruments identified
1
2
3
A- Tools/instruments developed for the Households
# | Name of the tool/invest model | Adaptation Programme & Financing Mechanisms Project for PPCR Jamaica (AP&FM) | Number of Households |  | Please describe how the tools, instruments, strategies, and activities developed by the project have help households increase their adaptive or resilience capacity.
|  |  | Actual results (Cumulative since project started) | Expected Results | Please provide 1 example from the project for each of the tools/instruments identified
1 | Vulnerability assessments developed for 15 priority communities | AP&FM | 0 | 12187.5 | The assessments will cover hazard assessment and mapping and risk profile for all of the Rio Minho Watershed and prioritize 15 communities of the Upper Rio Minho Watershed (URMW) to reduce the vulnerabilities and mitigate the climate change risks
2 | Climate Change Adaptation and Disaster Risk Reduction (CCA/DDR) plans developed for 15 priority communities | AP&FM | 0 | 12187.5 | Climate change adaptation plan for the RMWMU and disaster risk reduction / climate change adaptation (DRR/CCA) plans for fifteen pre-selected priority communities in the URMW Area.
3 | Climate change vulnerability assessments conducted for 5 Sectors | AP&FM | N/a
4 | 27 climate change focal points trained in leading and coordinating the mainstreaming of climate change | AP&FM | N/a
5 | Construction of 1800 Check Dams | AP&FM | 0 | 12187.5 | The check dams will enhance soil water retention and prevent soil erosion in the Upper Rio-Minho Watershed Area thereby building resilience to climate change
6 | Instalment of 250 communal rainwater harvesting systems | AP&FM | 0 | 12187.5 | These are communal systems to improve access to water for domestic use.
7 | Rehabilitation of 3 rain ponds | AP&FM | 0 | 1500 | Estimated # of farmers per pond is 500
8 | Construct and operate 5 aquaponics systems | AP&FM | 0 | 200 | The existing ponds in URMW at Reckford, Redland and Bog Hole will increase harvesting and access to rainwater. The estimated average farmers per pond is 500
9 | Construct and operate 3 greenhouses/ shadehouses | AP&FM | 0 | 30 | About 10 workers per facility is estimated as direct beneficaries. Each worker represent a household
10 | Construct/ Rehabilitate and operate agro processing plant | AP&FM | 0 | 10 | Workers comprise direct beneficaries. Each worker represent a household
11 | Facilitate access to financing to MSMEs through the Climate Change Adaptation Line of Credit | AP&FM | 151 | 600 | Based on completed projects, 151 workers or an average of 8 per project were directly employed. Each worker was assumed to represent one household. Businesses access funding by way of grants and/or loans to climate proof their businesses, organizations and/or communities
12 | Financing disbursed to NGOs/ CBOs through SCCAF for climate change resilience activities. | AP&FM | 3711 | 11330 | Based on completed projects, 3711 direct beneficiaries were counted or an average of 206 per project. Expected beneficiaries derived from the maximum # of $5MN grants within the SCCAF budget (=55), and average direct beneficiaries of completed projects (=206).Community Based Organizations among other entities access funding by way of grants and/or loans to climate proof their businesses, organizations and/or communities Expected result = Beneficiaries per completed project (250) x Expected number of grants (55) Assumption that each beneficiary represents a household
13 | PPCR webpage developed and functioning | AP&FM | 998 visits | >100 visits | Members of the public and development partners visit the website for information on climate change adaptation and mitigation measures, strategies and policies
14 | Report on project’s methodologies, techniques, lessons learned and good practices | AP&FM | N/a
….
B: Tools/instruments developed for the Communities
# | Name of the tool/invest model | Adaptation Programme & Financing Mechanisms for PPCR Jamaica | Number of Communities |  | Please describe how the tools, instruments, strategies, and activities developed by the project have help communities increase their adaptive or resilience capacity.
|  |  | Actual results (Cumulative since project started) | Expected Results | Please provide 1 example from the project for each of the tools/instruments identified
1 | Vulnerability assessments developed for 15 priority communities | AP&FM | 0 | 15
2 | Climate Change Adaptation and Disaster Risk Reduction (CCA/DDR) plans developed for 15 priority communities | AP&FM | 0 | 32
5 | Construction of 1800 Check Dams | AP&FM | 0 | 17
6 | Instalment of 250 communal rainwater harvesting systems | AP&FM | 0 | 17
7 | Rehabilitation of 3 rain ponds | AP&FM | 0 | 3
8 | Construct and operate 5 aquaponics systems | AP&FM | 0 | 5
9 | Construct and operate 3 greenhouses/ shadehouses | AP&FM | 0 | 3
10 | Construct/ Rehabilitate and operate agroprocessing plant | AP&FM | 0 | 1
11 | Facilitate access to financing to MSMEs through the Climate Change Adaptation Line of Credit | AP&FM | 18 | 64 | Each Micro Small & Medium Enterprise (MSME) represents one community. Businesses access loan funding to climate proof their businesses and/or livelihoods
12 | Financing disbursed to NGOs/ CBOs through the Special Climate Change Adaptation Fund for climate change resilience activities. | AP&FM | 18 | 55 | Community Based Organizations and other entities access funding by way of grants to implement climate change adaptation measures. Each entity represents one community
….
C: Tools/instruments developed for the Public services
# | Name of the tool/invest model | Adaptation Programme & Financing Mechanisms Project for PPCR Jamaica | Number of Public Sector Entities |  | Please describe how the tools, instruments, strategies, and activities developed by the project have help Public services increase their adaptive or resilience capacity.
|  |  | Actual results (Cumulative since project started) | Expected Results | Please provide 1 example from the project for each of the tools/instruments identified
2 | Climate Change Adaptation and Disaster Risk Reduction (CCA/DDR) plans developed for 15 priority communities | AP&FM | 0 | 2 | Office of Disaster Preparedness & Emergency Management and Parish Disaster Committee of the Clarendon Municipal Corporation
3 | Climate change vulnerability assessments conducted for 5 Sectors | AP&FM | 0 | 4 | Ministries with portfolio responsibility for five PPCR priority sectors and their related departments and agencies
4 | 27 climate change focal points trained in leading and coordinating the mainstreaming of climate change | AP&FM | 0 | 27
5 | Construction of 1800 Check Dams | AP&FM | 0 | 1 | RADA
7 | Rehabilitation of 3 rain ponds | AP&FM | 0 | 1 | RADA
10 | Construct/ Rehabilitate and operate agroprocessing plant | AP&FM | 0 | 2 | RADA and the Jamaica Agricultural Society (JAS) would have oversight responsibilities for the plant
13 | PPCR webpage developed and functioning | AP&FM | 15 | 15 | Represents the number of direct PPCR partner agencies. Website received approximately 1000 hits during the reporting period
14 | Report on project methodologies, techniques, lessons learned and good practices | AP&FM | 0 | 15 | Represents the number of direct PPCR partner agencies
….
D: Tools/instruments developed for the Businesses
# | Name of the tool/invest model | Adaptation Programme & Financing Mechanisms Project for PPCR Jamaica | Number of Businesses |  | Please describe how the tools, instruments, strategies, and activities developed by the project have help Businesses increase their adaptive or resilience capacity.
|  |  | Actual results (Cumulative since project started) | Expected Results | Please provide 1 example from the project for each of the tools/instruments identified
8 | Construct and operate 5 aquaponics systems | AP&FM | 0 | 5
9 | Construct and operate 3 greenhouses/ shadehouses | AP&FM | 0 | 3
10 | Construct/ Rehabilitate and operate agroprocessing plant | AP&FM | 0
11 | Facilitate access to financing to MSMEs through the Climate Change Adaptation Line of Credit | AP&FM | 18 | 64 | Business loans supported climate proofing for businesses in agriculture and tourism through installation of Rainwater harvesting systems, water re-circulation system, drip irrigation systems, greenhouses, implementation of climate smart agriculture techniques (contour ploughing, terracing), water harvesting, climate resilient holding facilities for animals, water tanks. Example - Small hotel facility installed 3.1 million gallon rainwater harvesting system to support ecotourism. Expected Number of loans = budget envelope ÷ maximum per loan (JMD5MN)
12 | Financing disbursed to NGOs/ CBOs through SCCAF for climate change resilience activities. | AP&FM | 44 | 55 | Resilience of CBOs/NGOs built and resulted in over 150,000 gallons of water in storage facilities; 6,000 square feet in greenhouse cultivation; 5 acres of land under cultivation; 64 solar panels and 5 solar pumps; protected 4.21 km area for fish; established 5 coral nurseries; direct employment provided for 182 individuals; 209 persons trained. Example - Frankfield Primary & Infant School P.T.A - 3,000 sq. ft. greenhouse and 40,000 gallon tank constructed; over 1000 lbs of vegetables harvested Expected Number of grants = budget envelope ÷ maximum per grant (JMD5MN)
….
Instructions: 1. Clearly identify the target population of your instruments / investment models/tools etc. : Is it Households? Communities? Businesses (private sector), public service entities or a combination thereof (refer to the project documents). 2. Actual results: cumulatively report results achieved since the project started implementation. Expected Results: Results expected to be achieved at completion of the project as stated in the project document. 3. Always provide written comments on how the target population identified in this table will use the instruments/investment models/tools to respond to climate change. 4. Add more lines under each project if needed.
**There are no entries for the Financing Water Adaptation in Jamaica’s new urban housing sector as the project received effectiveness in October 1, 2017

## 5 Supported
PPCR Table 5 | [5 empty] | Date of Report:
| PPCR Core Indicator 5: | Number of people supported by the PPCR to cope with the effects of climate change
| Data Collection Method: | Data collected for each project and compiled at the PPCR Investment Plan level
Jamaica
Country Aggregate Report
| Reporting Period | From: | 2017-01-01 | To: | 2017-12-31
[6 empty] | Direct beneficiaries |  | Indirect beneficiaries1 |  | Total beneficiaries
[6 empty] | Actual results (Cumulative since project started) | Expected Results | Actual results (Cumulative since project started) | Expected Results | Actual results (Cumulative since project started) | Expected Results
Project Title | a |  |  |  |  | b | c | d | e | f | g
Improving Climate Data and Information Management Project | Number of people supported by the PPCR to cope with the effects of climate change (serves entire population) |  |  |  |  | 161197 | 412485 | 2567667 | 2316379 | 2728864 | 2728864
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 91666 | 191095 | 1186377 | 1186377 | 1377472 | 1377472
Adaptation Programme & Financing Mechanism - Financing | Number of people supported by the PPCR to cope with the effects of climate change (#s will change when community interventions begin) |  |  |  |  | 3862 | 11330 | 11972.2 | 35123 | 15834.2 | 46453
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 2061 | 6051 | 6389.1 | 18758.1 | 8450.1 | 24809.1
Financing water adaptation in Jamaica’s new urban housing sector | Number of people supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | TBD | 0 | TBD | 0 | TBD
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | TBD | 0 | TBD | 0 | TBD
Jamaica (aggregation) | Total number of people supported by the PPCR to cope with the effects of climate change in the country |  |  |  |  | 165059 | 423815 | 2567667 | 2316379 | 2728864 | 2728864
| Total number of females supported by the PPCR to cope with the effects of climate change in the country |  |  |  |  | 93727 | 197146 | 1192766.1 | 1205135.1 | 1385922.1 | 1402281.1
1 - Direct female beneficiaries in the ICDIMP communities accounted for 56.9% of total while those in the AP&FM communities accounted for 53.3%. Because the ICDIMP benefits the entire population, the Indirect beneficiaries will be the difference between the total pop and those directly benefiting 2.Expected Result -direct beneficiaries for AF&FM = sum of the maximum number of grants and loans @J$5m each *actual beneficiaries to date
Instructions: 1. Actual results: cumulatively report the number of people supported by the project since it started implementation. 2. Expected Results: number of people expected to be reached by the project at completion as stated in the project document. 3. If the target population of the project is households or communities, provide best estimates of the number of people in these households or communities. Triangulate this data with data provided in Table 4 for consistency. 4.Please do not leave cells. Put Zero(0)in the corresponding cell if people are not supported yet by the project.
Lessons Learned: ICDIMP
What have been the key successes when people have been supported by the PPCR?
1.The early warning system in the Bog Walk Gorge has contributed to the safeguarding of life and property within the area. Since the development of the system no lives have been lost as a result of flooding in the gorge.
2. The upgrading of the hydro-met network has contributed to significant improvements in the operations of the Water Resources Authority.
3. The Installation of AWS by the MSJ has improved the quality and reliability of data collected by the entity.
4. Having a project champion in a partner agency helps to drive interest and promote ownership. This is the case in the WRA which is well advanced in the installation and use of their upgraded systems.
5. The capacity of the MSJ staff has been improved in regards to the set-up, installation and maintenance of Automatic Weather Stations across the Island
What have been the key challenges and what opportunities for improvement do you see?
1.Procurement of highly technical equipment require a long lead time and multi-layered approval process. This results in a lag time between the procurement and installation of equipment and the delivery of services. Frontload as much of the procurement to the extext possible.
2.Obtaining planning permits for installation of equipment can result in delayed implementation as it was not possible to obtain a 'blanket permit' due to the fact that sites are in different planning jurisdictions.
Lessons Learned: AP&FM
What have been the key successes when people have been supported by the PPCR?
1. Climate financing as a business process, whether for small or larger businesses, requires significant effort in educating the marketplace about the link between climate change adaptation and business success. It was after the PPCR partners began to reach the target market with information and education campaigns that the fund administrators got a more significant uptake.
2. Significant 'Learning By Doing' is experienced by the grant beneficiaries under the SCCAF, which is leading to the fine-tuning of implementation activities at the sub project level. The Environment Foundation of Jamaica (EFJ)(grant administrators) and the PEU for the AP&FM encourage interaction and networking between grantees and this knowledge sharing drives innovation in project designs as well as builds capacity at a peer-to-peer level between groups of different communities. The training of potential grantees in proposal writing improved the quality of proposals submitted for approval.
3.The importance of partnerships was evident in the implementation of some of the projects under the SCCAF. Many grant beneficiaries expressed the benefits of partnerships with government entities in implementing their projects. For example one grantee partnered with the National Works Agency which provided support in the construction of culverts and drains to alleviate flooding and soil erosion.
What have been the key challenges and what opportunities for improvement do you see?
1. A significant number of PPCR project activities are at an advanced stage of procurement and should enter implementation in 2018. This will push the implementation team for the AP&FM to full capacity for the contract management, coordination and monitoring of a number of activities at once.
**There are no entries for the Financing Water Adaptation in Jamaica’s new urban housing sector as the project received effectiveness in October 1, 2017

## Scoring Workshop Summary
Summary of the scoring workshop
Who were the different stakeholder groups invited to the scoring workshop (composition and number)? Please attach the list of participants.
The assessment of Jamaica's progress on the five core indicators of its Strategic Programme for Climate Resilience for 2017was facilitated through a scoring workshop held between July 19 and 20, 2018. A total of XX stakeholders representing xx public and private sector entities and civil society were invited to share their knowledge on climate adaptation and resilience building initiatives/activities which would have been pursued during the reporting period. Thirty-Nine (39) stakeholders, 14 males and 25 females were in attendance, representing a 44 per cent increase over the number of participants last year. Almost half of the stakeholders were participating in the workshop for the first time (See List of Workshop Participants and Invitees in Appendix 1). Attendees included project managers or their designated representative from all four investment projects being implemented under Jamaica’s SPCR - Improving Climate Data and Information Management, and Adaptation Program and Financing Mechanisms for the PPCR in Jamaica, the recently approved Promoting Community Based Resilience in the Fisheries Sector Project and the Financing Water Adaptation in Jamaica’s New Urban Housing Sector, the latter of which is being implemented via PPCR private sector set-aside resources. Representatives of the Project Management Unit of the regional PPCR project and the respective coordinating entity also participated in the workshop. Stakeholders representing the implementing partner agencies for all the projects were also among the participants. . Representatives from the PPCR priority sectors were also in attendance including representatives from agencies with responsibility for health, water resources, meteorology, environment and agriculture and fisheries. The private sector and civil society groups from the Human Settlement and Coastal resources priority sectors were also represented.
How did you define your scoring criteria for Scorecards 1 and 2 (national level) and scorecard 3 (project level)? Please attach scoring criteria for scorecards 1, 2, and 3
The PPCR Focal Point and team developed a set of criteria and used information and data from a cross-section of sources to prepare the scorecard and recommend scores for the baseline and the 2014 reports. These were subsequently crossed checked with a number of sector specialists and experts in the PPCR priority sectors and complemented with the outputs from other consultations including under Vision 2030 Jamaica - National Development Plan. For the 2014 review, two scoring workshops were conducted over the periods May 21-22, 2015 and June 23, 2015. The first was led by the CIF- AU in partnership with the IADB and supported by the IBRD(World Bank) ; participants were introduced to the scoring toolkit, required process and timelines for completing the monitoring reports. At the May workshop, stakeholders agreed to having the scoring criteria for national level planning as distinct from sector-level criteria (for Indicators 1 and 2). A two-stage approach was used to define the national scoring criteria Firstly, participants were grouped and established draft criteria. Secondly, the groups came together in plenary where the output of all was discussed, reviewed and amended. At the second Scoring workshop in June, the national level scoring criteria were refined and approved. Acting on the decision of the May 2015 workshop for the preparation of sector criteria and in the interest of jump-starting the discussion, draft sector-level criteria were prepared by the Focal Point and team using the national as a guide. These were presented to the June 23 meeting, discussed, amended and approved. The scoring criteria for Indicator 3 were defined in 2016 primarily due to the fact that neither of the projects had commenced when the report was being prepared in 2015. In a project team scoring meeting on May 31, 2016 the draft criteria for Indicator 3 was prepared by the PPCR Focal point and the Project Managers from both the Improving Climate Data and Information Management and the Adaptation Programme and Financing Mechanism Projects . The meeting was not held in the first quarter of the year as recommended by the toolkit since both projects were still in the process of establishing their Project Management Units at that time. The criteria were defined based on the five categories of climate responsive instruments/investment models identified in the M&R toolkit (2016). This was done out of a realization that each type of climate responsive instrument/investment model will have different stages of development. The criteria were presented to stakeholders, discussed, refined and accepted at the Scoring Workshop on June 9 and 10, 2016.
Please provide a brief summary of the workshop (What were the key issues raised during the workshop? )
As in previous years, the scoring exercise was held over two days with the main objectives being to i. provide participants with a background to the PPCR, Jamaica’s SPCR and the PPCR monitoring and reporting process, including an overview of PPCR progress to date; ii. Discuss and finalize scores for Indicators 1 and 2 and validate scores for indicators 4 and 5 in the PPCR Monitoring and Reporting Toolkit; iii Provide participants with an update on changes to the toolkit; and iv.allow investment project implementing entities and beneficiaries to share project status, achievements/success stories/lessons learnt associated with implementation of PPCR projects (See Appendix 2 for Workshop Agenda). In preparation for the meeting, participants were provided with a copy of 2018 M&R Toolkit and a copy of the 2016 Report. On the first day of the workshop participants were presented with a general overview of the CIF, PPCR and Jamaica’s SPCR as well as the 7 steps involved in scoring indicators 1 and 2 was also introduced. Emphasis was placed on the importance of the exercise, citing the need for accountability to both donors and the Jamaican population. Similar to the previous year, the presentation on the M&R process served as a refresher to regular participants as well as an introduction to our 17 new participants. The change in representatives of implementing partner agencies or sector specialists is an issue which has faced the scoring process, impacting both the time taken to explain the process as well as that taken to understand and assimilate the process. Despite this, however, all workshop participants provided meaningful input and contributed to spirited discussions to arrive at final scores. In order to facilitate the scoring for Indicators 1 and 2, the stakeholders were divided into two groups, each focusing on a single Indicator. Each group was provided with a hard copy of the M&R toolkit, hard copies of the 2016 report scorecards for Indicators 1 and 2, and resource material such as the Economic and Social Survey Jamaica 2017 which includes information on resilience building initiatives for all sectors for the reporting period. While the scoring did not benefit from the input of some sector specialists on the days that the workshop was hosted, input was provided through a post workshop review of the scorecards. Following on a recommendation from the previous scoring workshop, scoring at the project level was done prior to the scoring workshop and was presented and validated on Day 2 of the workshop. There was some discussion on the identification of the beneficiary groups associated with the modification of scorecard 4. It was also decided that although Scorecard 3 was optional, Jamaica will continue to complete the scorecard to capture progress made on project outputs. A new Item on the workshop agenda this year was the Knowledge Sharing Session. This was held out of the recognition for the need to not only monitor project progress as it relates to outputs but share how these outputs have been impacting the lives of Jamaican households, communities, public and private sector entities and civil society. Presentations were delivered by the Water Resources Authority (beneficiary under the Improving Climate Data and information Management Project); the White River Fish Sanctuary (beneficiary under the Adaptation Programme and Financing Mechanisms Project); JN Foundation (implementing entity of the Water Project) and the PPCR Communications Specialist (See Knowledge Sharing attachment). Feedback from participants was very positive as they indicated that it not only served to make them more aware of what was being achieved under the projects but also served as a source of motivation for those projects in the early phases of implementation. Among the key issues emanating from the discussions were the need for more deliberate effort to follow up with ministries, departments and agencies in the priority sectors to ensure that low scoring areas are being addressed. This could be achieved by a joint effort between the Climate Change Division and the PPCR focal point making interventions on a quarterly or bi-annual basis through visits/presentations at strategic planning retreats etc. The need for a greater understanding of gender and climate change and how to better include gender considerations in the mainstreaming and coordination mechanisms was also emphasized. The focal point indicated that this would be addressed in a special session at the upcoming mid-term review of Jamaica’s SPCR being facilitated through additional funds provided by the CIF to support the M&R process in PPCR countries.
See link at https://jamaicappcrmrscoringworkshop2018.shutterfly.com/pictures/5 for Workshop pictures
Have you shared the results of the scoring workshop to a wider in-country stakeholder group (e.g. an annual multi-stakeholder national-level steering committee and/or stock-taking meeting on the implementation of the PPCR investment plan)?
All scores assigned at the workshop and supporting information were further refined by the PPCR focal point team using published documents containing information on CCA and resilience building initiatives/actions pursued in 2017. The revised scores were then resent to the workshop participants and invitees for review and validation. Although the necessity for the hosting of the workshop earlier in the year was emphasized the focal point team was unable to host the workshop sooner due to national and international commitments which were scheduled for the first half of the year.

## Workshop Participants
PIOJ/IDB – PPCR RESULTS MONITORING AND REPORTING SCORING WORKSHOP 2018 | DAY 1 |  | DAY 2
ORGANISATION Invited | Participant | Gender |  | Gender
Climate Studies Group Mona | Delando Grant | M | Delando Grant | M
Climate Studies Group Mona | Roxann Stennett-Brown | F
Ministry of Health | Sherine Huntley-Jones | F | Sherine Huntley-Jones | F
Ministry of Health | Nicole Dawkins-Wright | F | Nicole Dawkins-Wright | F
Meteorological Service Jamaica | Kareen Gourzong | F | Kareen Gourzong | F
Meteorological Service Jamaica | Romayne Robinson | M | Romayne Robinson | M
Water Resources Authority | Michael Wilson | M | Michael Wilson | M
Water Resources Authority | Geoffrey Marshall | M | Geoffrey Marshall | M
Ministry of Economic Growth and Job Creation (Climate Change Division) | Omar Alcock | M
Ministry of Industry, Commerce, Agriculture and Fisheries | Carlton Wedderburn | M | Carlton Wedderburn | M
Ministry of Industry, Commerce, Agriculture and Fisheries | Leitha Geddes | F | Leitha Geddes | F
Ministry of Industry, Commerce, Agriculture and Fisheries (Fisheries Division) - PPCR Fisheries Project | Avery Smikle | F | Avery Smikle | F
Ministry of Industry, Commerce, Agriculture and Fisheries (Fisheries Division) | Paul Wright | M | Paul Wright | M
PPCR Jamaica _ICDIMP | Lehome Johnson | M | Lehome Johnson | M
PPCR Jamaica _ICDIMP |  |  | Christena McCarthy | F
PPCR Jamaica - APFM | Indi McClymont-Lafayette | F | Indi McClymont-Lafayette | F
PPCR Jamaica - APFM | Angella Lalor | F | Angella Lalor | F
PPCR Jamaica - APFM | Rohan Bell | M | Rohan Bell | M
JN Foundation - PPCR-Water Project | Cicyln Joseph-Johnson | F | Cicyln Jospeh-Johnson | F
JN Foundation - PPCR-Water Project | Shauna-Kaye Rowe | F | Shauna-Kaye Rowe | F
Jamaica National Small Business | Kimberly Atkinson | F | Kimberly Atkinson | F
PIOJ | Claire Bernard | F | Claire Bernard | F
PIOJ | Nadine Brown | F | Nadine Brown | F
PIOJ | Le-Anne Roper | F | Le-Anne Roper | F
PIOJ | Larytha Fletcher | F | Larytha Fletcher | F
PIOJ | Tracie-Ann West | F
Investment Plan for the Caribbean Regional Track PPCR | Ainsley Henry | M
University of the West Indies | Georgiana Gordon-Strachan | F | Georgiana Gordon-Strachan | F
Clarendon Parish Development Committee | Ingrid Parchment | F | Ingrid Parchment | F
Environmental Foundation of Jamaica | Allison Rangolan | F
| Nadisha Poyser | F | Nadisha Poyser | F
National Spatial Data Management Division | Tariq King | M | Tariq King | M
Office of Disaster Preparedness and Emergency Management | Neva South-Bourne | F | Neva South-Bourne | F
Rural Agriculture Development Agency | Vaughn Barnaby | M | Vaughn Barnaby | M
Rural Agriculture Development Agency | Winston Shaw | M | Winston Shaw | M
NEPA | Monique Curtis | F | Monique Curtis | F
World Bank | Jody-Kay Maxwell | F
Private Sector |  |  | Alicia Hayman | F
White River Marine Association |  |  | Dalelan Anderson | M
Environmental Solutions Limited
Ministry of Finance
Private Sector - Janet Bedasse
National Irrigation Commission
Ministry of Tourism
University of Technology Jamaica
Ministry of Local Government and Community Development
Inter-American Development Bank
Ministry of Economic Growth and Job Creation
Total Agencies Invited - 41 | Total Participants -Day 1 - 36 ( 13 Males, 23 Females) |  | Total Participants Day 2 - 33 ( 12 Males, 21 Females)