## Cover
PPCR Monitoring and Reporting
TAJIKISTAN |  | PPCR Investment Plan
Annual Reporting Period
From: | 2014-01-01
To: | 2014-12-31
Projects:
ID No. | XPCRTJ036A | Title | Building Capacity for Climate Resilience
| XPCRTJ037A |  | Improvement of Weather, Climate and Hydrological Service Delivery
| XPCRTJ039A |  | Environmental Land Management and Rural Livelihoods
| XPCRTJ040A |  | Building Climate Resilience in the Pyanj River Basin
| PPCRTJ038A |  | Enhancing the Climate Resilience of the Energy Sector (infrastructure)
| PPCRTJ502A |  | Enhancing the Climate Resilience of the Energy Sector (enabling environment) to be signed in 2015

## 1 Integrated
PPCR Scorecard 1 | [6 empty] | Date of Report: |  |  | 2015-06-30
PPCR Core Indicator 1: | Degree of integration of climate change into national planning
Data Collection Method: | Data scored at the country level
TAJIKISTAN | PPCR Investment Plan
Reporting Period: |  |  |  | From: | 2014-01-01 |  | To: |  |  | 2014-12-31
Complete below the sectors identified as a priority in the PPCR investment plan. Insert other priority sectors or ministries below (optional) | Is there an approved climate change plan for the nation/ sector? |  | Have climate resilience strategies been embedded in the central government's/ sector's principal planning documents? |  | Has responsibility been assigned to institutions or persons to integrate climate resilience planning? |  | Have specific measures to address climate resilience been identified and prioritized? e.g. investments and programs |  | Do all planning processes routinely screen for climate risks?
a | b |  | c |  | d |  | e |  | f
| Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Scores reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new)
National Planning | 2 | 3 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! | Work is underway to develop the National Strategy for Adaptation to Сlimate Сhange in Tajikistan, which will guide adaptation planning. This process is led by the Coordination Mechanism. In 2014, two workshops were been held on the development of the National Strategy (May 5, 2014 and November 19-20, 2014). The main climate change risks and impacts have been identified and key sector strategies are being developed. |  | The current National Welfare Improvement Strategy of the Population of the Republic of Tajikistan for(2012-2015 includes limited reference to climate change. Drafting of the new National Welfare Improvement Strategy of the Population of the Republic of Tajikistan for 2015-2020 began in 2014 and includes climate change strategies, as a result of inputs facilitated by the Coordination Mechanism. |  | There have been no changes in allocation of formal responsibilities at national level since the 2014 report . The Coordination Mechanism which is spearheading the development of the National Strategy for Adaptation, was established in 2014 and is chaired by the Deputy Prime Minister. The Head of the Department of Agriculture and Environmental Protection of the Executive Office of the President of the Republic of Tajikistan is the PPCR Focal. A recent development is that the Committee for Environmental Protection was appointed by the Government as the designated body for the Green Climate Fund. |  | Six priority investment projects of the PPCR Second Phase are in the early phases of implementation. Priority areas for the investment projects are the following: quality improvement of weather, climate and water services; capacity building for adaptation to climate Change and environmental sustainability, land Use and livelihoods in rural areas; increasing resilience to climate change in the energy Sector; and building resilience to climate change in the Panj River Basin. There are concrete plans to identify additional investment projects for priority sectors in 2015, as part of the National Strategy for Adaptation development. |  | The Government is increasingly taking into account the importance of integrating climate change issues, and has begun to identify climate risks in key sectors of the national economy: agriculture, energy, transportation infrastructure, reduction of natural disasters, and the use of water resources. In 2014, work has begun on modeling climate change, which will improve capacity to screen for climate risks in national planning processes.
Agriculture | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 2
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! | The main risks associated with climate change and their impact on the development of agriculture and basic adaptation measures are reflected in Agriculture Reform Program of the Republic of Tajikistan for the period of 2012 - 2020 (paragraphs 22, 23 and 24). The Action Plan for the implementation of the Program (paragraph 12) provides for the development of agricultural technologies adapted to climate change (for instance, drought-tolerant crops) and for carrying out research. However, the mechanism for the implementation of this Program has not been developed. |  | The National Strategy for Adaptation to Climate Change, which is currently in the process of development, includes agriculture as one of the priority sectors. Through the strategy consultation process, stakeholders have identified the main risks and impacts of climate change on agriculture, and have developed adaptation options. |  | There is no separate institution (department) with an approved budget responsible for the integration of climate resilience issues within the Ministry of Agriculture. However, in 2014, these tasks were partially taken on within the Ministry by specialists from the Department on International Relations, the Department of Science and Application of Scientific Innovation, and the Department of Crop Management. The Institute for Breeding and Seed Production of the Academy of Agricultural Sciences started research in the field of breeding crops that are adapted to climate change. |  | The World Bank and the Committee for Environmental Protection (CEP) continue to implement the Second Phase of the PPCR aimed at the Sustainable Land Management and Safe Management of the Economy in Rural Areas, amounting to 17 million US dollars. A draft of the Program of Integrated Protection of Crops, Orchards and Vineyards from Pests and Diseases in the Republic of Tajikistan for 2015-2020 was developed, which also takes into account climate change issues. |  | The Reform Program of the Agricultural Sector of the Republic of Tajikistan for the period 2012-2020 includes measures that take into account climate change risks in crop production. In 2014 the Academy of Agricultural Sciences together with the Tajik Agrarian University have integrated climate screening into the development of new types of resilient crop types.
Water Resources/Irrigation | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 3 | 2 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! | In 2014, the Amelioration and Irrigation Agency was in the process of developing the draft Strategy for Amelioration and Irrigation Development of the Republic of Tajikistan, which will explicitly consider climate change impact on water resources and adapation measures. |  | The National Strategy for Adaptation to Climate Change, which is currently in the process of development, includes water resources as one of the priority sectors. Through the strategy consultation process, stakeholders have identified the main risks and impacts of climate change on water resources and have developed adaptation options. |  | The Ministry of Energy and Water Resources and the Amelioration and Irrigation Agency do not have a designated unit with an approved budget and ToR, which is responsible for the planning of climate resilience. There are plans to assign some of these functions in 2015 to the Department of Hydropower, the Department of Water Management, and to the Amelioration and Irrigation Agency. Until then, climate resilience in the water sector is mainly covered by experts from the Institute of Water Resources. |  | Implementation has started of the PPCR Project: Building Climate Resilience in the Panj River Basin. |  | In 2014, there were several pilot studies undertaken by the Ministry of Energy and Water Resources in cooperation with the State Agency of Hydrometerology that included climate screening in determining the reserve of snow cover, glaciers and changes in water availability. However, due to lack of financial resources, such studies are irregular.
Energy | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! | The energy sector has been identified as as a priority sector for adaptation to climate change in the drafting porcess for the National Strategy for Adaptation to Climate Change. In 2014, preparations were started for the preparation of the National Strategy for the Development of the Energy Sector in 2015. This includes establishment of a technical working group that will integrate climate issues into this strategy. |  | The National Strategy for Adaptation to Climate Change, which is currently in the process of development, includes the energy sector as one of the priority sectors. Through the strategy consultation process, stakeholders have identified the main risks and impacts of climate change on the energy sector and have developed adaptation options. |  | A new Ministry of Energy and Water Resources was established in 2014. The tasks of the Ministry included some of the functions of the Ministry of Energy and Industry and the Ministry of Irrigation and Water Resources. The newly established Ministry plans to establish a special Department dealing with climate change issues, which will have its own staff, terms of references and budget financing. Currently, this function is partially performed by the department on Energy Policy. |  | In 2014, the Government of the Republic of Tajikistan and the European Bank for Reconstruction and Development (EBRD) signed an agreement on the implementation of the Second Phase of the PPCR in the energy sector. The total project cost is estimated at about 75.7 million USD |  | In 2014, there were several pilot studies undertaken by the Ministry of Energy and Water Resources in cooperation with the State Agency of Hydrometerology that included climate screening in determining the reserve of snow cover, glaciers and changes in water availability. However, due to lack of financial resources, such studies are irregular.
Disaster Risk Reduction | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! | At the end of 2014, only a small part of the National Strategy of the Republic of Tajikistan for Disaster Management for 2010-2015 was implemented due to the lack of financial resources and a clear system to monitor actions is not yet in place .The current plan does not directly address climate change adaptation, although low-regret adaptive strategies such as infrastruture improvements and early warning systmes are included. A new strategy will be developed in 2015. |  | Under the National Strategy of the Republic of Tajikistan for Disaster Management for 2010-2015, disaster risk reduction priorities have been been included in the 34 regional development plans |  | There has been general progress on improving coordination and integration of disaster risk reduction. At the end of 2014, a Government Resolution was adopted on the structure and operation of the single state system for prevention and liquidation of emergency situations. In 2014 or 2015????? - a Center for the Study of Climate Change was established within the State Agency for Hydrometeorology of Tajikistan, which cooperates with the Committee on Emergency Situations and Civil Defense on prevention of disaster risks. |  | The World Bank Project on Modernization of Hydrometeorological Services in Central Asia includes the following component: “Improving the Hydrometeorological Monitoring System to Provide Timely Warnings of Extreme Disasters and Hazardous Weather Events and to Manage Water Resources.” This component is not yet implemented. |  | No climate change risks are included in the disaster risk reduction planning process. However, there is regular monitoring of galcier and embankments to allow timely warnings for disaters.
Education | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 1 | 2
How do you Justify increase (or decrease) in scores between scores repored last year (2014) and scores repored this year 2015? Briefely describe with evidence. | Climate change issues are still embedded in environmental education, and the main government channels for information on environmental issues are the State Ecological Program and the State Program on Environmental Education. In 2014, a new State Comprehensive Program on Environmental Education of the Republic of Tajikistan was prepared for formal adoption in 2015, which will include a focus on climate change issues. |  | There has been no progress on this indicator. Issues related to adaptation to climate change are only integrated into the education system through local-level projects implemented by NGOs and international organizations.. |  | There is no special Department with an approved budget and terms of reference responsible for the planning of climate change resilience in the Ministry of Education and Science. |  | The preparation for the State Comprehensive Program on Environmental Education of the Republic of Tajikistan 2015-2020 includes planning for projects and programs to raise public awareness on climate change. In addition, in 2014 there were NGO projects that raised awareness on climate change and resilience. |  | In 2014, climate risks (floods, mudslides, heavy rains, low temperatures) have been taken into account during the construction of new schools, e.g., by location assessments, and incorporating new technology for windows, doors, and heating. Starting with the 2014-2015 school year, the regional education departments were given autonomy to change the schedule of curricula, taking into account changes in temperature, especially in winter. In 2015, the Ministry of Education and Science of the Republic of Tajikistan plans to restructure educational establishments taking into account climate risks.
Health | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 2
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! | In collaboration with the WHO Country Office in Tajikistan, the Ministry of Health completed the National Strategy and Action Plan, spanning up to 2020, concerning the adaptation of public health to climate change. The Strategy addressed the following issues: water resources and supplies, reproductive health, the climate system, infectious and cardio-vascular diseases. An action matrix and recommendations for monitoring have been developed. The Strategy has not been approved by the Government of the Republic of Tajikistan. |  | In 2014, integration of climate issues into health care occurred only in projects implemented by NGOs and International Organizations. |  | The Ministry has no special Department or an Institution with an approved budget and terms of reference specializing in the integration of climate change resilience into the overall planning. |  | In 2014, identification and implementation of priority issues occurred only in project implemented by NGOs and International Organizations. The National Strategy and the Action Plan for 2020 aims to attract additional strategic investment in the health care system with special attention paid to climate change. |  | In 2014, climate risk screening was still limited to projects implemented by NGOs and International Organization
Instructions: 1. Please establish scoring criteria for each of the aspects of this scorecard and submit them with your report. This should be done once, preferably at baseline stage and used during subsequent reporting years. 2. If you have previously established your scoring criteria, use them and submit them with your report . 3. Score each cell with a score between 0 and 10 (refer to your scoring criteria defined for this scorecard) 4. Provide explanation of change in scores between 2014 and 2015 in appropriate cells and avoid abbreviations.
Lessons learned: What have been the key successes when integrating climate change in national, including sector planning ?
1.The development of the National Strategy for Adaptation to Climate Change in Tajikistan has been started. In order to develop the National Strategy, a technical working group (20 people) has been established consisting of representatives of key ministries, research centers and NGOs. The final strategy will be submitted to the Government of the Republic of Tajikistan approval at the end of 2015.
What have been the key challenges and what opportunies for improvement do you see?
2.Despite the fact that Tajikistan has been a pilot country of the PPCR since 2009, no specialized institutions (departments) responsible for climate change, with their own approved staff, terms of references and budgets have been created at the level of the key ministries (agriculture, water resources, energy, reduction of natural disasters).
3.The development and implementation of climate change adaptation strategies for key sectors lacking financial resources. For example, the Draft of the National Strategy and the Action Plan for Public Health Adaptation to Climate Change, developed by the Ministry of Health and Social Protection, has not been approved by the Government due to the lack of financial resources.
4.It is necessary to include climate change issues in the main strategic documents of the country. One such document is the National Development Plan of the Republic of Tajikistan for 2016 - 2020, which is currently being developing. For monitoring of the activities in this area climate change indicators should be included.
Sharing experiences: please let us have some insights into the particular experience of your country with integrating climate change in nationnal, including sector planning
1. The development of the National Strategy for Adaptation has been a major catalyst in convening multi-stakeholder climate stakeholders and building awareness of gaps in existing national frameworks. It has provided sector representatives with the understanding of climate impacts and adpatation staretegies that will form the foundation for effective climate action in the coming years.

## 2 Capacity
PPCR Scorecard 2 | [6 empty] | Date of Report: |  |  | 2015-06-30
PPCR Core Indicator 2: |  |  | Evidence of strengthened government capacity and coordination mechanism to mainstream climate resilience
Data Collection Method: |  |  | Data scored at the country level
TAJIKISTAN |  |  | PPCR Investment Plan
Reporting Period: |  |  | From: |  | 2014-01-01 |  | To: |  |  | 2014-12-31
Government Capacity Complete below the sectors identified as a priority in the PPCR investment plan. Insert other priority sectors or ministries below (optional) |  |  | Are information, studies and assessments addressing climate change, variability and resilience available? |  | Is the necessary climate change expertise available? |  | Do national/sector incentives and legislative policies expressly address climate change and resilience? |  | Does the government/sector participate in the coordination mechanism?
a |  |  | b |  | c |  | d |  | e
|  |  | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new)
Tajikistan Government |  |  | 2 | 3 | 2 | 3 | 0 | 1 | 3 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! |  |  | In 2014, preparation was underway for the Third National Communication of the Republic of Tajikistan under the UN Framework Convention on Climate Change, the Country Report on Situational Analysis of the Republic of Tajikistan, prepared by the Regional Environmental Centre for Central Asia (CAREC), to be released in 2015. The 2014 National Human Development Report: “Tajikistan: Access to Resources for Human Development,” provides analysis on climate change. In addition, information about climate change is increasingly distributed through print material and various NGO websites,and by the Committee on Environmental Protection, State Agency for Hydrometeorology, and the Department of Environmental Education. |  | Climate experise in increasing. In 2014, numerous experts from various ministries, departments and scientific research centers in national and international seminars, conferences and training courses that reflected on capapcity gaps relevant to climate adaptation. In addition, training programs with improved climate change focus were introduced at three national universities – the Tajik National University, the Tajik Agrarian University and the Tajik Pedagogical University – and at the Tajik Lyceum of Communication in the 2014-2015 school year. |  | Improved analysis of the legal framework of the Republic of Tajikistan showed that climate change issues are, to some extent, addressed by the Laws “On Energy,” “On Transport,” “On Ecological Expertise,” “On Environmental Protection,” “On Environmental Education”, “On the Use of Renewable Energy,” and “On Energy Efficiency.” This provided a foundation for discussion on policy implementation to address climate change. |  | Government involvement in the Coordination Mechanism remains at a similar level as stated in the last report. The Deputy Prime Minister is the Chairman of the Coordination Mechanism. The Coordination Mechanism is composed of the representatives of key ministries, research centers and NGOs. The Head of the Department of Agriculture and Environment Protection of the Executive Office of the President of the Republic of Tajikistan is the coordinator of PPCR. Work is underway for establishing a National Agency for coordination.
Agriculture |  |  | 2 | 3 | 2 | 3 | 0 | 1 | 2 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! |  |  | 2: A key theme in the work of the Research Institutes of the Tajik Academy of Agricultural Sciences is impact of climate change on the yield of agricultural crops. The Tajik Agrarian University and the Xinjiang University prepared research papers on climate change impact on cultivation of agricultural crops. Section 4 of the Third National Communication of the Republic of Tajikistan under the UN Framework Convention on Climate Change partially addressed the issues of climate change vulnerability of in the agriculture.; 2: In 2014, several employees of the Ministry of Agriculture and the Academy of Agricultural Sciences took part in international training courses on climate change. The Tajik UNiversity introduced new educational courses by for graduate students titled "Introduction into Climate Change Studies”; 0: The development of legislative incentives to climate change is part of the implementation of the Agricultural Production Reform Program for 2020.; 2: In 2014, a representative of the Ministry of Agriculture was included in the composition of the PPCR Coordination Mechanism.
Water Resources/Irrigation |  |  | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! |  |  | 2: Section 4 of the Third National Communication of the Republic of Tajikistan under the UN Framework Convention on Climate Change addresses glaciers conditions, snow cover and climate change effects on the hydrological cycle and water resources as well as water availability scenarios. The 2014 National Human Development also addresses access to water resources. Work has begun on development of the database and information system for the water sector, including climate change and resilience. Preparatory work is underway for research on climate change impacts on water resources in the Tajik Agricultural Academy and in the Academy of Sciences of the Republic of Tajikistan.; 2: Water sector specialists are increasingly participating in advanced courses on climate change and adaptation measures. The leading universities in Tajikistan have improved their curricula are addressing climate change and water resources and are retraining of sciencist.; 0: There is still a need to strengthen implementation of policies and laws relevant to adaptation, such as the law on safety of hydraulic structures, improve current legislation (the Water Code, the Law on Water User Associations, the Law on Protection of Environment, etc.) and further develop the regulatory framework based for and adaptation measures in the water sector.; 2: The Agency for Amelioration and Irrigation functions as the coordinator of PPCR projects during the Second Phase of the “Strengthening the Resilience to Climate Change in the Panj River Basin,” project. As a result of the water reform, two government agencies were created in the water sector: the Ministry of Energy and Water Resources, and the Land Reclamation and Irrigation Agency. Representatives of these two structures are included in the Water-Energy Council of the Republic of Tajikistan and the Coordination Council on Water Policy under the IWRM. Two representatives of the water sector will also be included in the cross-sectoral Coordination Mechanism in 2015.
Energy |  |  | 1 | 2 | 2 | 3 | 0 | 2 | 2 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! |  |  | 2: Sections 2 and 4 of the Third National Communication of the Republic of Tajikistan under the UN Framework Convention on Climate Change, and the 2014 National Human Development Report address problems related to climate in the energy sector.; 2: The Scientific Research and Design Institute “Nurofar” conducts research in the energy sector. The Institute has a Department specializing on Environment and Environmental Impact Assessment, which addresses the climate change impact on the energy sector. The Institute provides technical assistance to the energy sector.; 0: Climate change issues are reflected in the “Law On the Use of Renewable Energy,” “Law On Energy Saving and Energy Efficiency," and the “Law On the Safety of Hydraulic Structures.” However,the implementation mechanisms for these Laws are not yet fully developed.; 2: The Government coordinates the two PPCR energy sector projects during the Second Phase in the energy sector, represented by the Ministry of Energy and Water. Participation has increased.
Disaster Risk Reduction |  |  | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! |  |  | 2: Section 4 of the Third National Communication of the Republic of Tajikistan under the UN Framework Convention on Climate Change specifically includes the key drivers of natural disasters. In addition, current disaster risk reduction analysis is based on climate scenarios and impacts of extreme weather conditions. The Archive in the National Hydrometeorology Service is being modernized, which has increased availability of information and facilitates the organization of climate studies.; 2: In 2014-2015, numerous employees of the Committee for Emergency Situations and Civil Defense and the State Agency for Hydrometeorology took part in international training courses. In addition, there has been specific focus on developing university courses on climate change modeling, which will support disaster risk reduction initiatives.; 0: No significant changes have been made in the legislative incentives; Current programs and laws only indirectly address the issues of climate change and resilience.; 2: Two representatives from the Disaster Risk Reduction sector participate actively in the Coordination Mechanism: a representative of the Committee on Emergency Situations and Civil Defense (Head of the Department of Population and Territory Defense) and an NGOn representative (Director of the Center on Climate Change and Disaster Risk Reduction).
Education |  |  | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 2
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! |  |  | 2: Section 7 of the Third National Communication of the Republic of Tajikistan under the UN Framework Convention on Climate Change specifically addressed issues related to the distribution of information on climate change in the educational system and public awareness raising on climate change issues and the role of NGOs and the media.; 2: More than thirty teachers from seven Tajik universities took part in a two-week training seminar conducted to roll out the teaching program "Introduction into Climate Change Studies.” In addition, training programs with improved climate change focus were introduced at three national universities – the Tajik National University, the Tajik Agrarian University and the Tajik Pedagogical University – and at the Tajik Lyceum of Communication in the 2014-2015 school year. As part of the UNDP Project on Ecological Education, the Tajik Technical University and the Institute of Postgraduate Education opened Resource Centers that develop training modules on climate change for schools and universities.; 0: There are no laws and incentives directly addressing climate change and resilience issues in the current education system. Some climate change issues are addressed under the 2010 "Law On Ecological Education.” The Ministry of Education plans to make amendments to more specifically focus on climate change.; 2: The Head of the Department of Innovation and International Relations was included in the technical working group of the Coordination Mechanism. The Coordination Mechanism also included a representative from the NGO "Iktidor" to focus on educational issues related to climate change
Health |  |  | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 2
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! |  |  | 2: The report "Assessment of Public Health Vulnerability to Climate Change in the Republic of Tajikistan” provides analysis for climate change policy development in the health care system. The issues linkages between climate change and health were described in section 4 of the Third National Communication of the Republic of Tajikistan under the UN Framework Convention on Climate Change.; 2: The Ministry of Health has multiple employees that focus on the impact of climate change on human health through training and professional assignments.; 0: Preparations are underway to develop studies on the impact of climate change and reproductive health in accordance with the order of the Ministry of Health from 16.08.2008 (№ 449).; 2: A representative of the Ministry of Health and Social Affairs (Head of the Department of Monitoring of Sanitation and Hygiene) is included in the technical working group of the PPCR Coordination Mechanism. The National Coordinating Committee (NCC) to Combat Tuberculosis and Malaria is also in the process of reviewing climate change linkages.
Coordination Mechanism Name the coordination mechanism below | Is the coordination mechanism functional e.g., established, effective and efficient? |  | 2: Does it coordinate climate resilience interventions other than those funded by PPCR?; 2: Is there a broad set of non-governmental stakeholders involved?; 0: Is the relevant climate resilience information in the public domain?; 2: Are females and males participating equally?
| Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new)
Coordination Framework for the Management of the Pilot Program for Climate Resilience in Tajikistan (commonly referred to as the Coordination Mechanism) | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 3
How do you justify the increase (or decrease) in scores between scores repored last year (2014) and scores repored this year (2015) ? Please explain! | The Coordinating Mechanism members actively participate in the development of National Strategy for Adaptation to Climate Change. The content of the National Strategy has been developed, the risks of climate change and their impacts have been identified and adaptation options for key sectors of the national economy have been elaborated with the direct participation of the Coordination Mechanism members. |  | 2: The Coordinating Mechanism was engaged mainly in the coordination of activities aimed at strengthening resilience to climate change, financed through the PPCR. The Coordination Mechanism has also been involved in stakeholder consultation for other climate change projects, mainly implemented by international organizations.; 2: 20 per cent of the Coordination Mechanism members are representatives of the NGOs. Of the total number of non-governmental organizations involved in the Coordination Mechanism, two are directly dealing with climate change issues and two are focused on gender and educational issues in relation with climate change.; 0: At present time, all the information about climate change is available on the PPCR website in Tajikistan (www.ppcr.tj). During the reporting period, the site has been significantly improved. Information on climate change is also available in the PPCR Facebook page. In addition, information about climate change is increasingly distributed through print material and various NGO websites.; 2: During the reporting period, the gender balance in the Coordination Mechanism has improved; women now make up 30 per cent of the Technical Working Group members.
Instructions: 1. Please establish scoring criteria for each of the aspects of this scorecard and submit them with your report. This should be done once, preferably at baseline stage and used during subsequent reporting years. 2. If you have previously established your scoring criteria, use them and submit them with your report . 3. Score each cell with a score between 0 and 10 (refer to your scoring criteria defined for this scorecard) 4. Provide explanation of change in scores between 2014 and 2015 in appropriate cells and avoid abbreviations.
Lessons Learned: What have been the key successes when strengthening the Government capacity and the coordination mechanism?
1. A new teaching program “Introduction into Climate Change Studies” was developed for university students at three national universities - the Tajik National University, the Tajik Agrarian University and the Tajik Pedagogical University - and for the students of the Tajik Lyceum of Communication, and it was included in the curriculum for the 2014-2015 school year.
2.The involvement of civil society and, specifically, women into climate change issues has increased. Of the total number of members of the Coordination Mechanism 20% are representatives of civil society and 30% are women. There has been a sharp increase in the number of employees of key ministries and departments, scientific research centers and civil society who took part in special training courses, as abroad as well as within the country.
What have been the key challenges and what opportunities for improvement do you see?
3.The lack of policy incentives and legislative policy related to climate change issues and resilience, both at the government level and at the level of key ministries, does not allow developing an adaptation plan to climate change at the level of key sectors.
4. In accordance with the currently developing National Strategy for Adaptation to Climate Change, it is necessary to develop a Law “On Climate Change”. It is also advisable to include the functions related to climate change issues into the sphere of competences of the Committee on Environmental Protection and, in connection with this, it is necessary to create a corresponding authoritative body.
5. The lack of specialists officially appointed to engage with climate change issues on sectoral level is the factor that does not allow the Coordination Mechanisms to work more effectivel
Sharing experiences : Please let us have some insights into the particular experience of your country with strengthening the Governement capacity and the coordination mechanism to mainstream climate resilience

## 3 Tested
PPCR Scorecard 3 | [5 empty] | Date of Report: | 2015-06-30
PPCR Core Indicator 3: |  |  |  | Quality of and extent to which climate responsive instruments/investment models are developed and tested
Data Collection Method: |  |  |  | Scored at the project-level and compiled at the PPCR Investment plan level
PPCR Investment Plan
Country Aggregate Report
Reporting Period: |  |  |  | From: | 2014-01-01 | To: | 2014-12-31
Project Title |  | Climate responsive instrument/ investment models identified: |  | Has the instrument/ investment model been developed and tested? | Has the instrument/ investment model been implemented to the scale proposed? | Has the instrument/ investment model appropriately incorporated the needs of both females and males into its design and implementation? | Has the instrument/ investment model incorporated the needs of vulnerable populations into its design and implementation?
a | # | b |  | c | d | e | f
Building Capacity for Climate Resilience | 1 | Creating a Modeling Center for Climate Change in the State Hydrometeorology Establishment |  | 3 | 4 | 3 | 3
|  | Briefly comment on each score |  | The location and necessary equipment list have been selected for the Modeling Climate Center | The Modeling Center building was reconstructed, It is now on the process of equipment purchase and software supply | The Center for Climate Change will take under consideration the need of females as well as the male ones | The Modeling Design includes all users’ needs as well as the vulnerable groups
| 2 | Developing Climate Model for Climate Change Forecasting (Dynamic disaggregation) |  | 3 | 3 | 4 | 4
|  | Briefly comment on each score |  | Conducted a round table for selecting a Climate Model, report was received from international experts for Model Selection. Suggested two Models: Global and Regional | All the Hydro meteorological data for climate change process are collected in electronic form. Local Experts are involved for training and using the climate change data. | Design takes under consideration the need of females as well as the male ones | The Modeling Design includes all users’ needs as well as the vulnerable groups
| 3 | Climate Change Impact evaluation to the economical priority sectors |  | 3 | 3 | 4 | 4
|  | Briefly comment on each score |  | Two practical seminars were held for ranking of adaptation priorities, considering the risks, impacts, adaptation potentials and investment projects. Have been ranked and developed the risks and impacts of climate change in these sectors such as water resources, energy, transport and so forth. Investment Model takes under consideration the needs of females as well as the male ones. Particular section is intended for gender aspects of climate change impacts for females The Modeling Design includes all users’ needs as well as the vulnerable groups | Have been ranked and developed the risks and impacts of climate change in these sectors such as water resources, energy, transport and so forth. | Investment Model takes under consideration the needs of females as well as the male ones. Particular section is intended for gender aspects of climate change impacts for | The Modeling Design includes all users’ needs as well as the vulnerable groups
| 4 | Development of Local Adaptation Projects through the mechanism of small subsidies, by involving the public organizations in 5 vulnerable areas |  | 3 | 3 | 3 | 3
|  | Briefly comment on each score |  | Considering the vulnerable indicators (exposure, sensitivity and adaptation potential) there were selected 5 more vulnerable areas for climate change. | In tender base there were selected 2 Scientific development and production centers for developing local adaptation projects in the base of directing small grant opportunities. There were selected more vulnerable communities in 3 pilot areas (local administrative executives). | The mechanism of small subsidies considers the needs of females as well as the male ones | The Modeling Design includes all users’ needs as well as the vulnerable groups
| 5 | Development of management system for climate change. |  | 5 | 4 | 3 | 3
|  | Briefly comment on each score |  | The website, www.ppcr.tj (PPCR) updated in three languages: Tajik, Russian and English. A Facebook page was also created under www.facebook.com/ppcr.tj | Developed the project of “human Resource management and communication on climate change matters”. “Data Management System”, “Human Resource Management System” portal was created. A particular Database section was created in order to manage the 5 PPCR projects and was also created the scenery of methodic data for climate change in Tajikistan. | The investment instrument expects that the 30% of the population whereas 50% of them are the females will be informed by 2017 about the climate change. | The Investment Model includes the needs of all vulnerable groups
| 6 | Development of a new climate program at one of the education establishment |  | 6 | 5 | 6 | 7
|  | Briefly comment on each score |  | A new training program “Introduction of Climate change in Science” was developed and tested for students. There was held 30 day training for education staff | During 2014-2015, a study program “Introduction of Climate change in Science” study programs were introduced at 3 universities and one lyceum | 30% of the participants where the study program “Introduction of Climate change in Science” was introduced, consists female students. | 35% of the students are taken from the vulnerable areas of the population.
Improvement of Weather, Climate and Hydrological Service Delivery | 1 | NHMS staff qualification is increased, taking into account technological changes in NHMS’s performance and operations. |  | 3 | 3 | 1 | 1
|  | Briefly comment on each score |  | Programme to raise the level NHS staff developed a list of participants and conducted several trainings | Programme to raise the level NHS staff developed a list of participants and conducted several trainings | The design takes into consideration needs of men and women, 42% are women specialist NHMS | The design takes into consideration needs of vulnerable groups
| 2 | Updated regulatory and methodical base is developed taking into account of institutional and technological changes in the NHMS’s performance and operations. |  | 2 | 2 | 1 | 1
|  | Briefly comment on each score |  | The model is under development | in the implementation phase | The design takes into consideration needs of men and women | The design takes into consideration needs of vulnerable groups
| 3 | Meteorological instruments are installed for more accurate weather forecasts |  | 2 | 2 | 1 | 1
|  | Briefly comment on each score |  | The model is under development | in the implementation phase | The design takes into consideration needs of men and women | The design takes into consideration needs of vulnerable groups
| 4 | Stream gauges are repaired and telemetry installed for more reliable seasonal river flow forecasts |  | 2 | 2 | 1 | 1
|  | Briefly comment on each score |  | The model is under development | in the implementation phase | The design takes into consideration needs of men and women | The design takes into consideration needs of vulnerable groups
| 5 | The information transmission to the global telecommunications system is improved |  | 2 | 2 | 1 | 1
|  | Briefly comment on each score |  | The model is under development | in the implementation phase | The design takes into consideration needs of men and women | The design takes into consideration needs of vulnerable groups
| 6 | Technical conditions for improved assessment of climate changes, including rapid access to information archives and more expedient hydrometeorological service delivery are provide |  | 2 | 2 | 1 | 1
|  | Briefly comment on each score |  | The model is under development | in the implementation phase | The design takes into consideration needs of men and women | The design takes into consideration needs of vulnerable groups
| 7 | Early warning system is improved. Emercom capacity to disseminate NHMS’s information on severe weather conditions to the regional and local branches of the committee is enhanced. |  | 2 | 2 | 1 | 1
|  | Briefly comment on each score |  | The model is under development | in the implementation phase | The design takes into consideration needs of men and women | The design takes into consideration needs of vulnerable groups
| 8 | Expanded access of the external and internal users to the observation data and information products, including climate information is provided |  | 2 | 2 | 1 | 1
|  | Briefly comment on each score |  | The model is under development | in the implementation phase | The design takes into consideration needs of men and women | The design takes into consideration needs of vulnerable groups
Environmental Land Management and Rural Livelihoods | 1 | Farm Production |  | 2 | 1 | 1 | 2
|  | Briefly comment on each score |  | The first draft of the small grant proposals by the communities proposed and it's under the discussion | Proposed and not implemented yet | One of the main indicator of the project is the persentage of the women involved | The proposals will be designed on behalf of the needs of rural communities
| 2 | Land Resource Management |  | 2 | 1 | 1 | 2
|  | Briefly comment on each score |  | The first draft of the small grant proposals by the communities proposed and it's under the discussion | Proposed and not implemented yet | One of the main indicator of the project is the persentage of the women involved | The proposals will be designed on behalf of the needs of rural communities
| 3 | Rural Production Infrastructure |  | 2 | 1 | 1 | 2
|  | Briefly comment on each score |  | The first draft of the small grant proposals by the communities proposed and it's under the discussion | Proposed and not implemented yet | One of the main indicator of the project is the persentage of the women involved | The proposals will be designed on behalf of the needs of rural communities
| 4 | Sustainable Community Pasture Management |  | 3 | 3 | 3 | 2
|  | Briefly comment on each score |  | The three community PLMPs already prepared and and been supported | Implementation of PLMPs started and 35% has already been achieved | The PLMPs strictly given to account involvment of women | Participatory approach has been used during the plans designing process where the needs of vulnerable groups of rural people was considered
| 5 | On-farm Water Management |  | 3 | 3 | 3 | 2
|  | Briefly comment on each score |  | The three community PLMPs already prepared and and been supported | Implementation of PLMPs started and 35% has already been achieved | The PLMPs strictly given to account involvment of women | Participatory approach has been used during the plans designing process where the needs of vulnerable groups of rural people was considered
| 6 | Trainings, Analysis, Dissemination and Metworking |  | 3 | 2 | 3 | 1
|  | Briefly comment on each score |  | The process of implementation started | Selected three ICs and been conducted 4 TOTs and 1 reseach work | Involvment of women is coming everywhere especially in the trainings process | Participatory approach has been used during the trainings also, where the needs of vulnerable groups of rural people was considered
Building Climate Resilience in the Pyanj River Basin | 1 | Upgrade and climate-proof flood and mud-flow protection infrastructure in ten locations including river bank reinforcement, embankment reconstruction, restoration of stream beds, terracing and planting of trees, and soil stabilization |  | 1 | 1 | 2 | 2
|  | Briefly comment on each score |  | instrument/ investment models were partially examined during the first phase of the PPCR in 2011 | The preparatory work on realization of investment model is being conducted | The instrument includes that up to 20% of opportunities of employment in the coordinated spheres are completed by women | Model design includes the needs of vulnerable groups of the population in its development.
| 2 | Establish operation & maintenance (O&M) practices, develop O&M guidelines and train local units of the responsible agencies |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially development models of the management (on operation manual and technical service) were examined during assessment of the first Phase of PPCR in 2011 | Management has not been developed and implemented | Not less than 30% of the local residents trained in operation and servicing of infrastructure, belonging to the project are presented by women. | Development of the management takes into account the needs of more vulnerable groups of the population (50% of the population is considered to be more vulnerable groups of population)
| 3 | Develop early warning communication systems through the use of modern technologies including mobile phones |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially models of development of the communication alert systems were considered during the first Phase of PPCR | Communication alert systems have not been developed and implemented | The communication system provides that 30% of participants are women | The model design considers the needs of the most vulnerable groups of the population
| 4 | Establish DRMCs in target communities |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially models of the organization of committees of risk management of natural disasters were defined at a basic assessment (1 phase of PPCR) | Committees of risk management aren't organized | In 3 months after the organization of committees on risk management, not less than 30% of members and officials of committees have to be women (basic research of 2012: (0%)) | The model design considers the needs of the most vulnerable groups of the population
| 5 | Conduct training and disseminate information on the impact of climate change and adaptation measures for local government officials and local institutions |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Some models of conducting training and distribution of information were tested in a basic assessment of 1 Phase of PPCR | Right now not at a realization stage | The design of the project provides that not less than 50% of participants of all trainings on climate risks and adaptation, systems of early notification are women. | The model design considers the needs of the most vulnerable groups of the population
| 6 | Rehabilitate and climate-proof irrigation canals and network assets, including reconstruction and desilting of drainage and delivery channels and rehabilitation of pumping stations |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially the design of model was considered on the first Phase of PPCR | Right now not at a realization stage | The instrument includes that up to 20% of opportunities of employment in the coordinated spheres are completed by women | The model design considers the needs of the most vulnerable groups of the population
| 7 | Pilot a drip irrigation scheme |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially the design of model was considered on the first Phase of PPCR | Right now not at a realization stage | Implementation of the project considers needs of women and men | Realization of the project considers the needs of the most vulnerable groups of the population
| 8 | Strengthen WUAs |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially the design of model was considered on the first Phase of PPCR | Right now not at a realization stage | The design of the project considers that not less than 30% of members and officials of groups of water users are women (basic research of 2012 :) | Realization of the project considers the needs of the most vulnerable groups of the population
| 9 | Provide advice and disseminate information on water resources management and climate-resilient agricultural practices to farmers, local government officials, women’s groups, and other stakeholders |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially the design of model was considered on the first Phase of PPCR | Right now not at a realization stage | The design of the project provides that not less than 50% of participants on water resources management are women. | Realization of the project considers the needs of the most vulnerable groups of the population
| 10 | Rehabilitate and climate-proof seven rural drinking water supply systems, including rehabilitation, upgrade, and construction of boreholes, provision of new and rehabilitated pumping equipment, and construction of new service reservoirs and water tanks |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially the design of model was considered in the first Phase of PPCR | Realization of the instrument hasn’t begun | The instrument includes that up to 20% of opportunities of employment in the coordinated spheres are completed by women | Realization of the project considers the needs of the most vulnerable groups of the population
| 11 | Establish O&M practices for drinking water supply systems, develop O&M guidelines, and train local units of the responsible agencies |  | 1 | 0 | 2 | 2
|  | Briefly comment on each score |  | Partially the design of model was considered in the first Phase of PPCR | Realization of the instrument hasn’t begun | Implementation of the project provides that not less than 30% of the local residents trained in operation and servicing of infrastructure, belonging to the project are presented by women. | Realization of the project considers the needs of the most vulnerable groups of the population
| 12 | . Establish WCGs to influence responsible agencies and ensure performance of the water supply facilities |  | 1 | 0- | 2 | 2
|  | Briefly comment on each score |  | Partially models of the organization of committees of drinking water consumers were defined during the basic assessment | Realization of the instrument hasn’t begun | The design of the project provides that not less than 30% of members and officials of groups of water users are women (basic research of 2012: (0%)). | Realization of the project considers the needs of the most vulnerable groups of the population
| 13 | Raise awareness of health and other risks associated with climate change |  | 0 | 0 | 2 | 2
|  | Briefly comment on each score |  | The instrument of the model hasn't been developed | Realization hasn’t begun | The design of the project provides that not less than 50% of participants on increasing awareness on risks to health and other risks connected with climate change are women. | Realization of the project considers the needs of the most vulnerable groups of the population
| 14 | Expand capacity of participating financial institutions (PFIs) to accept micro and small deposits, and provide microloans in support of climate-resilient economic activities in the Pyanj River Basin |  | 1 | 1 | 2 | 2
|  | Briefly comment on each score |  | The instrument of the model is partially considered | The instrument of the model is considered on a selective basis | The project provides that 100% of credit employees of all FID (financial institutions’ departments) are trained in work with needs of female clients prior to delivery of microloans and other design products. | Realization of the project considers the needs of the most vulnerable groups of the population
| 15 | Provide credit lines for agricultural improvements (Climate-Resilient Agriculture Credit Line) and economic diversification (Income Diversification Credit Line) targeting particularly women |  | 1 | 1 | 2 | 2
|  | Briefly comment on each score |  | The instrument of the model is partially considered | Instruments are at a consideration stage | The design of the project provides that not less than 30% of all subcredits are given to competent subborrowers who either are women, or represent the enterprises where not less than 50% belong to women. For the first quarter of 2015, 20 credits were issued from which 12% are female subborrowers. The objectives for 1 quarter aren't achieved | Realization of the project considers the needs of the most vulnerable groups of the population
| 16 | Strengthen financial literacy of the local population |  | 0 | 0 | 2 | 2
|  | Briefly comment on each score |  | Instrument model hasn’t been tested | Realization of the instrument hasn’t begun | Implementation of the project provides that not less than 50% of the trained in financial literacy are women trained within 3 months after the beginning of loans issuance | Realization of the project considers the needs of the most vulnerable groups of the population
| 17 | Assess the feasibility of collateral insurance linked to credit and, if appropriate, pilot a credit insurance scheme |  | 0 | 0 | 2 | 2
|  | Briefly comment on each score |  | Instrument model hasn’t been tested | Realization of the instrument hasn’t begun | Implementation of the project considers the interests of men and women (50%) | Realization of the project considers the needs of the most vulnerable groups of the population
Enhancing the Climate Resilience of the Energy Sector (infrastructure) | 1 | Integration of climate change resilience features into Kairakkum hydropower plant rehabilitation |  | developed, but not tested as the project implementation has not been finalised | yes | yes | yes
|  | Briefly comment on each score |  | The project used a highly innovative approach by incorporating climate change considerations into the investment design. Experts recruited for the project modelled future hydrology – in other words, the water infl ow into Qairokkum’s reservoir – under different climate change scenarios. This served as a basis for selecting the most suitable rehabilitation design across the range of possible projected climate change scenarios. In addition a dedicated technical assistance package will assist Barki Tojik as it mainstreams climate change into the operational management of hydropower assets. | The approach has been used to develop a full-scale project wth a total investment value of USD 75 million, which exceeds the amount of USD 68.6 million that was anticipated at the time of PPCR Subcommittee approval. | A gender assessment was undertaken as part of the Environmental and Social Analysis performed during project development, and the recommendations were included into the project and into its Stakeholder Engagement Plan. | An Environmental and Social Impact Analysis (including a Stakeholder Engagement Plan) was undertaken and recommendations were incorporated into the project design
| 2 | Replicable model for planning, developing and implementing climate resilient upgrades of hydropower facilities developed and tested |  | yes | yes | n/a | n/a
|  | Briefly comment on each score |  | The investment approach developed for this project has been developed so that it can be transferred and replicated in other river basins and other countries that are exposed to climate change risks. | EBRD is now considering using this investment approach in hydropower operations in other countries, such as Georgia and Morocco. | EBRD's Strategic Gender Initiative requires all projects to take gender considerations into account, so this will be done on a case-by-case basis, tailored to the needs of the specific investment in question. | EBRD's Environmental and Social Policy requires all projects to take account of the needs of vulnerable populations who may be affected by a project, so this will be done on a case-by-case basis, tailored to the needs of the specific investment in question.
| 3 | Adoption of best practices as used by hydropower operators in OECD countries by Barki Tojik and other relevant Tajik institutions |  | Procurement in progress | yes | Yes | Yes
|  | Briefly comment on each score |  | The hydropower operator will receive support in updating the plant’s dam operating rules in line with international best practice in order to maximise energy production, minimise spills and optimise dam safety. This will be done on the basis of the newly available hydrological and meteorological data. | Yes, the full allocation of USD 1 million is being used for this purpose. | The technical cooperation (TC) support associated with this activity includes a programme of household and business surveys that will identify gender differences. These will allow intra-household gender analysis of energy use and vulnerability as well as differentiated analysis of energy use by male- and female-led businesses. | The technical cooperation (TC) support associated with this activity includes a programme of household and business surveys that will address the needs of the most vulnerable sections of the population.
Enhancing the Climate Resilience of the Energy Sector (enabling environment) to be signed in 2015 | 1
Briefly comment on each score
2
Briefly comment on each score
3
Briefly comment on each score
4
Briefly comment on each score
5
Briefly comment on each score
Instructions: 1. List all climate responsive instruments/ investment models identified in each of your project before starting (refer to projects documents) 2. Establish scoring criteria for each of the aspects of this scorecard and submit them with your report. This should be done once, preferably at baseline stage and used during subsequent reporting years. 3. If you have previously established your scoring criteria, use them and submit them with your report. 4. Score each cell with a score between 0 and 10 ( refer to your scoring criteria defined for this scorecard). 5. Add more lines under each project if needed.
Lessons Learned: What have been the key successes when developing and testing these instruments/investment models?
1. Investment models and tools were partially developed for most PPCR projects and tested during first Phase. Some success in development and test of investment models was achieved during last two years of TA8090: Building Capacity for Climate Resilience project implementation in Tajikistan. Other PPCR projects are in initial stage and investment models are not fully developed and tested.
What have been the key challenges and what opportunities for improvement do you see?
2. It should be noted that in administrative guidelines of ADB project ‘Building Climate Resilience in the Pyanj River Basin Project’ and EBRD project ‘Enhancing Climate Resilience of Energy Sector Project’ contribution in a framework of PPCR monitoring and evaluation program is clearly described. In administrative guidelines of other PPCR projects, definition of investment models are not yet fully clerar and the monitoring and evaluation framwork needs strengthening
3. The needs of male and female beneficiaries in the investment models is not fully clear in the 'Enhancing Climate Resilience of Energy Sector' Project (EBRD) and the 'Improvement of Weather, Climate and Hydrological Service Delivery' Project (WB)

## 4 Used
PPCR Table 4 | [11 empty] | Date of Report: | mm/dd/yy
PPCR Core Indicator 4: |  |  | Extent to which vulnerable households, communities, businesses and public sector services use improved PPCR supported tools, instruments, strategies, activities to respond to Climate Variability and Climate Change
Data Collection Method: |  |  | Data collected for each project and compiled at the PPCR investment plan level
PPCR Investment Plan
Country Aggregate Report
Reporting Period: |  |  | From: |  | 2014-01-01 |  |  | To: | 2014-12-31
Only complete for the categories targeted by the tool, instrument, strategy, or activity
Project Title | Identify the improved PPCR supported tool, instrument, strategy, activity below. |  |  | Number of Households |  | Write up to three sentences describing how households use this? | Number of Communities |  | Write up to three sentences describing how communities use this? | Number of Businesses |  | Write up to three sentences describing how businesses use this? | Number of Public Sector Service Entities |  | Write up to three sentences describing how public sector service entities use this?
| These are the same as those identified in Scorecard 3 |  |  | Actual results (Cumulative since project started) | Expected Results |  | Actual results (Cumulative since project started) | Expected Results |  | Actual results (Cumulative since project started) | Expected Results |  | Actual results (Cumulative since project started) | Expected Results
a | # | b |  | c | d | e | f | g | h | i | j | k | l | m | n
Building Capacity for Climate Resilience | 1 | Creating a Modeling Center for Climate Change in the State Hydrometeorology Establishment |  | l: 0; m: 7; n: Climate Modeling Center will be located at State Establishment of Hydrometeorology. The increased quality information about the risks of climate change will also be utilized by other ministries such as the ministry of Energy and water resources, irrigation ad melioration agency, ministry of agriculture, environmental care committee, ministry of transport and so on
| 2 | Developing Climate Model for Climate Change Forecasting (Dynamic disaggregation) |  | l: 0; m: 7; n: Climate data about the risks of climate change will also be utilized by other ministries such as the ministry of Energy and water resources, irrigation ad melioration agency, ministry of agriculture, environmental care committee, ministry of transport, ministry of health, committee of women affairs and so on.
| 3 | Climate Change Impact evaluation to the economical priority sectors |  | l: 3; m: 7; n: This model allows to develop steady investment projects as well as includes the climate change risk control. The governmental offices will be able to update the leadership on planning, engineering leadership, avoiding expenses and so on. The National Strategy Allows to rank the adaptation priorities and involve additional investment.
| 4 | Development of Local Adaptation Projects through the mechanism of small subsidies, by involving the public organizations in 5 vulnerable areas |  | f: 0; g: 20; h: The communities will be able to utilize the results of vulnerable research on climate change, develop the adaptation measures, by the organized training centers; l: 0; m: 5; n: The local executive authorities may utilize the fund of small grants to support the activities which identifies the main vulnerability of climate change and priority adaptation measures in cooperation with public organizations.
| 5 | Development of management system for climate chang |  |  | Not identified | Females and other social groups will have much more access on different adaptation measures and support in such changes | 0 | 20 | Communities may utilize adopted knowledge in order deal with problems occurred on climate change. |  |  |  | 3 | 5 | Creating Saving System and Human Resource management on the impacts of climate change in the key sectors including water resources, agriculture, energy, transport and social development allow to improve the knowledge on climate change risks.
| 6 | Development of a new climate program at one of the education establishment |  | l: 3; m: 1; n: Introducing the trainings on “Introduction of Climate change in Science ” including academic modules for climatology and hydrometeorology which influence the students’ knowledge and will facilitate preparing the specialists.
Improvement of Weather, Climate and Hydrological Service Delivery | 1 | NHMS staff qualification is increased, taking into account technological changes in NHMS’s performance and operations. |  | l: 1; m: 1; n: This activity will engage staff in developing an overall concept for the Service. Tajik Hydromet is developing a marketing program to enhance capacity to provide fee-based services.
| 2 | Updated regulatory and methodical base is developed taking into account of institutional and technological changes in the NHMS’s performance and operations. |  | l: 1; m: 1; n: This activity will improve Hydromet's capacity to foster cooperation among its services on how information is received, integrated, and exchanged in the region
| 3 | Meteorological instruments are installed for more accurate weather forecasts |  | i: 0; j: 80000; k: Farms use improved weather forecasts to to grow a good crop
| 4 | Stream gauges are repaired and telemetry installed for more reliable seasonal river flow forecasts |  | l: 0; m: 2; n: The energy sector, water management organizations use the improved seasonal forecasts for water resources management and hydropower generatio
| 5 | The information transmission to the global telecommunications system is improved. |  | l: 0; m: 1; n: The Republic of Tajikistan successfully fulfills its international obligations
| 6 | Technical conditions for improved assessment of climate changes, including rapid access to information archives and more expedient hydrometeorological service delivery are provided. |  | l: 0; m: 1; n: Rapid access to archive information allows to conduct the study of climate change
| 7 | Early warning system is improved. Emercom capacity to disseminate NHMS’s information on severe weather conditions to the regional and local branches of the committee is enhanced. |  | i: 0; j: 80000; k: Approximately 80% of Tajikistan's territory covered by the early warning system. Thus, about 80% of farms will have advance information about severe weather conditions
| 8 | Expanded access of the external and internal users to the observation data and information products, including climate information is provided. |  | l: 0; m: 7; n: Expanded access of the external and internal users to the observation data and information products, including climate information allows to make better management decisions in various sectors of the economy and agriculture of the republic
Environmental Land Management and Rural Livelihoods | 1 | Farm Production |  | 0 | 42000 | Will be provide small-scale grants at the village level for groups of households to implement rural production. The grant will not exceed US$7,000 and require a match of 25% in beneficiary contributions which may be in cash-or in-kind | 0 | 389 | Following a participatory rural appraisal covering environmental, social and economic issues and prepared with the assistance of facilitating organizations (FOs) , villages prepare a “community action plan. CIGs will be formed and supported with the small grant to implement CAPs that needs include; field and horticultural crop productivity and diversification, livestock production efficiency, agro-processing and market access... | 0 | 677 | Project started to creat CIGs at community level. Project supports CIGs with the small grants under three main categories of activities that are expected to contribute to their assets and sustainable land management, and increase climate resilience, examples of which are listed below | 4 | 6 | Raion Review Committee (RRC) will be established at district level. The RRC consisting members from the representatives of the raion administration (1 person), raion-level line agencies (Water Resources and Land Reclamation/Agriculture, Women and Family Affairs – 2 persons), non-government (1 person) and RCEP (1 person). There will be five members in total. The RRC will be able to analise and give recomendation on rural productivity subproject proposals in all three categories that meet project financing, eligibility and feasibility criteria (including those for individual households as permitted under the farm productivity category).
| 2 | Land Resource Management |  | c: 0; d: 42000; e: Will be provide small-scale grants at the village level for groups of households to implement rural production. The grant will not exceed US$7,000 and require a match of 25% in beneficiary contributions which may be in cash-or in-kind.; f: 0; g: 389; h: Pasture management, water management, soil fertility, integrated pest management, and sustainable sloping lands cultivation (including orchards, woodlots, joint forest management, shelter-belts)
| 3 | Rural Production Infrastructure |  | c: 0; d: 42000; e: Will be provide small-scale grants at the village level for groups of households to implement rural production. The grant will not exceed US$7,000 and require a match of 25% in beneficiary contributions which may be in cash-or in-kind.; f: 0; g: 389; h: Irrigation/drainage system rehabilitation, minor transport infrastructure, renewable energy, and energy efficiency measures. Project-financed grants to CIGs for each subproject under categories
| 4 | Sustainable Community Pasture Management |  |  | 2100 | Mainly this activity will introduce sustainable community-managed pasture/fodder-based livestock production systems in villages. Pasture User Groups would be formed consisting of all pasture users. Anticipated membership is between 50 and 200 households in each village depending on size and between 6 and 10 villages per jamoat. | 4 | 8 | The activities implementing in the eight selected jamoats, primarily in hill and upland areas. The selected jamoats would be within the districts selected by the government. | 4 | 8 | Pasture User Unions are being created under this activity and through these unions’ pastures and livestock management plans are being developed |  |  | Local government agronomists (pasture specialists), livestock specialists and environment officers would support the PUGs and NGOs in the preparation and implementation of the participatory Pasture and Livestock Management Plans. The land surveyor in each jamoat under the State Land Committee would have responsibility of supporting the PUGs in the designation of pasture areas under their responsibility and supporting the process of obtaining land certificates if needed to the extent possible.
| 5 | On-farm Water Management |  | 5760 | 15570 | The main aim is to introduce sustainable on-farm water management practices in irrigated croplaThis sub-component aims to introduce sustainable on-farm water management practices in irrigated cropland primarily in lowland districts. The beneficiaries would be existing Water User Associations (WUAs) and WUA members in the --- districts selected by the government. At least 80% of the WUA managed area would have to be under family farms to help ensure sustainability of investments. Anticipated membership is an average of around 400 households in each WUA depending on size. | 3 | 8 | Activity implementing in lowland districts in eight selected jamoats. According to these practices, existing Water User Associations (WUAs) are introducing activities following advanced experience and methods that can contribute to improving on-farm water management, maintaining soil fertility and reducing lands degradation | 3 | 8 | Existing Water User Associations in the selected project districts will be responsible for preparation and implementation of the participatory Water Management Plans. Each WUA would open a Bank account for the transfer of funds, and would maintain accounts, records of their expenditures, and achievement of targets. | 9 | 15 | Local government agronomists and environment officers would support the WUAs and NGOs in the preparation and implementation of the participatory Water Management Plans. The land surveyor under the State Land Committee would have responsibility of supporting the members of WUAs in the process of obtaining land certificates if needed to the extent possible, including those renting land. The District Water Departments have responsibilities in the delivery of water to the WUAs and would support the WUAs in the identification of on-farm water management and drainage improvement opportunities when possible. In addition to local government specialists, other extension providers where available, primarily those formed through other donor and NGO programs, would be asked to support the WUAs and participate in the planning process.
| 6 | Trainings, Analysis, Dissemination and Metworking |  |  |  | The trained people provide gained knowledge to the communities and the results is metioned above | 8 | 16 | The PUUs(psture unit uions) and WUA' s bodies(4 form each) have been participated in the TOTs and trained PUGs (pasture users groups) at village level and other WUA members as they participated in the TOTs and have needed knowledge and it's metioned above | 80 | 80 | Local consultant contracted and supported the locally-based facilitating organizations (NGOs) and the Implementation Group (IG) in the Committee for Environmental Protection (CEP) in the development of the Water Management Plans, including advising on the format of the Plan, assessments of soil and water quality, and monitoring. The consultant will also provide training for the NGOs and WUAs in the design and development of the Water Management Plans, and in the implementation of the grants A local Cosultatnt contracted to evaluate the performance of the WUAs and facilitating NGO, and assess the impact of the grant in improving on-farm water management and livelihoods of the water users. The study would also provide lessons learned and recommendations for future work in the topic. The consultant will also provide training for the NGOs and WUAs in the design and development of the Water Management Plans, and in the implementation of the grants An international consultant contracted to support the locally-based facilitating organizations (NGOs) and the Implementation Group (IG) in the Committee for Environmental Protection (CEP) in the development of the Pasture and Livestock Management Plans, including advising on the format of the Plan, assessments of pasture and feed/fodder balances, and monitoring. The consultant will also provide training for the NGOs and PUGs in the development and implementation of the Pasture and Livestock Management Plans, and in the implementation of the grants | 20 | 20 | The Rayon administration consisting one reprezentative from each sector of the hukumat also involved in the process of TOT trainings; Agriculture department Women and family Affairs department Rayon COEP Water Farm Deparment Land Management Specialist
Building Climate Resilience in the Pyanj River Basin | 1 | Upgrade and climate-proof flood and mud-flow protection infrastructure in ten locations including river bank reinforcement, embankment reconstruction, restoration of stream beds, terracing and planting of trees, and soil stabilization |  | c: 0; d: 2532; e: Provides protection of houses and plants against risk of natural disasters and increases the level of the income of women and other persons of the most vulnerable households of the agriculture sector; f: 0; g: 17; h: To provide protection of social infrastructure of communities (schools, medical institutions, mosques, roads), irrigational constructions, rural grounds. Not less than 231 hectares of the irrigated lands are protected from annual floods to 2019. Not less than 1490 hectares irrigated are protected from floods
| 2 | Establish operation & maintenance (O&M) practices, develop O&M guidelines and train local units of the responsible agencies |  | f: 0; g: 17; h: Will help communities to avoid the consequences of climatic changes through the use of such local actions, as "hashar" (groups of self-support)
| 3 | Develop early warning communication systems through the use of modern technologies including mobile phones |  | f: 0; g: 17; h: Will allow communities (mahalla) to take timely and necessary measures for decreasing the risks of natural disasters
| 4 | Establish DRMCs in target communities |  | f: 0; g: 17; h: Instructions and the manuals will be developed so that different groups and committees could continue effective functioning and to provide long-term effective adaptation to climate changes.
| 5 | Conduct training and disseminate information on the impact of climate change and adaptation measures for local government officials and local institutions |  | f: 0; g: 17; h: Will help communities to avoid climate change consequences with usage of such local actions as "hashar" (groups of self-help), women's committees and communities
| 6 | Rehabilitate and climate-proof irrigation canals and network assets, including reconstruction and desilting of drainage and delivery channels and rehabilitation of pumping stations |  | c: 0; d: 6729; e: To improve access of households to irrigated water, to increase profitability taking climate change into account; f: 0; g: 26; h: 1450 hectares of the arable lands served by 5 irrigational channels and networks protected from climatic factors (basic data of 2012 =0)
| 7 | Pilot a drip irrigation scheme |  | c: 0; e: In view of lack of irrigational water in target areas of garden agriculture, Dehkan households can use information from this demonstration activity for support of the corresponding irrigation of the lands. The number of beneficiaries isn't defined yet; it will be made during realization.; f: 0; g: 2; h: In view of lack of irrigational water in target areas of garden agriculture, Dehkan households can use information from this demonstration activity for support of the corresponding irrigation of the lands. The number of beneficiaries isn't defined yet; it will be made during realization.
| 8 | Strengthen WUAs |  | f: 0; g: 8; h: Instructions and manuals will be developed so that members of various groups and committees can carry out their functions out more effectively and to provide long-term efficiency of adaptation to climate changes.; i: 0; j: 200; k: Farmers will use it for realization of practices, steady against climate changes. Creation of AVP will create a condition to farmers for steady access to the irrigated water taking into account climate change.
| 9 | Provide advice and disseminate information on water resources management and climate-resilient agricultural practices to farmers, local government officials, women’s groups, and other stakeholders |  | f: 0; g: 8; h: To increase the level of knowledge of the community on water resources management and climate-resilient agriculture among representatives of local authorities, women's groups and other interested parties; i: 0; j: 200; k: To increase the level of knowledge of the community on water resources management and climate-resilient agriculture among farmers
| 10 | Rehabilitate and climate-proof seven rural drinking water supply systems, including rehabilitation, upgrade, and construction of boreholes, provision of new and rehabilitated pumping equipment, and construction of new service reservoirs and water tanks |  | c: 0; d: 4150; e: It will improve access of households to clear drinking water, will reduce quantity of the diseases connected with bad quality of water and will reduce costs of households on; f: 0; g: 23; h: It will improve access of community to clear drinking water, will reduce quantity of the diseases connected with bad quality of water and will reduce costs of households on
| 11 | Establish O&M practices for drinking water supply systems, develop O&M guidelines, and train local units of the responsible agencies |  | c: 0; d: 45; e: Households can use it for water use improvement; f: 0; g: 23; h: Will help communities to avoid consequences of climatic changes through use of such local actions, as "hashar" (groups of self-support)
| 12 | Establish WCGs to influence responsible agencies and ensure performance of the water supply facilities |  | f: 0; g: 7; h: Instructions and manuals will be developed so that members of various groups and committees can carry out the functions more effectively and to provide long-term efficiency of adaptation to climate changes.
| 13 | Raise awareness of health and other risks associated with climate change |  | f: 0; g: 7; h: The communities which were trained on risks of health care will use more practices of stability connected with climate change that will lower the incidence rate, connected with drinking water
| 14 | Expand capacity of participating financial institutions (PFIs) to accept micro and small deposits, and provide microloans in support of climate-resilient economic activities in the Pyanj River Basin |  | i: 0; j: 10; k: Micro financial institutions can train and keep the employees who have the skills of microcredit applied to the projects aimed at adaptation to climate changes
| 15 | Provide credit lines for agricultural improvements (Climate-Resilient Agriculture Credit Line) and economic diversification (Income Diversification Credit Line) targeting particularly women |  | c: 11; d: 160; e: It will increase access to productive assets of resistance to climate changes for the participating households that provides the improved risk management, connected with climate change. These credits will be utilized for financing of purchase of assets and accessories at lower prices
| 16 | Strengthen financial literacy of the local population |  | c: 0; d: 160; e: To increase financial literacy of heads of households and first of all women in access to credit lines connected with climate change and purchases of assets
| 17 | Assess the feasibility of collateral insurance linked to credit and, if appropriate, pilot a credit insurance scheme |  | c: 0; d: 160; e: Use of insurance of the credits which include an assessment of a climate risk
Enhancing the Climate Resilience of the Energy Sector (infrastructure) | 1 | Kairakkum hydropower plant power generation to be resilient to climatic variation and extreme climate events |  | c: 0; d: 92105; e: Households in Sugd province will benefit from a more reliable and climate-resilient electricity supply as a result of this project.; l: 0; m: 1; n: Households in Sugd province will benefit from a more reliable and climate-resilient electricity supply as a result of this project.
| 2 | Replicable model for planning, developing and implementing climate resilient upgrades of hydropower facilities developed and tested |  | l: 0; m: 3; n: The investment approach developed for this project has been developed so that it can be transferred and replicated in other river basins and other countries that are exposed to climate change risks.
| 3 | Adoption of best practices as used by hydropower operators in OECD countries by Barki Tojik and other relevant Tajik institutions |  | l: 0; m: 7; n: The hydropower operator will receive support in updating the plant’s dam operating rules in line with international best practice in order to maximise energy production, minimise spills and optimise dam safety. This will be done on the basis of the newly available hydrological and meteorological data.
Enhancing the Climate Resilience of the Energy Sector (enabling environment) to be signed in 2015 | 1
2
3
4
5
Instructions: 1. List the same climate responsive instrument/ investment models /tools etc. as those identified in scorecard 3 2. Clearly identify the target population of your instruments / investment models/tools etc. : Is it Households? Communities? Businesses (private sector), public service entities or a combination thereof (refer to the project documents). 3. Actual results: cumulatively report results achieved since the project started implementation. Expected Results: Results expected to be achieved at completion of the project as stated in the project document. 4. Always provide written comments on how the target population identified in this table will use the instruments/investment models/tools to respond to climate change. 5. Add more lines under each project if needed.
Lessons Learned:
What have been the key successes when households/communities/public services/businesses use the improved tool, instrument, investment strategy,activity.
1. Almost all PPCR projects are in initial stage of implementation. Currently they are under process of partners selection, awareness-raising and explanatory activities among beneficiaries.
What have been the key challenges and what opportunities for improvement do you see?
2. The main issue in projects implementation process is that most projects were launched later, which negatively affected to implementation dates scheduled during first PPCR Phase.
3. The PPCR project need to strengthen the definition of investment projects, and monitoring and PPCR evaluation experts need to be trained in an early initial stage so they can organize necessary project information independently.

## 5 Supported
PPCR Table 5 | [5 empty] | Date of Report: | 2015-06-30
| PPCR Core Indicator 5: | Number of people supported by the PPCR to cope with the effects of climate change
| Data Collection Method: | Data collected for each project and compiled at the PPCR Investment Plan level
Tajikistan
Country Aggregate Report
| Reporting Period | From: | 2014-01-01 | To: | 2014-12-31
Direct beneficiaries
[6 empty] | Actual results (Cumulative since project started) | Expected Results
Project Title | [5 empty] | b | c
Building Capacity for Climate Resilience | Number of people supported by the PPCR to cope with the effects of climate change |  |  |  |  | 1000 | 522270
| Number of people below the national poverty line supported by the PPCR to cope with the effects of climate change |  |  |  |  | 250 | 235020
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 500 | 261350
Improvement of Weather, Climate and Hydrological Service Delivery | Number of people supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 2000
| Number of people below the national poverty line supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 1000
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 820
Environmental Land Management and Rural Livelihoods | Number of people supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 126000
| Number of people below the national poverty line supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 63000
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 100.8 | 50400
Building Climate Resilience in the Pyanj River Basin | Number of people supported by the PPCR to cope with the effects of climate change |  |  |  |  | 80 | 89393
| Number of people below the national poverty line supported by the PPCR to cope with the effects of climate change |  |  |  |  | 40 | 50961
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 30 | 37876
Enhancing the Climate Resilience of the Energy Sector (infrastructure) | Number of people supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 460525
| Number of people below the national poverty line supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 230262
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 230262
Enhancing the Climate Resilience of the Energy Sector (enabling environment) to be signed in 2015 | Number of people supported by the PPCR to cope with the effects of climate change
Number of people below the national poverty line supported by the PPCR to cope with the effects of climate change
Females supported by the PPCR to cope with the effects of climate change
Tajikistan ( aggregation of six projects) | Total number of people supported by the PPCR to cope with the effects of climate change in the country |  |  |  |  | 1080 | 1200188
| Total number of people below the national poverty line supported by the PPCR to cope with the effects of climate change in the country |  |  |  |  | 290 | 580243
| Total number of females supported by the PPCR to cope with the effects of climate change in the country |  |  |  |  | 630.8 | 580708
Instructions: 1. Actual results: cumulatively report the number of people supported by the project since it started implementation. 2. Expected Results: number of people expected to be reached by the project at completion as stated in the project document. 3. If the target population of the project is households or communities, provide best estimates of the number of people in these households or communities. Triangulate this data with data provided in Table 4 for consistency. 4.Please do not leave blank cells. Put Zero (0) in the corresponding cell if people are not supported yet by the project.
Lessons Learned:
What have been the key successes when people have been supported by the PPCR?
1. All PPCR projects are in initial stage of implementation; the support and benefits from the investment models/instruments have not yet come to fruition
+
What have been the key challenges and what opportunities for improvement do you see?
2. The results frameworks and target number of beneficiaries for the PPCR projects need to be strengthened. It is also recommended to include determination of indirect beneficiaries
3. It is also recommended to include determination of indirect beneficiaries
+

## Scoring Workshop Summary
Summary of the scoring workshop
Who were the different stakeholder groups invited to the scoring workshop (composition and number)? Please attach the list of participants.
The scoring workshop participants included representatives from government ministries and committees (17), national civil society organizations (10), international organizations (10) and the Phase 2 PPCR projects (17).
How did you define your scoring criteria for Scorcards 1 and 2 (national level) and scorecard 3 (project level)? Please attach scoring criteria for scorcards 1, 2, and 3
The scorecards were reviewed and updated during a separate event that included members from the Coordination Mechanism Technical Working Group, organized in Dushanbe on 12 March 2015. The updated scorecards were used for the actual scoring workshop on 13 May 2015.
Please provide a brief summary of the workshop (What were the key issues raised during the workshop? )
The workshop was a one-day event organized on 13 May 2015. Prior to the workshop, draft scoring sheets were prepared by the PPCR projects for indicators 3 and 4; and individual and small-group consultations were organized with climate stakeholders to develop draft scoring sheets for indicators 1 and 2, and to collect supporting evidence. During the workshop on 13 May, participants reviewed and revised the scores for indicators 1 and 2 in small groups, and presented the results of the group work in plenary to the meeting participants for final validation. The scores for indicators 3 and 4 were reviewed and revised in plenary for each PPCR project.
Have you shared the results of the scoring workshop to a wider in-country stakeholder group (e.g. an annual multi-stakeholder national-level steering committee and/or stock-taking meeting on the implementation of the PPCR investment plan)?
The participants in the 13 May scoring workshop included a wide range of senior officials, who shared the results within their own institutions. The validated scoring results were shared with the PPCR focal point prior to submission to CIF.