## Cover
PPCR Monitoring and Reporting
Zambia |  | PPCR Investment Plan
Annual Reporting Period
From: | 2014-01-01
To: | 2014-12-31
Projects:
ID No. | XPCRZM041A | Title | Strengthening Climate Resilience in Zambia and the Barotse Sub-Basin
| XPCRZM042A |  | Strengthening Climate Resilience in the Kafue Sub-Basin

## 1 Integrated
PPCR Scorecard 1 | [6 empty] | Date of Report: |  |  | 2015-06-15
PPCR Core Indicator 1: | Degree of integration of climate change into national planning
Data Collection Method: | Data scored at the country level
Zambia | PPCR Investment Plan
Reporting Period: |  |  |  | From: | 2014-01-01 |  | To: |  |  | 2014-12-31
Complete below the sectors identified as a priority in the PPCR investment plan. Insert other priority sectors or ministries below(optional) | Is there an approved climate change plan for the nation/ sector? |  | Have climate resilience strategies been embedded in the central government's/ sector's principal planning documents? |  | Has responsibility been assigned to institutions or persons to integrate climate resilience planning? |  | Have specific measures to address climate resilience been identified and prioritized? e.g. investments and programs |  | Do all planning processes routinely screen for climate risks?
a | b |  | c |  | d |  | e |  | f
| Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Scores reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new)
National Planning | 5 | 5 | 6 | 7 | 6 | 6 | 6 | 6 | 2 | 3
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! | The National Climate Response Strategy (NCCRS) is still in draft form, awaiting the approval of the Climate Change policy although a number of its recommendations are being implemented. |  | The Revised Sixed National Development Plans (RSNDP) had climate change mainstreamed. The Climate Change policy has been circulated for comments and is awaiting cabinet approval. A Climate proofing manual has been developed to assist in mainstreaming efforts |  | The Interim Inter-Ministerial Climate Change Secretariat (ICCS) has been established. Permanent institutional arrangements awaiting approval of the climate change policy |  | Specific measures (investments and programs) to address climate resilience have been identified and approved, but application has not been consistent throughout government |  | Screening for climate risks done to some extent, sometimes based on a particular project's guidelines. However, ICCS has planned for consultancy to develop screening guidelines for priority sectors
Environment and Natural Resources |  |  | 6 | 6 | 7 | 7 | 5 | 6 | 2 | 3
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | Climate Change has been embedded in the sectorial strategic plan, National Bio diversity Strategy action Plan (NBSAP), though National Policy on Environment has very limited information on Climate Change. The draft of the REDD+ strategy on deforestation was done. |  | Responsibility has been assigned to focal persons supported by approved budgets |  | Some programs and investments in place e.g. under Zambia Environmental Management Agency (ZEMA): the Lundazi Solar project, Solwezi Solid waste management project |  | Screening for climate risks has recently started
Agriculture (Livestock, Fisheries and Crops) |  |  | 7 | 8 | 7 | 6 | 6 | 7 | 5 | 5
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | The National Agriculture Policy of 2004 has climate change embedded; Government promoted irrigation in Revised 6th National Development Plan (RSNDP), which can also be seen as deliberate measure to address Climate Change; the National Agriculture Investment Plan (NAIP) also addresses Climate Change. |  | Officers have been appointed as focal point persons and been assigned to ensure climate resilience planning, however, yet to be supported by budgets and job descriptions hence the decrease from last year's score |  | Some programs and investments in place however not to scale, e.g. the Climate Change Adaptation Project was only piloted in 8 districts, and the PPCR participatory adaptation is being piloted in 25 districts. There are 103 districts in Zambia. The sector is also implementing a smart agriculture project with support from FAO. |  | There has been some pilot screening for Climate Change risks in a selection of projects, but screening is not mandatory across the sector
Health |  |  | 6 | 7 | 6 | 7 | 6 | 6 | 5 | 5
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | Climate Change embedded in the National Health policy (2013); National Health Adaptation plan to climate change (regional plan to which Zambia is party) done in 2013 and approved in 2014; Epidemic preparedness response (EPR) plans which take into account CC. |  | Officers have been appointed as focal point persons and been assigned to ensure climate resilience planning, supported by budgets |  | Some programs and investments in place, e.g. Unintended Persistent Organic Pollutants (UPOP) projects (GEF/UNDP), Zambia Health Services Improvement project (WB), Environmental Safeguards in Malaria control. |  | There has been some pilot screening for Climate Change risks in a selection of projects, but screening is not mandatory across the sector
Transport and Infrastructure |  |  | 0 | 8 | 0 | 6 | 3 | 5 | 0 | 7
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | The Sectorial Strategic Plan (2014-2016) for the Ministry of Transport, Works, Supply and Communication developed and has climate change considerations embedded in it. |  | Officers have been appointed as focal point persons and been assigned to ensure climate resilience planning, however, yet to be supported by budgets and job descriptions |  | Some programs and investments in place including PPCR investments (PPCR Component: Climate resilient infrastructure and NDF Developing Climate Resilient Infrastructure Standards and Codes Project). Also Green Jobs/ Buildings being done by National Council for Construction (NCC) in partnership with International Labour Organisation (ILO). |  | Screening mandated in the sector but not consistently done. Infrastructure planning & design usually accounts for worst case scenario (including extreme events).
Energy |  |  | 4 | 6 | 0 | 4 | 3 | 5 | 0 | 3
How do you Justify increase (or decrease) in scores between scores reported last year (2014) and scores reported this year 2015? Briefly describe with evidence. |  |  | Energy policy 2008 and the Rural Electrification Master plan (2008) has CR strategies embedded in them which are being used in the planning process |  | A focal point person assigned |  | Specific measures (investment & programs) to address climate resilience have been identified and approved and implementation has just began, e.g. Renewable energy program, Flood control program under ZESCO, Rural Electrification Agency implementing some of the work agreed under the NAMAs i.e. rural electrification. |  | The authorities have recently started to screen for climate risks
Tourism |  |  | 3 | 4 | 0 | 1 | 0 | 2 | 0 | 1
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | Sectorial Strategic Plan does not have climate change considerations however the tourism policy is currently being reviewed. Some institutions in sector have activities in their implementation plan to address the impacts of climate change, though climate change not expressly mentioned e.g. Zambia Wildlife Authority (ZAWA) |  | Plans are in place to assign a focal point person |  | Work has recently commenced on the identification of measures to address climate change |  | Plans are in place to develop climate risk screening guidelines |  | `
Water |  |  |  | 5 |  | 3 |  | 6 |  | 5
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | Strategy for Flood Management for Kafue Sub-Basin (2007) addresses Climate Change. Water Resource Management Act (2011) some provision for climate change which could be strengthened. National water policy (2010) is under review, and has climate change considerations in it |  | No specific focal point person that has been assigned, however institutions like National Water and Sanitation Council have persons assigned within their institutions to address any issues on climate change |  | Specific measures (investments and programs) to address climate resilience have been identified and approved, e.g. from the NAMAs, a Water and Waste management project is to be developed; there is also the Zambia Water Resource Development project funded by the World Bank at a total cost of US$50 million for dam and well construction as well as the establishment of irrigation Schemes and flood warning systems. |  | There has been some pilot screening for Climate Change risks in a selection of projects, but screening is not mandatory across the sector
Instructions: 1. Please establish scoring criteria for each of the aspects of this scorecard and submit them with your report. This should be done once, preferably at baseline stage and used during subsequent reporting years. 2. If you have previously established your scoring criteria, use them and submit them with your report . 3. Score each cell with a score between 0 and 10 (refer to your scoring criteria defined for this scorecard) 4. Provide explanation of change in scores between 2014 and 2015 in appropriate cells and avoid abbreviations.
Lessons learned: What have been the key successes when integrating climate change in national, including sector planning ?
1. Several sectors indicated having strategies to address climate change impacts though they may not be expressly mentioned in planning documents
2. Most sectors now have specific programs promoting climate resilience e.g. Green Jobs /Buildings being done by National Council for Construction (NCC) in partnership with International Labour Organisation (ILO) (infrastructure), the Climate change adaptation project in agriculture; the Water Resource Management project in the Kafue catchment area; and the Lundazi Solar project in the environmental sector
3. Most Sectors have a focal point person/s or are in the process of identifying someone responsible for coordinating mainstreaming Climate change issues
What have been the key challenges and what opportunities for improvement do you see?
3. The National Climate Response Strategy (NCCRS) is still in draft form and awaiting the approval of the Climate Change policy although a number of its recommendations are being implemented
4. The Climate Change policy has been developed and circulated for comments, however, it is still awaiting cabinet approval
5. There is room for more stakeholder engagement and awareness raising/ sensitization on the Zambia climate change programme especially among the youth and academia
Sharing experiences: please let us have some insights into the particular experience of your country with integrating climate change in national, including sector planning
The process of integration of climate change in National and Sector planning has progressed steadily though consideration still needs to continue being given to the effectiveness of the mainstreaming process and sectors moving beyond having the climate change strategies in the planning documentation to actual implementation. There is still scope to improve in understanding of what really constitutes integrating climate change within a particular sector. There is increasing interest by donors to support Zambia's mainstreaming process at both the sectoral and district levels. Various tools such as the climate proofing manuals and investments in capacity strengthening in Strategic Environmental Assessment (SEA) are also being pursued. An Inclusive Green Growth Strategy is also being developed to strengthen the mainstreaming process in Zambia. Also, it is important to note that in the previous reporting period, the water sector was not included as a priority sector. However, it was realized that there are a lot of climate change initiatives currently being undertaken within that sector which need to be captured. It is for this reason that the sector has been included.

## 2 Capacity
PPCR Scorecard 2 | [6 empty] | Date of Report: |  |  | 2015-06-15
PPCR Core Indicator 2: |  |  | Evidence of strengthened government capacity and coordination mechanism to mainstream climate resilience
Data Collection Method: |  |  | Data scored at the country level
Zambia |  |  | PPCR Investment Plan
Reporting Period: |  |  | From: |  | 2014-01-01 |  | To: |  |  | 2014-12-31
Government Capacity Complete below the sectors identified as a priority in the PPCR investment plan. Insert other priority sectors or ministries below (optional) |  |  | Are information, studies and assessments addressing climate change, variability and resilience available? |  | Is the necessary climate change expertise available? |  | Do national/sector incentives and legislative policies expressly address climate change and resilience? |  | Does the government/sector participate in the coordination mechanism?
a |  |  | b |  | c |  | d |  | e
|  |  | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new)
Zambia Government |  |  | 6 | 6 | 5 | 5 | 2 | 3 | 7 | 7
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | Number of studies and assessments undertaken but access as well as consolidation of information needs to be improved |  | Few highly qualified experts available across the sectors |  | Few incentives and legislative policies are available within some sectors but indirectly related to Climate Change and Climate Resilience |  | Interim Government driven coordination mechanism in place.
Environment and Natural Resources |  |  | 7 | 4 | 6 | 4 | 0 | 1 | 8 | 5
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | A lot of studies and assessments have been done but accessibility of information is a challenge. The score decreased from 7-4 because last year only one person from the sector scored whereas this year the sector was represented by 6 people, which is more representative. |  | There are few persons who are trained in climate change resilience and are qualified in climate change resilience. The score decreased from 6-4 because last year only one person from the sector scored whereas this year the sector was represented by 6 people, which is more representative |  | Some legislative policies are available in the environmental sector but indirectly related to Climate Change and Climate Resilience |  | There is a decrease from last year's score because stakeholders felt that participation of the sector in the Interim Climate Change Secretariat (ICCS) needs to be enhanced. There was need for improved information sharing by ICCS.
Agriculture (Livestock, Fisheries and Crops) |  |  | 6 | 5 | 6 | 4 | 2 | 2 | 8 | 4
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | Limited periodic studies being done to update information in the sector, and if done are donor funded; however, accessibility of information is a challenge hence the decrease from last year's score |  | There are few persons who are trained in climate change resilience and are qualified in climate change resilience. The score decreased from 6-4 because last year only one person from the sector scored whereas this year the sector was represented by 6 people, which is more representative |  | Some incentives are available but indirectly related to Climate Change and Climate Resilience e.g. agriculture equipment having zero rating (tax rebate), Farmers input support programme (FISP), providing seeds according to agro-ecological regions e.g. flood areas - rice, drought areas - drought resistant seedlings |  | There is a decrease from last year's score because stakeholders felt that participation of the sector in the Interim Climate Change Secretariat (ICCS) needs to be enhanced. There was need for improved information sharing by ICCS.
Health |  |  | 5 | 7 | 5 | 5 | 0 | 2 | 4 | 5
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | Some vulnerability assessments have been done by Disaster Management & Mitigation Unit (DMMU); Other studies include linkage between climate change and disease occurrence; The sector has a website (District Health Information System (DHIS2)) on which information from districts is posted. Because health information is sensitive accessibility of information is on request/demand |  | There are few persons who are trained in climate change resilience and are qualified in climate change resilience. |  | Some incentives are available but indirectly related to Climate Change and Climate Resilience e.g. free spraying of mosquitos and free Insectide Treated Nets (ITN) for expecting mothers to address malaria (Climate sensitive disease); Government programme to replace fridges (CFCs) |  | Improved participation by sector as they have been involved in a number of climate change meetings and forums.
Transport and Infrastructure |  |  | 1 | 2 | 2 | 2 | 0 | 0 | 5 | 4
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | A few of the required information, studies or assessments have been done but accessibility is a challenge |  | Some Government / sector officials have attended climate change training courses. |  | No incentives nor legislative policies in place |  | There is a decrease from last year's score because stakeholders felt that participation of the sector in the Interim Climate Change Secretariat (ICCS) needs to be enhanced. There was need for greater coordination of the sector's climate change activities by ICCS.
Energy |  |  | 4 | 6 | 4 | 4 | 2 | 4 | 5 | 3
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | A lot of research work has been done in the energy sector, e.g. ' the effects of climate change on hydro-energy'; however information may not be readily accessible. |  | There are few persons who are trained in climate change resilience and are qualified in climate change resilience |  | Some incentives and legislative policies are in place but indirectly address climate change e.g. no tax on importation of solar panels, 'Feed-in tariffs' for alternative energy providers (various sources of energy feeding into the main national grid). |  | There is a decrease from last year's score because stakeholders felt that participation of the sector in the Interim Climate Change Secretariat (ICCS) needs to be enhanced. There was need for greater coordination of the sector's climate change activities by ICCS.
Tourism |  |  | 1 | 1 | 2 | 2 | 0 | 1 | 2 | 2
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | A few of the required information, studies or assessments have been done but accessibility is a challenge |  | Very few people knowledgeable and this is from attending workshops and not training courses |  | Some incentives are available but indirectly related to Climate Change and Climate Resilience e.g. People in Game Management Areas (GMAs) provided with alternative livelihoods to discourage deforestation. |  | Stakeholders felt that the sector was not fully engaged and had limited participation in the coordination mechanism.
Water |  |  |  | 2 |  | 2 |  | 3 |  | 5
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! |  |  | Some studies have been done under JICA and a lot on the Kafue but accessibility is a challenge |  | Some Government / sector officials have attended climate change training courses. |  | Some incentives and legislative policies are in place but indirectly address climate change e.g. increase in tariffs for utilities with low non-revenue water levels (reducing water losses and promoting water conservation). |  | Sector participating in coordination mechanism however, participation could be enhanced
Coordination Mechanism Name the coordination mechanism below | Is the coordination mechanism functional e.g., established, effective and efficient? |  | Does it coordinate climate resilience interventions other than those funded by PPCR? |  | Is there a broad set of non-governmental stakeholders involved? |  | Is the relevant climate resilience information in the public domain? |  | Are females and males participating equally?
| Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new) | Score reported last year (2014) | Score in 2015 (new)
National Climate Change Development Council | 4 | 5 | 4 | 5 | 5 | 6 | 4 | 4 | 5 | 5
How do you justify the increase (or decrease) in scores between scores reported last year (2014) and scores reported this year (2015) ? Please explain! | Interim Climate Change Secretariat is fulfilling the mandate until the National Climate Change Development Council is formed |  | Growing portfolio of climate change initiatives (Green Climate Fund, SREP, Bio Carbon, GRZ-UN Joint Programme, Green Growth Strategy) |  | Active stakeholder engagement in various activities and also stakeholders grouped into platforms according to areas of specialization (Climate information, Climate Finance, Climate resilient agriculture and Climate resilient infrastructure). |  | Limited relevant climate resilience information in the public domain |  | Interim Climate Change Secretariat has equal participation of males and females
Instructions: 1. Please establish scoring criteria for each of the aspects of this scorecard and submit them with your report. This should be done once, preferably at baseline stage and used during subsequent reporting years. 2. If you have previously established your scoring criteria, use them and submit them with your report . 3. Score each cell with a score between 0 and 10 (refer to your scoring criteria defined for this scorecard) 4. Provide explanation of change in scores between 2014 and 2015 in appropriate cells and avoid abbreviations.
Lessons Learned: What have been the key successes when strengthening the Government capacity and the coordination mechanism?
1. The Interim Inter-Ministerial Climate Change Secretariat (ICCS) has been established to coordinate climate change initiatives within the country. Permanent institutional arrangements are still awaiting approval of the climate change policy which has been developed
2. Awareness on climate change and climate change initiatives being undertaken within the sectors has increased. Various stakeholders expressed a desire to acquire more knowledge and access to information.
What have been the key challenges and what opportunities for improvement do you see?
3. There is still room for enhanced participation of sectors and improvement in the coordination of climate change activities by the Interim Inter-Ministerial Climate Change Secretariat.
4.Though several studies, assessments have been done, there is need for improvement on accessibility to information. This could be done by providing a website or portal where this information can be accessed. The ICCS is in the process of developing a website which will help serve this need.
5. Capacity building and training programmes in climate change should be sector-tailored in order to meet the needs of various stakeholders with the sectors.
Sharing experiences : Please let us have some insights into the particular experience of your country with strengthening the Government capacity and the coordination mechanism to mainstream climate resilience
An Interim Inter-Ministerial Climate Change Secretariat has been established under the Ministry of Finance, with staff from various sectorial Ministries, to coordinate all climate change activities across sectors in Zambia. The ICCS was placed within that Ministry because the Ministry of Finance is responsible for the mobilization, planning and distribution of Government and external resources, and therefore is in a strategic position to promote climate change mainstreaming. Additionally, as a Ministry responsible for national planning and budgeting, it also has convening power over other participating Ministries. Thus, the placement of the coordination mechanism within the Ministry of Finance has ensured high level coordination.

## 3 Tested
PPCR Scorecard 3 | [5 empty] | Date of Report: | 2015-06-15
PPCR Core Indicator 3: |  |  |  | Quality of and extent to which climate responsive instruments/investment models are developed and tested
Data Collection Method: |  |  |  | Scored at the project-level and compiled at the PPCR Investment plan level
PPCR Investment Plan
Country Aggregate Report
Reporting Period: |  |  |  | From: | 2014-01-01 | To: | 2014-12-31
Project Title |  | Climate responsive instrument/ investment models identified: |  | Has the instrument/ investment model been developed and tested? | Has the instrument/ investment model been implemented to the scale proposed? | Has the instrument/ investment model appropriately incorporated the needs of both females and males into its design and implementation? | Has the instrument/ investment model incorporated the needs of vulnerable populations into its design and implementation?
a | # | b |  | c | d | e | f
Strengthening Climate Resilience in Zambia and the Barotse Sub-Basin | 1a | Climate Resilient sub-grants (Community Level) |  | 6 | 4 | 10 | 7
|  | Briefly comment on each score |  | The instrument/ investment model has been developed and starting to be tested. | 31 sub- projects out of the targeted 1150 were being implemented | The sub-grants are gender responsive in design and implementation based on environmental and social safeguards guidelines | The climate risk assessment was not yet finalized
| 1b | Climate Resilient sub-grants (Ward Level) |  | 6 | 4 | 10 | 5
|  | Briefly comment on each score |  | The instrument/ investment model has been developed and starting to be tested. However, the requirement to have a ward development plan has been an impending factor making the investment implementation slow. | 3 Ward sub-projects out of targeted 72 were under implementation | The sub-grants are gender responsive in design and implementation based on environmental and social safeguards guidelines | Most ward projects had not been implemented
| 1c | Climate Resilient sub-grants (District Level) |  | 1 | 0 | 0 | 0
|  | Briefly comment on each score |  | Plans are in place to develop the model, however the requirement of the use Integrated Development Plans (IDPs) and District Strategic Plans (DSP) has slowed the process | No district sub-projects had been done | Not yet commenced implementation | Not yet commenced implementation
| 2 | Climate Risk Assessment |  | 8 | 4 | 10 | 7
|  | Briefly comment on each score |  | Climate Risk assessments done to identify the 34 sub-projects, however a consultant was recruited to refine process and build capacity of District teams. | Only 7 districts out of the 14 were targeted | Both male and females are incorporated in the design and implementation | Only 7 districts out of the 14 were targeted
| 3 | Climate Risk Maps |  | 8 | 4 | 10 | 7
|  | Briefly comment on each score |  | This is normally part of the risk assessment process. Climate Risk assessments done to identify the 34 sub-projects, however a consultant was recruited to refine process and build capacity of District teams. | Only 7 districts out of the 14 were targeted | Both male and females are incorporated in the design and implementation | Only 7 districts out of the 14 were targeted
| 4 | Integrated Development Plans |  | 1 | 0 | 0 | 0
|  | Briefly comment on each score |  | The score was reduced from last year’s 2 to 1 because it was noted that it was not only existence of the IDP but also it had to be mainstreamed | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation
| 5 | Contingency Adaptation Fund |  | 0 | 0 | 0 | 0
|  | Briefly comment on each score |  | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation
| 6 | Rehabilitation of Canals to operate near optimum level |  | 5 | 0 | 7 | 5
|  | Briefly comment on each score |  | The seven major canals had been identified and feasibility studies and detailed designs completed | Not yet commenced implementation | Incorporates needs of both sexes in its design through a detailed ESMP, however implementation has not yet began | Incorporates most of the vulnerable groups in its design
Strengthening Climate Resilience in the Kafue Sub-Basin | 1 | Climate Training Sessions |  | 5 | 2 | 8 | 6
|  | Briefly comment on each score |  | Some trainings were delivered during the launch of the project and also at the Planning meeting for the 2015 Annual Work Plan and Budget, held with district officials in Dec. 2014 | Implementation just commenced at district level. However, the required number of training sessions (12 by EOP both at District, Ward & Community level) not yet done | Trainings are gender responsive in design | Implementation is just taking off and scoring is based on the design aspect
| 2 | Micro Projects |  | 0 | 0 | 0 | 0
|  | Briefly comment on each score |  | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation
| 3 | Technological Packages (farm level system support) |  | 0 | 0 | 0 | 0
|  | Briefly comment on each score |  | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation
| 4 | Medium- large scale investment projects |  | 0 | 0 | 0 | 0
|  | Briefly comment on each score |  | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation
| 5 | Climate Resilient Road |  | 2 | 0 | 0 | 0
|  | Briefly comment on each score |  | The detailed design for the road and bidding documents for the consultancy for supervision and works for the roads have been completed | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation
| 6 | Integrated Development Plans |  | 0 | 0 | 0 | 0
|  | Briefly comment on each score |  | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation | Not yet commenced implementation
Instructions: 1. List all climate responsive instruments/ investment models identified in each of your project before starting (refer to projects documents) 2. Establish scoring criteria for each of the aspects of this scorecard and submit them with your report. This should be done once, preferably at baseline stage and used during subsequent reporting years. 3. If you have previously established your scoring criteria, use them and submit them with your report. 4. Score each cell with a score between 0 and 10 ( refer to your scoring criteria defined for this scorecard). 5. Add more lines under each project if needed.
Lessons Learned: What have been the key successes when developing and testing these instruments/investment models?
1. The Pilot Programme for Climate Resilience (PPCR) funded 18 Projects (1 Ward & 17 Community Infrastructure Projects) in the first phase of the Barotse project in Limulunga, Mongu, Nalolo & Senanga districts. Major activities have involved rehabilitation of canals to drain fields for agriculture purposes. By December 31, 16 more sub-projects had been approved for implementation.
2. By December 31 2014, 10 NGOs (Climate Risk Adaptation Facilitators) to cover all 14 Districts in Barotse Sub-Basin had been engaged and oriented on PPCR activities and their role in facilitating climate risk planning and district & Ward development plans and facilitation of community sub projects
3. Following the project launch in Kafue Sub-Basin on 13th March 2014, recruitment, selection, placement and orientation of staff in the Project Implementation Unit (PIU) took place between April 2014 and August 2014.
4. Following the recruitment of the Kafue Sub-Basin PIU staff, activities have taken place aimed at preparing the districts for project implementation. These included orientation through workshops on project implementation and procedures, meetings with Provincial Planning Units (for all three provinces: Central, Lusaka and Southern Province), including meetings with District Commissioners, District Planners, Town Clerks and Councils Secretaries from 5 out the 11 target districts.
What have been the key challenges and what opportunities for improvement do you see?
5. Capacity building of district teams should be a continuous process and it is vital that various stakeholders (i.e. Districts, CRAFS, Provincial Teams and PIU) clearly understand their roles and responsibilities for effective project management
6. Lack of District Integrated Development Plans (IDP) in most districts has delayed the disbursement of the District Grants, as none of the Districts has accessed the funds. The PPCR proposes to embark on supporting the District Planning Process through piloting in Mongu, Mwandi and Senanga Districts which have draft IDPs in place.
7. In the Kafue Sub-Basin Project, most instruments/ investment models have been not yet been developed and tested as implementation of activities in the districts is just commencing.

## 4 Used
PPCR Table 4 | [11 empty] | Date of Report: | 2015-06-15
PPCR Core Indicator 4: |  |  | Extent to which vulnerable households, communities, businesses and public sector services use improved PPCR supported tools, instruments, strategies, activities to respond to Climate Variability and Climate Change
Data Collection Method: |  |  | Data collected for each project and compiled at the PPCR investment plan level
PPCR Investment Plan
Country Aggregate Report
Reporting Period: |  |  | From: |  | 2014-01-01 |  |  | To: | 2014-12-31
Only complete for the categories targeted by the tool, instrument, strategy, or activity
Project Title | Identify the improved PPCR supported tool, instrument, strategy, activity below. |  |  | Number of Households |  | Write up to three sentences describing how households use this? | Number of Communities |  | Write up to three sentences describing how communities use this? | Number of Businesses |  | Write up to three sentences describing how businesses use this? | Number of Public Sector Service Entities |  | Write up to three sentences describing how public sector service entities use this?
| These are the same as those identified in Scorecard 3 |  |  | Actual results (Cumulative since project started) | Expected Results |  | Actual results (Cumulative since project started) | Expected Results |  | Actual results (Cumulative since project started) | Expected Results |  | Actual results (Cumulative since project started) | Expected Results
a | # | b |  | c | d | e | f | g | h | i | j | k | l | m | n
Strengthening Climate Resilience in Zambia and the Barotse Sub-Basin | 1a | Climate Resilient sub-grants (Community Level) |  | c: 2514; d: 25800; e: 1. Diversify to climate resilient livelihoods, crops or infrastructure; 2. Soft Adaptation (community to undertake locally appropriate innovations); 3. 78 individual champions (30% for women) to benefit
| 1b | Climate Resilient sub-grants (Ward Level) |  | f: 3 wards; g: 24 wards; h: 1. Diversify to climate resilient livelihoods, crops or infrastructure; 2. Communities use improved tools, information and instruments to respond to climate change and variability 3. Promote the uptake of locally-appropriate innovations
| 1c | Climate Resilient sub-grants (District Level) |  | l: 0; m: 14 District Councils; n: 1. Use improved tools, information and instruments to respond to climate change and variability; 2. Building resilience to climate risks into local planning (particularly as these plans are expected to drive local budgets) 3. Through risk-based planning and mapping, local governments and communities can visualize options for future expansion of their settlements and infrastructure
| 2 | Climate Risk Assessment |  | l: 7 Districts; m: 14 District Councils; n: 1. To incorporate climate risk assessment into provincial level planning; 2. Develop knowledge products in area of climate change and risk management to share with communities; 3. Build capacity required for mainstreaming climate adaptation and risk management.
| 3 | Climate Risk Maps |  | l: 7 districts; m: 14 District Councils; n: 1. To incorporate climate risk assessment into provincial level planning; 2. Develop knowledge products in area of climate change and risk management to share with communities; 3. Build capacity required for mainstreaming climate adaptation and risk management.
| 4 | Integrated Development Plans |  | f: 0; g: 18 wards; h: 1. To account for risks associated with climate change impacts such as event of droughts, floods, and extreme heat and frost events; 2. Utilize opportunities in the opportunities through identifying projects for interventions; 3. Use as basis for allocating resources in annual budget; l: 0; m: 6 pilot district councils; n: 1. To account for risks associated with climate change impacts such as event of droughts, floods, and extreme heat and frost events; 2. Utilize opportunities in the opportunities through identifying projects for interventions; 3. Use as basis for allocating resources in annual budget
| 5 | Contingency Adaptation Fund |  | c: 0; d: 25800; e: 1. To fund additional sub-projects upon early warning of a disaster; 2.
| 6 | Rehabilitation of Canals to operate near optimum level |  | c: 0; d: 8340; e: 1. Used for Navigation (transport); 2. Used for drainage of agricultural land; 3. Used as a source of food (fishing)
Strengthening Climate Resilience in the Kafue Sub-Basin | 1 | Climate Training Sessions |  | l: 0; m: 15 training sessions; n: -To incorporate climate risk assessment into provincial level planning; -Develop knowledge products in area of climate change and risk management to share with communities; - Build capacity required for mainstreaming climate adaptation and risk management.
| 2 | Micro Projects |  | f: 0; g: 27 wards; h: -Flood control and diversion structures; - Small-scale irrigation schemes; -Community forest plantations and wildlife estates
| 3 | Technological Packages (farm level system support) |  | f: 0; g: 27 wards; h: - Conservation agricultural training; -Livestock and fisheries for diversification farming systems; -Providing inputs such as seeds for drought and flood resistant crop varieties for crop diversification
| 4 | Medium- large scale investment projects |  | i: 0; j: 200; k: - Livestock production; - Out grower schemes (crops & livestock); - Fisheries
| 5 | Climate Resilient Road |  | f: 0; g: 27 wards; h: -Use as strategic farm - to - market access roads; -Link to Kafue National Park; -
| 6 | Integrated Development Plans |  | f: 0; g: 11 Districts (27 wards); h: -To account for risks associated with climate change impacts such as event of droughts, floods, and extreme heat and frost events; - Utilize opportunities in the opportunities through identifying projects for interventions; - Use as basis for allocating resources in annual budget
Instructions: 1. List the same climate responsive instrument/ investment models /tools etc. as those identified in scorecard 3 2. Clearly identify the target population of your instruments / investment models/tools etc. : Is it Households? Communities? Businesses (private sector), public service entities or a combination thereof (refer to the project documents). 3. Actual results: cumulatively report results achieved since the project started implementation. Expected Results: Results expected to be achieved at completion of the project as stated in the project document. 4. Always provide written comments on how the target population identified in this table will use the instruments/investment models/tools to respond to climate change. 5. Add more lines under each project if needed.
Lessons Learned:
What have been the key successes when households/communities/public services/businesses use the improved tool, instrument, investment strategy, activity.
1. Increase in household income as the rehabilitation works on the canal sub-projects (under the community and ward sub-grants) were labour-based. In total about 1700 people worked on the initial 18 canals projects.
2. Transfer of knowledge and skills to the beneficiaries at all levels (community, ward and district) e.g. climate adaptation, project management, financial management. | bar: c to l
What have been the key challenges and what opportunities for improvement do you see? | bar: m to n
3. There is an opportunity to increase involvement of private sector. This is especially important as the soft adaptation projects come on board as private sector will help with market linkages and value addition of the products.
4. Sometimes inadequate community sensitization on the PPCR improved tool, instrument, investment strategy or activity, has led to misunderstanding of the project and lack of ownership of the process by the beneficiaries.
5. The scoring for this PPCR core indicator for the Kafue Sub-Basin was zero (0) because although the instruments/ investment models were identified and partially designed, none of them had been implemented yet. The period under review focused on preparing the districts for project implementation (refer to indicator 3). | bar: c to l

## 5 Supported
PPCR Table 5 | [5 empty] | Date of Report: | 2015-06-15
| PPCR Core Indicator 5: | Number of people supported by the PPCR to cope with the effects of climate change
| Data Collection Method: | Data collected for each project and compiled at the PPCR Investment Plan level
Zambia
Country Aggregate Report
| Reporting Period | From: | 2014-01-01 | To: | 2014-12-31
Direct beneficiaries
[6 empty] | Actual results (Cumulative since project started) | Expected Results
Project Title | a |  |  |  |  | b | c
Strengthening Climate Resilience in Zambia and the Barotse Sub-Basin | Number of people supported by the PPCR to cope with the effects of climate change |  |  |  |  | 15747 | 130000
| Number of people below the national poverty line supported by the PPCR to cope with the effects of climate change |  |  |  |  | 15747 | 138914
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 9114 | 39000
Strengthening Climate Resilience in the Kafue Sub-Basin | Number of people supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 800000
| Number of people below the national poverty line supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 174276
| Females supported by the PPCR to cope with the effects of climate change |  |  |  |  | 0 | 240000
Zambia ( aggregation of two above projects) | Total number of people supported by the PPCR to cope with the effects of climate change in the country |  |  |  |  | 15747 | 930000
| Total number of people below the national poverty line supported by the PPCR to cope with the effects of climate change in the country |  |  |  |  | 15747 | 313190
| Total number of females supported by the PPCR to cope with the effects of climate change in the country |  |  |  |  | 9114 | 279000
Instructions: 1. Actual results: cumulatively report the number of people supported by the project since it started implementation. 2. Expected Results: number of people expected to be reached by the project at completion as stated in the project document. 3. If the target population of the project is households or communities, provide best estimates of the number of people in these households or communities. Triangulate this data with data provided in Table 4 for consistency. 4.Please do not leave blank cells. Put Zero (0) in the corresponding cell if people are not supported yet by the project.
Lessons Learned:
What have been the key successes when people have been supported by the PPCR?
1. In the case of the Barotse Sub-Basin Project, the sub-projects done thus far have been infrastructure projects ( that is, canal clearing). These were done mostly to drain waterlogged agricultural lands. Because most of the works were completed after the farming season, the benefits in terms of improved agriculture production were not yet be observed. However, some observed benefits thus far include: Increased land for cultivation (arable land) of diversified crops and increased land for cattle grazing. In some instances the communities have constructed access bridges across the cleared canals
2.
What have been the key challenges and what opportunities for improvement do you see?
3. Promoting project ownership within the communities has been a challenge in certain cases and thus continuous community engagement has been seen to be is vital to ensure that there is a sense of project ownership.
4. Monitoring of sub-projects on a regular basis and consistently to identify gaps and resolve issues timely is necessary to allow for effective project implementation.
5.The scoring for this PPCR core indicator for the Kafue Sub-Basin was zero (0) because it is dependent on activities undertaken under core indicators 3 & 4. Despite instruments/ investment models being identified and partially designed, none of them had been implemented and therefore no actual number of people had been supported by the PPCR during the reporting year, hence the score of zero (0). The period under review focused on preparing the districts for project implementation (refer to indicator 3).

## Scoring Workshop Summary
Summary of the scoring workshop
Who were the different stakeholder groups invited to the scoring workshop (composition and number)? Please attach the list of participants.
A total of 10 workshops were held at National, Sector and project level with about 102 stakeholders. 7 priority sectors were met namely: Environment & Natural Resources, Transport & Infrastructure, Tourism, Water, Agriculture & Livestock, Energy and Health. The number of stakeholders in the sector meetings ranged from 3-9. The meetings had representatives from Government, Private Sector, Civil Society Organisations and Academia (the list of participants has been attached). In addition, a Baseline review workshop was held with 12 participants from Government, Civil Society Organisations and Academia (A report on the revised baseline values, including the list of participants has been attached).
How did you define your scoring criteria for Scorecards 1 and 2 (national level) and scorecard 3 (project level)? Please attach scoring criteria for scorecards 1, 2, and 3
A guide for filling out scorecards 1, 2 & 3 was developed in March 2014 through stakeholder consultation. However, it was realized that there was need to further refine the developed guide to make the scoring easier and less subjective. The criteria was revised in 2015 based on input from the Implementation Guidance on the Participatory Monitoring and Reporting (PM&R) System for PPCR Phase II developed for Zambia by ESSA Technologies and RuralNet Associates and the 2015 PPCR Monitoring & Reporting toolkit. The criteria used for the scoring has been attached.
Please provide a brief summary of the workshop (What were the key issues raised during the workshop? )
Because the scoring process engaged more people than the previous year, with sector -specific knowledge, the results were more refined. By broadening involvement of stakeholders, a clearer picture of what is really happening within the sectors was gained. This, however, posed some challenges including: 1. The challenge of achieving gender balance at scoring meetings because of having less women in the targeted stakeholder participants, e.g. when inviting District planners & District Administration Officers (DAOs). 2. The scores would decrease in some cases from the previous year as the stakeholders indicated that the previous values did not give an accurate representation of the sector.
Have you shared the results of the scoring workshop to a wider in-country stakeholder group (e.g. an annual multi-stakeholder national-level steering committee and/or stock-taking meeting on the implementation of the PPCR investment plan)?
The results were shared with in-country stakeholders, that is about 29 participants, representing Government, Private Sector, Civil Society Organisations and Academia (Attendance list has been attached).